## Schedule Table
COA PROJECT TIMEFRAME ¦ ORIGINAL FORMAT, REVISED DATES
Historical Done rows follow the supplied plan. Later dates are proposed as of 10 Oct 2026; QA input due 16 Oct is a schedule condition.
Go Live target: 10 Dec 2026 ¦ Support: 11–18 Dec 2026 ¦ QA UAT approval and production window remain to be confirmed.
PHASE | ACTIVITIES | DELIVERABLES | START DATE | END DATE | STATUS
PREPARE | Project Initiation | Project scope and schedule defined | 2026-05-18 | 2026-05-22 | Done
| Discovery and Evaluation | Solutions discovered and evaluated | 2026-05-18 | 2026-05-22 | Done
| Business Process Map | Business process map defined | 2026-05-18 | 2026-05-29 | Done
EXPLORE | Business Blueprint Design | Business Blueprint Design completed and documented | 2026-05-25 | 2026-05-29 | Done
| Business Blueprint Confirmation & Finalization | Business Blueprint Design approved | 2026-05-25 | 2026-06-05 | Done
| Enhancement (RICEF) Design | RICEF Design documented | 2026-05-25 | 2026-06-05 | Done
| Authorization Requirement and Design | Authorization requirements and design documented | 2026-05-25 | 2026-06-05 | Done
| QA COA Templates, Header & Alias Confirmation | QA-approved COA master template, Export/Domestic header, and Product Alias examples | 2026-10-12 | 2026-10-16 | Waiting QA
| QA Barrier MIC/Plan & Batch List Confirmation | Confirmed Barrier MIC limits, SPSR0003 plan, and customer Batch List template | 2026-10-12 | 2026-10-16 | To Confirm
| Mapping Review & Test Scenario Approval | Customer/alias/outsource/multi-step rules and expected test results approved | 2026-10-19 | 2026-10-23 | Planned
REALIZE | Enhancement (RICEF) Development — Initial | Initial RICEF design developed | 2026-06-01 | 2026-08-07 | Done
| Run Scenario Test and Integration Test | Scenario/integration tests continued; revised scope retested and issues resolved | 2026-06-08 | 2026-11-20 | In Progress
| COA Mapping, Tracing & Limit Revision | Customer/alias mapping, four-step tracing, limits and out-of-spec display ready | 2026-10-26 | 2026-11-13 | Planned
| Barrier Inspection & Upload Revision | Manual/upload of three values, Last Value and sample correction ready | 2026-10-26 | 2026-11-13 | Planned
| COA Form, Batch List & Report Revision | Export/Domestic COA, Batch List and Report revisions ready | 2026-11-02 | 2026-11-13 | Planned
| Final Integration Test for Revisions | Barrier–COA–Batch List regression tested; defects triaged | 2026-11-16 | 2026-11-20 | Planned
| Prepare UAT and EUT | UAT scenarios, evidence sheets and EUT materials ready | 2026-11-16 | 2026-11-20 | Planned
DEPLOY | User Acceptance Test (UAT) | QA UAT approved after retest | 2026-11-23 | 2026-12-04 | Planned
| End User Training (EUT) | End users trained on COA and Barrier workflow | 2026-11-30 | 2026-12-04 | Planned
| Prepare Production System Environment | Production environment, transport and master data ready | 2026-12-07 | 2026-12-09 | Planned
| Cut-over Strategy | Production window, cutover steps and rollback plan approved | 2026-11-30 | 2026-12-04 | Planned
RUN | Go Live | COA and Barrier live in production | 2026-12-10 | 2026-12-10 | Planned
| Support After Go Live | Functional/technical issues monitored and resolved | 2026-12-11 | 2026-12-18 | Planned

## Gantt 2026
COA PROJECT TIMEFRAME ¦ REVISED 10 OCTOBER 2026
ACTIVITY | 2026
| MAY |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
| 01–07 | 08–14 | 15–21 | 22–EOM | 01–07 | 08–14 | 15–21 | 22–EOM | 01–07 | 08–14 | 15–21 | 22–EOM | 01–07 | 08–14 | 15–21 | 22–EOM | 01–07 | 08–14 | 15–21 | 22–EOM | 01–07 | 08–14 | 15–21 | 22–EOM | 01–07 | 08–14 | 15–21 | 22–EOM | 01–07 | 08–14 | 15–21 | 22–EOM
PREPARE
Project Initiation
Discovery and Evaluation
Business Process Map
EXPLORE
Business Blueprint Design
Business Blueprint Confirmation & Finalization
Enhancement (RICEF) Design
Authorization Requirement and Design
QA COA Templates, Header & Alias Confirmation
QA Barrier MIC/Plan & Batch List Confirmation
Mapping Review & Test Scenario Approval
REALIZE
Enhancement (RICEF) Development — Initial
Run Scenario Test and Integration Test
COA Mapping, Tracing & Limit Revision
Barrier Inspection & Upload Revision
COA Form, Batch List & Report Revision
Final Integration Test for Revisions
Prepare UAT and EUT
DEPLOY
User Acceptance Test (UAT)
End User Training (EUT)
Prepare Production System Environment
Cut-over Strategy
GO LIVE SUPPORT
Go Live | [29 empty] | GO
Support After Go Live
GREEN Done ¦ AMBER In Progress / To Confirm ¦ RED Waiting QA / Go Live ¦ GREY Planned
Proposed go live: 10 Dec 2026. Requires QA inputs by 16 Oct, UAT approval, and an agreed production cutover window.

## Schedule Changes
KEY DATE CHANGES AND ASSUMPTIONS
ACTIVITY | OLD PLAN | REVISED PLAN | REASON / CONDITION
QA input | MOM: 4 Oct 2026 | 16 Oct 2026 (proposed) | QA COA template and header had not been delivered as of 10 Oct; other QA items need status confirmation.
Integration test | 8 Jun–11 Sep 2026 | 8 Jun–20 Nov 2026 | Original testing remains In Progress in the supplied plan; revised scope needs final regression.
Prepare UAT / EUT | 31 Aug–4 Sep 2026 | 16–20 Nov 2026 | UAT package follows revised development and integration test.
UAT | 7–11 Sep 2026 | 23 Nov–4 Dec 2026 | QA sign-off depends on final templates, test cases and retest.
End User Training | 7–18 Sep 2026 | 30 Nov–4 Dec 2026 | Training follows near-final UAT build.
Production environment | 21–25 Sep 2026 | 7–9 Dec 2026 | Transport and master data readiness follow UAT sign-off.
Cut-over strategy | 21–25 Sep 2026 | 30 Nov–4 Dec 2026 | QA/production must approve cutover window and rollback plan.
Go Live | 28 Sep–2 Oct 2026 | 10 Dec 2026 target | Target depends on QA input by 16 Oct and agreed production window.
Support After Go Live | 2–31 Oct 2026 | 11–18 Dec 2026 | One-week initial support after the revised go live target.
If QA decisions or production cutover move, recalculate the remaining duration and agree a new target date.