## Slide 1
SAP CAPABILITY ENHANCEMENT & SIMPLIFICATION SAP Enhancement for Streamlined COA Workflow
Streamlining Quality Assurance by Retrieving Data Directly from SAP Result Recording, Significantly Reducing Lead Time and Eliminating Manual Entry Errors
PRESENT STATE
VALUE-DRIVEN RESULTS
QA / Inspector
Manual Process
COA
Manual
Manual copy inspection
Random inspection copying
Manual QA mapping
Manual data entry in COA
NEW REQUIREMENT
COA
COA Automation
Dynamic Mapping Matrix (By JR/SR)
Get Data from Result Recording
COA
Generated
COA
QA / Inspector
High Manual Effort
Multiple manual check and re-checks.
Data Inconsistency
Risk of human error and sample mismatch
High Accuracy
Eliminates manual data entry error & inconsistencies
Real Time Data
Updates from Result Recording & Mapping in real time
Manual data entry in COA
Impact
Faster COA Delivery
Significantly reduces COA lead time.
Improved Data Accuracy
Eliminates manual errors and ensures sample consistency.
Operational Efficiency
Reduce manual workload and rework, allowing QA to focus on value-added task.
Eliminate manual copying and manual data entry
Create dynamic QA mapping matrix (Film Type ⇔ Source Inspection)
Pull data automatically from Result Recording
Generate COA automatically (Delivery Order → Inspection → Result → COA)
Automate COA generation by pulling data directly from result recording, implement a dynamic QA mapping matrix to link film types with their designated source inspections, and eliminate manual data entry to ensure sample consistency, reduce lead time, and improve data accuracy.

## Slide 2
SAP CAPABILITY ENHANCEMENT & SIMPLIFICATION SAP Enhancement for Streamlined COA Workflow
Streamlining Quality Assurance by Retrieving Data Directly from SAP Result Recording, Significantly Reducing Lead Time and Eliminating Manual Entry Errors
Key Accomplishment:
PHASE | ACTIVITIES | DELIVERABLES | START DATE | END DATE | STATUS
PREPARE | Project Initiation | Project Scope & Schedule are Defined | 18-May-26 | 22-May-26 | Done
 | Discovery and Evaluation | Solutions are Discovered and Evaluated | 18-May-26 | 22-May-26 | Done
 | Business Process Map | Business Process Map Defined | 18-May-26 | 29-May-26 | Done
EXPLORE | Business Blueprint Design | Business Blueprint Design is completed and documented | 25-May-26 | 29-May-26 | Done
 | Business Blueprint Confirmation & Finalization | Business Blueprint Design is Approved | 25-May-26 | 5-Jun-26 | Done
 | Enhancement (RICEF) Design | RICEF Design is Documented | 25-May-26 | 5-Jun-26 | Done
 | Authorization Requirement and Design | Authorization Requirements and Design is Completed and Documented | 25-May-26 | 5-Jun-26 | Done
REALIZE | Enhancement (RICEF) Development | RICEF Design is Developed | 1-Jun-26 | 7-Aug-26 | Done
 | Run Scenario Test and Integration Test | Scenario and Integration Test are executed and Issues are resolved | 8-Jun-26 | 11-Sep-26 | In Progress
 | Prepare UAT and EUT | UAT and EUT Document are ready | 31-Aug-26 | 4-Sep-26 | Planned
DEPLOY | User Acceptance Test (UAT) | User Acceptance Test is Approved | 7-Sep-26 | 11-Sep-26 | Planned
 | End User Training (EUT) | End-Users are trained | 7-Sep-26 | 18-Sep-26 | Planned
 | Prepare Production System Environment | Production System Environment is Ready | 21-Sep-26 | 25-Sep-26 | Planned
 | Cut-over Strategy | Cut-over Strategy is Documented | 21-Sep-26 | 25-Sep-26 | Planned
RUN | Go Live | Live Production Environment | 28-Sep-26 | 28-Sep-26 | Planned
 | Support After Go Live | Functional or Technical Issues are Solved | 28-Sep-26 | 31-Oct-26 | Planned

## Slide 3
SAP CAPABILITY ENHANCEMENT & SIMPLIFICATION SAP Enhancement for Streamlined COA Workflow
Schedule:
Streamlining Quality Assurance by Retrieving Data Directly from SAP Result Recording, Significantly Reducing Lead Time and Eliminating Manual Entry Errors
Legend:
Planned
In Progress
Done
Proposed Milestone
Finished Milestone
We Are Here