## Project Team (hidden)
Process Expert | Accounting & Tax | Irianti, Lussy, Bunga
| Purchasing | Lisa Santoso
| PPIC | Gunaryanto, Eva, Anas, Agil, Nalom, Dillwyn
| Logistics | Eko Saifudin, Suhartono, Sampun Widodo
| Production | Laminator Production Team, Laminator Packing Team
| QA | Mugi
SAP Senior Consultant
SAP Consultant |  | Siti Maimunah | Arrandi | Rafly Septianarta | Rafly Septianarta | Wahyu Setya
|  |  | Alif Noor | Ana Balqis | Ana Balqis | Dwi Tyas
|  |  | Yuliana Prastiwi | Melania | Melania
|  |  |  | Aryo Satyo | Aryo Satyo
SAP ABAP Developer |  | Ryan, Budi Purwanto, Dila
UX Tool - Backend Developer |  | Rasyid, Nafianta, Krisna
OLAP & Meeting Pagi - Backend Developer |  | Taufiq, Adit, Malak
SAP BASIS |  | Sugik, Althof, Riza
IT Infrastrcuture |  | Fawwaz, Wijaya, Virgi
Steering Commitee
Sugeng Kurniawan, Hananto Indrakusuma, Santoso Handoyo, Silvester Terisno, Esther Darmawan,
Hans Chandra, Ervin Kohar, Tjiptono Richard, Abram Pranantya, Adi Yuda
Project Manager
Debie Shabastian Rosie
Business Process Owner
Ching Siong Lai, Hans Chandra, Hennie Susanto, Tjiptono Richard, Sayid Akhmad, Samsu Hidajat, Yuli Kurniawati,
Abram Pranantya
Solution Architects
Adi Yuda, Rysca, Alfa, Yunita, Ryan, Sugik
Finance and Controlling
Material Management & Plant Maintenance
Production Planning
Quality Management
Sales and Distribution

## Milestones General (GCG) (hidden)
ACTIVITY |  | 2024
|  | PHASE 1 | [8 empty] | PHASE 2
|  | NOV | DES |  |  | JAN |  | FEB |  | MAR |  | APR
PREPARE
Project Initiation | [6 empty] | ` |  | ` |  | ` |  | `
Discovery and Evaluation
Business Process Map
EXPLORE |  |  |  | 10 | 12
Business Blueprint Design
Business Blueprint Confirmation & Finalization
Enhancement (RICEF) Design
Configuration Design
Authorization Requirements and Design
REALIZE
Configuration and Documentation
Enhancement (RICEFW) Development
Run Scenario Test and Integration Test
Quality Assurance Environment (QAS): Roles and Transport
Quality Assurance Environment (QAS): Data Load
Prepare End User Training and User Acceptance Test Delivery
DEPLOY
Pre Go-Live End-User Training Delivery
User Acceptance Test (UAT)
Production System Environment
Helpdesk Setup
RUN
Go Live
Post Go-Live End-User Training Delivery
Support After Go Live
Done
In Progress
Planned
Finished Milestone
Planned Milestone
EXPLORE
PREPARE
REALIZE
RUN
RUN 1
RUN 2
DEPLOY

## Milestones General (CR) ALT1 (hidden)
ACTIVITY |  | 2024 |  |  |  | 2025
|  | PHASE 1 | [10 empty] | PHASE 2
|  | NOV | DES |  |  | JAN |  | FEB |  | MAR |  | APR |  | MAY
PREPARE
Project Initiation | [6 empty] | ` |  | ` |  | ` |  | ` |  | `
Discovery and Evaluation
Business Process Map
EXPLORE |  |  |  | 10 | 12
Business Blueprint Design
Business Blueprint Confirmation & Finalization
Enhancement (RICEF) Design
Configuration Design
Authorization Requirements and Design
REALIZE
Configuration and Documentation
Enhancement (RICEFW) Development
Run Scenario Test and Integration Test
Quality Assurance Environment (QAS): Roles and Transport
Quality Assurance Environment (QAS): Data Load
Prepare End User Training and User Acceptance Test Delivery
DEPLOY
Pre Go-Live End-User Training Delivery
User Acceptance Test (UAT)
Production System Environment
Helpdesk Setup
RUN
Go Live
Support After Go Live
Done
In Progress
Planned
Finished Milestone
Planned Milestone
EXPLORE
PREPARE
REALIZE
RUN
RUN 1
RUN 2
DEPLOY

## Milestones General
ACTIVITY | 2026
| MAY | JUNE | JULY | JAN | AUG | SEP | OCT | NOV
PREPARE
Project Initiation
Discovery and Evaluation
Business Process Map
EXPLORE
Business Blueprint Design
Business Blueprint Confirmation & Finalization
Enhancement (RICEF) Design
Authorization Requirements & Design
REALIZE
Enhancement (RICEFW) Development
Run Scenario Test and Integration Test
Prepare UAT and EUT Delivery
DEPLOY
User Acceptance Test (UAT)
End-User Training Delivery
Prepare Production System Environment
Cut-over Strategy
GO LIVE SUPPORT
Go Live
Support After Go Live
PRE
EXP
REALIZE
RUN
RUN
DEP

## Schedule
PHASE | ACTIVITIES | DELIVERABLES | START DATE | END DATE | STATUS
PREPARE | Project Initiation | Project Scope & Schedule are Defined | 2026-05-18 | 2026-05-22 | Done
| Discovery and Evaluation | Solutions are Discovered and Evaluated | 2026-05-18 | 2026-05-22 | Done
| Business Process Map | Business Process Map Defined | 2026-05-18 | 2026-05-29 | Done
EXPLORE | Business Blueprint Design | Business Blueprint Design is completed and documented | 2026-05-25 | 2026-05-29 | Done
| Business Blueprint Confirmation & Finalization | Business Blueprint Design is Approved | 2026-05-25 | 2026-06-05 | Done
| Enhancement (RICEF) Design | RICEF Design is Documented | 2026-05-25 | 2026-06-05 | Done
| Authorization Requirement and Design | Authorization Requirements and Design is Completed and Documented | 2026-05-25 | 2026-06-05 | Done
REALIZE | Enhancement (RICEF) Development | RICEF Design is Developed | 2026-06-01 | 2026-08-07 | Done
| Run Scenario Test and Integration Test | Scenario and Integration Test are executed and Issues are resolved | 2026-06-08 | 2026-09-11 | In Progress
| Prepare UAT and EUT | UAT and EUT Document are ready | 2026-08-31 | 2026-09-04 | Planned
DEPLOY | User Acceptance Test (UAT) | User Acceptance Test is Approved | 2026-09-07 | 2026-09-11 | Planned
| End User Training (EUT) | End-Users are trained | 2026-09-07 | 2026-09-18 | Planned
| Prepare Production System Environment | Production System Environment is Ready | 2026-09-21 | 2026-09-25 | Planned
| Cut-over Strategy | Cut-over Strategy is Documented | 2026-09-21 | 2026-09-25 | Planned
RUN | Go Live | Live Production Environment | 2026-09-28 | 2026-10-02 | Planned
| Support After Go Live | Functional or Technical Issues are Solved | 2026-10-02 | 2026-10-31 | Planned

## WBS
ACTIVITY | W01 | PIC | JUL '25 | [30 empty] | AUG '25 | [30 empty] | SEP '25
|  |  | W1 | [5 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11 | [6 empty] | W12 | [6 empty] | W13
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
PREPARE | 50%
1.1 Project Initiation | 100% | bar: W1 1
1.2 Discovery and Evaluation | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
1.2.1 SAP Discovery and Evaluation | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
Sales and Distribution | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
DISC-SD-... | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
Production Planning | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
DISC-PP-... | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
ABAP | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
DISC-ABAP-SOAUTO-01 Flow Program ZPP001L | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
DISC-ABAP-SOAUTO-02 Program Create SO | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
DISC-ABAP-SOAUTO-03 Program Free to SO | 0% | bar: W1 1 to W1 4; W2 7 to W2 11; W3 14 to W3 18
EXPLORE | 0%
2.1 Business Blueprint Design | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.1.1 Sales and Distribution | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
SD01 ... | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
SD02 ... | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
SD03 ... | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.2 Business Blueprint Confirmation & Finalization | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.2.1 End to End Business Process | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
BP-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
BP-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
BP-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.2.2 Sales and Distribution | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
BP-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
BP-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
BP-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.3 Enhancement (RICEFW) Design | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.3.1 Sales & Distribution-Production Planning | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
RICEFW-SDPP-SOAUTO-01 Create SO Automation from ZPP001L | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.4 Authorization Requirements and Design | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.4.1 Sales and Distribution | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
RICEFW-SD-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
2.4.2 Production Planning | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
RICEFW-PP-… | 0% | bar: W3 14 to W3 18; W4 21 to W4 25
REALIZE | 0%
3.1 Enhancement (RICEFW) Development | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8
3.1.1 DEV NC | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8
3.1.1.1 Sales & Distribution-Production Planning | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8
RICEFW-SDPP-SOAUTO-01 Create SO Automation from ZPP001L | 0% | Budi | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8
1. Get SO reference based on PO | bar: W4 21 to W4 25
2. Get detail SO reference | bar: W4 21 to W4 25
3. Create new SO item based on GRN data | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8
4. Free to SO | bar: W5 28 to W5 1; W6 4 to W6 8
5. Cancel Free to SO | bar: W6 4 to W6 8
3.1.2 DEV AIX | 0% | bar: W5 28 to W5 1; W6 4 to W6 8
3.1.2.1 Sales & Distribution-Production Planning | 0% | bar: W5 28 to W5 1; W6 4 to W6 8
RICEFW-SDPP-SOAUTO-01 Create SO Automation from ZPP001L | 0% | Budi | bar: W5 28 to W5 1; W6 4 to W6 8
1. Get SO reference based on PO | bar: W5 28 to W5 1; W6 4 to W6 8
2. Get detail SO reference | bar: W5 28 to W5 1; W6 4 to W6 8
3. Create new SO item based on GRN data | bar: W5 28 to W5 1; W6 4 to W6 8
4. Free to SO | bar: W5 28 to W5 1; W6 4 to W6 8
5. Cancel Free to SO | bar: W5 28 to W5 1; W6 4 to W6 8
3.2 Run Scenario Test and Integration Test | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.2.1 Scenario Testing SAP | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.2.1.1 DEV AIX | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.2.1.1.1 Sales & Distribution-Material Management-Production Planning | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
RICEFW-SDPP-SOAUTO-01 Create SO Automation from ZPP001L | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.2.1.2 QA 320 | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.2.1.2.1 Sales & Distribution-Material Management-Production Planning | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
RICEFW-SDPP-SOAUTO-01 Create SO Automation from ZPP001L | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.2.2 Integration Testing SAP | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
DEV AIX | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
QA 320 | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
UT-IT INV- .. | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
UT-IT INV- .. | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.3 Prepare End User Training and User Acceptance Test Delivery | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.3.1 Prepare dokumen EUT | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
3.3.2 Prepare dokumen UAT | 0% | bar: W4 21 to W4 25; W5 28 to W5 1; W6 4 to W6 8; W7 11 to W7 15
DEPLOY | 0%
4.1 User Acceptance Test (UAT) | 0% | bar: W7 11 to W7 15; W8 18 to W8 22
4.2 End-User Training Delivery | 0% | bar: W7 11 to W7 15; W8 18 to W8 22
4.3 Prepare Production System Environment | 0% | bar: W7 11 to W7 15; W8 18 to W8 22
4.4 Cut-over Strategy | 0% | bar: W7 11 to W7 15; W8 18 to W8 22
GO LIVE AND SUPPORT | 0%
Go Live | 0% | bar: W9 25
Support After Go Live | 0% | bar: W9 25 to W9 29; W10 1 to W10 5; W11 8 to W11 12; W12 15 to W12 19; W13 22 to W13 26
10%
*WBS ini bisa berubah sewaktu waktu menyesuaikan dengan Situasi, Kondisi atau untuk kebutuhan memperbaiki management project.
LEGEND
Planned Milestone
Planned
In Progress
Finish
Solutions are discovered and evaluated
Project Charter, Project Management Plan, Project Organization, and WBS is Defined
0 of 0 Enhancement (RICEFW) Design is completed and documented
0 of 0 Business Blueprint Design is approved
0 of 0 Business Blueprint Design is documented
Authorization Design is completed and documented
Enhancement is Finished and Documented
Testing is Executed and OK
EUT and UAT are Prepared
EUT are Well Executed
UAT are Well Executed
Production System Environment are Ready and Documented
Go Live
Cut-over Strategy is Documented

## Project Teams
SAP Senior Consultant
SAP SD | Aldi Dwi Kusuma
SAP PP | Aryo Satyo, Indah Rahayu
SAP ABAP | Budi Purwanto
Steering Commitee
Silvester Terisno, Adi Yuda
Project Manager
Budi Purwanto
Business Process Owner
Garry Geraldy
Solution Architects
Adi Yuda, Alfa

## BP DATA (hidden)
Week# | Module | Blueprint Name | PIC | Development (%) | Development (GCG) | Confirmation & Finalization (%) | Confirmation & Finalization (GCG) | Date | Status | Cancel Reason | Priority
W01 | Production Planning | BP-… |  | 0% |  | 0%

## CONFIGURATION DATA (hidden)
Week# | Module | Configuration Name | PIC | Development DEV 100 (%) | Development (GCG) | Date | Development DEV 130 (%) | Development (GCG) | Date | Development QA 320 (%) | Development (GCG) | Date | Status | Cancel Reason | Tcode | Tcode Desc
| Production Planning |  |  | 0% |  |  | 0% |  |  | 0%

## RICEF DATA (hidden)
Week# | Module | RICEF Name | PIC Functional | PIC ABAP | Development Design(%) | Technical Specification | Development (%) | Development (GCG) | Date | Status | Cancel Reason | Tcode | Tcode Desc
| Sales & Distribution-Production Planning | RICEFW-SDPP-XXXX-01 Create SO Automation from ZPP001L |  | Budi | 0% | 0% | 0%

## External Factor (hidden)
Function | Factor Type | Date From | Date To | Support/Project | Project | Description | PIC | Days | Hours | Status | Note
W02
FICO | External |  |  | Support | Anti Dumping |  |  |  |  | In Progress
PP | External |  |  | Support | CCS |  |  |  |  | In Progress
ABAP | External |  |  | Support | CCS |  |  |  |  | In Progress
BE | External |  |  | Support | CCS |  |  |  |  | In Progress
W04
FICO | External |  |  | Support | Anti Dumping |  |  |  |  | In Progress
PP | External |  |  | Support | CCS |  |  |  |  | In Progress
ABAP | External |  |  | Support | CCS |  |  |  |  | In Progress
BE | External |  |  | Support | CCS |  |  |  |  | In Progress
W05
ALL Functional | External | 2024-11-25 | 2024-11-28 | Support | Audit ISO |  |  |  |  | In Progress
PP | External |  |  | Support | CCS |  |  |  |  | In Progress
ABAP | External |  |  | Support | CCS |  |  |  |  | In Progress
BE | External |  |  | Support | CCS |  |  |  |  | In Progress
CO | External |  |  | Support | Testing SBU |  |  |  |  | In Progress
W09
MM | External |  |  | Support | PPN 12% |  |  |  |  | In Progress
SD | External |  |  | Support | PPN 12% |  |  |  |  | In Progress
W10
MM | External |  |  | Support | AAF |  |  |  |  | In Progress
MM | External |  |  | Support | Enhancement SBU |  |  |  |  | In Progress
PP | External |  |  | Support | Enhancement SBU |  |  |  |  | In Progress

## Assessment Criteria (hidden)
Prepare Development Environment
0% | Belum dikerjakan
50% | In progress
100% | Done
Project Team Training
0% | Belum dilakukan
50% | In progress File Training
75% | File Done, Training not yet
100% | Done
Business Blueprint Design |  | Business Blueprint Confirmation & Finalization |  |  | RICEF Design
0% | Blueprint belum dibuat | 0% | Blueprint belum divalidasi |  | 0% | RICEF belum dibuat
25% | Flow telah dibuat | 25% | Blueprint telah divalidasi namun belum dikonfirmasi |  | 25% | In progress pembuatan RICEF
50% | Flow + Design UI telah dibuat | 50% | Blueprint telah dikonfirmasi |  | 50% | 3 Sheet pada file RICEF selesai, sheet-nya antara lain Overview, Functionality, Validation, dan Transaction
75% | Flow, Design UI + RICEF telah dibuat | 75% | Blueprint dalam tahap Finalization |  | 75% | Semua sheet pada file RICEF selesai dibuat
100% | Flow, Design UI, RICEF + Validasi telah dibuat | 100% | Blueprint Document telah selesai () |  | 90% | Semua file pendukung RICEF (1 folder dengan RICEF) selesai dibuat
[5 empty] | 100% | Semua file pendukung RICEF (folder Table Structure dan Configuration Data) selesai dibuat
RICEF Development (Backend) |  | RICEF Development (Frontend) |  |  | RICEF Development (ABAP) |  | RICEF Development (PDA Apps)
0% | RICEF belum didevelop | 0% | RICEF belum didevelop |  | 0% | RICEF belum didevelop | 0% | RICEF belum didevelop
25% | Struktur parameter telah didevelop | 20% | Screen telah di develop |  | 25% | RICEF baru mulai ngerjakan | 25% | RICEF baru mulai ngerjakan
50% | Validasi RICEF telah didevelop | 40% | Web Service telah di develop |  | 50% | RICEF sudah hampir selesai | 50% | RICEF sudah hampir selesai
75% | RICEF telah selesai & siap ditesting | 60% | Controller telah di develop |  | 75% | RICEF telah selesai & siap ditesting | 75% | RICEF telah selesai & siap ditesting
100% | RICEF telah ditesting & sudah OK | 80% | Semua komponen telah selesai & siap ditesting |  | 100% | RICEF telah ditesting & sudah OK | 100% | RICEF telah ditesting & sudah OK
|  | 100% | Frontend telah di testing & sudah OK
Discovery and Evaluation
0% | Belum dilakukan
25% | In progress discovery
75% | Discovery telah selesai, dokumen belum dibuat
100% | Discovery telah selesai, dokumen telah dibuat
Scenario Test
0% | Testing belum dilakukan
25% | Testing in Progress
50% | Testing selesai dilakukan (Cycle 1), terdapat status Not OK
75% | Testing selesai dilakukan (Cycle berikutnya), terdapat status Not OK
100% | Semua sheet pada dokumen selesai dibuat, Perbaikan selesai dilakukan dan Semua status OK
Configuration Design |  |  |  | Configuration and Documentation
0% | Design belum dibuat |  |  | 0% | Configuration belum dilakukan
25% | Table telah di download |  |  | 25% | Configuration in progress
50% | Design in Progress |  |  | 50% | Configuration in progress, table sedang di compare
75% | Design dan table telah siap, belum di review |  |  | 75% | Configuration selesai, table compare sesuai, belum di review
100% | Design telah selesai, sudah di review |  |  | 100% | Configuration selesai, table compare sesuai, sudah di review

## PP (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela | DISC-PP-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List Config New Production Line | Done | 100% | 08 -11-2024
Ana | DISC-PP-LAM02 Enhancement List | Mengetahui Program-Program SAP yang akan terimpact dengan adanya project Laminator | Program-Program SAP yang akan terimpact dengan adanya project Laminator diketahui | Done | 100% | 2024-11-15
W01 (08 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-PP-LAM04 Defining Order Type for Laminator #2 #3 | Order type Baru ready | List Config Order Type | Done | 100% | 08 -11-2024
Ana, Mela | DISC-PP-LAM02 Enhancement List | Enhancement List for New Production Line Laminator #2 & #3 are Discovered | Discovery New Enchancement | Done | 100% | 08 -11-2024
Ana | DISC-PP-LAM05 Defining Number Range for Order for Laminator #2 #3 | Number Range For Original Order are ready | List Config Number Order | Done | 100% | 08 -11-2024
Ana | DISC-PP-LAM20 Subcont CKI | Subcont CKI are Discovered | List New Enchacement Subcont CKI | Done | 100% | 2024-12-20
Mela | DISC-PP-LAM09 Configuration Creating Class for Laminator #2 #3 | Mengumpulkan data class JR dan SR Laminate. | Discovery List Class JR SR Desain | Done | 100% | 08 -11-2024
Mela | DISC-PP-LAM14 Configuration Defining Characteristic for Laminator #2 #3 | Mengumpulkan data class karakteristik JR dan SR Laminate (ZZPRODLINE) | Discovery List Karakteristik New Prodline Baru Desain | Done | 100% | 08 -11-2024
Mela | DISC-PP-LAM15 Maintain Table ZTMAP for Laminator #2 #3 | List table ZTMAP ZTMAP_SLOC_JR_GR, ZTMAP_SLOCFILM, ZTMAP_SLOCRR dan ZSEQNUM. | Desain List New Enchament | Done | 100% | 09 -11-2024
Ana | DISC-PP-LAM02 Enhancement List | Mengetahui Program-Program SAP yang akan terimpact dengan adanya project Laminator | Program-Program SAP yang akan terimpact dengan adanya project Laminator diketahui | Done | 100% | 2024-11-15
W02 (11 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | DISC-PP-LAM03 T-Code Variant List | List T-Code Variant (ZPP041 eksekusi jr, ZPP060 gi/rm, ZPP026 eksekusi jr) | Desain New Enchament | Done | 100% | 11 -11-2024
Ana,Mela,Aryo | DISC-PP-LAM20 Subcont CKI | Integration testing di dev nc | Integration Testing selesai, solution discovered | Done | 25% | 2024-11-12
Ana | DISC-PP-LAM02 Enhancement List | Mengetahui Program-Program SAP yang akan terimpact dengan adanya project Laminator | Program-Program SAP yang akan terimpact dengan adanya project Laminator diketahui | Done | 100% | 2024-11-15
W02 (12 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | DISC-PP-LAM18 Maintain Resource for Laminator #2 #3 | Desain Config Resource Process dan Slitter | Desain New Enchancement | Done | 100%
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario I Goods Receipt Material Using 101 B; 2 BATCH BF>CKI Cancel Confirmation; 4 BATCH BF=CKI | Integration Testing for Scenario I Goods Receipt Material Using 101 B; 2 BATCH BF>CKI Cancel Confirmation; 4 BATCH BF=CKI selesai | Done | 100% | 2024-11-12
Ana | DISC-PP-LAM02 Enhancement List | Mengetahui Program-Program SAP yang akan terimpact dengan adanya project Laminator | Program-Program SAP yang akan terimpact dengan adanya project Laminator diketahui | Done | 100% | 2024-11-15
W02 (13 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | DISC-PP-LAM19 Maintain HR Assignment for Laminator #2 #3 | Desain Config Resource Process dan Slitter | Desain New Enchancement for HRMS | Done | 100% | 2024-11-13
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario J Goods Receipt Material Using 563 E w/ Confirmation SR 0; Ukuran BF=CKI | Integration Testing for Scenario J Goods Receipt Material Using 563 E w/ Confirmation SR 0; Ukuran BF=CKI selesai | Done | 100% | 2024-11-13
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario K Goods Receipt Material Using 563 E w/ Confirmation; Ukuran BF=CKI | Integration Testing for Scenario K Goods Receipt Material Using 563 E w/ Confirmation; Ukuran BF=CKI selesai | Done | 100% | 2024-11-13
Ana | DISC-PP-LAM06 Defining Order Type Dependent Parameter for Laminator #2 #3 | Order Type Dependent Parameter for Laminator are Defined | Config Dependent Parameter | Done | 100% | 2024-11-13
Mela | DISC-PP-LAM18 Maintain Resource for Laminator #2 #3 | Desain Config Resource Process dan Slitter | Desain New Enchancement for Resource | Done | 100% | 2024-11-13
Ana | DISC-PP-LAM02 Enhancement List | Mengetahui Program-Program SAP yang akan terimpact dengan adanya project Laminator | Program-Program SAP yang akan terimpact dengan adanya project Laminator diketahui | Done | 100% | 2024-11-15
W02 (14 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | DISC-PP-LAM19 Maintain HR Assignment for Laminator #2 #3 | Desain Config Resource Process dan Slitter | Desain New Enchancement for HRMS | Done | 30% | 2024-11-13
Mela | DISC-PP-LAM18 Maintain Resource for Laminator #2 #3 | Desain Config Resource Process dan Slitter | Desain New Enchancement for Resource | Done | 25%
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario L Goods Receipt Material Using 563 E w/ BF Lami Confirmation SR 0; Ukuran BF>CKI | Integration Testing for Scenario L Goods Receipt Material Using 563 E w/ BF Lami Confirmation SR 0; Ukuran BF>CKI selesai | Done | 100% | 2024-11-14
Ana | DISC-PP-LAM02 Enhancement List | Mengetahui Program-Program SAP yang akan terimpact dengan adanya project Laminator | Program-Program SAP yang akan terimpact dengan adanya project Laminator diketahui | Done | 75% | 2024-11-15
W02 (15 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting selesai | Done | 100% | 2024-11-15
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting selesai | Done | 100% | 2024-11-15
Ana | DISC-PP-LAM02 Enhancement List | Mengetahui Program-Program SAP yang akan terimpact dengan adanya project Laminator | Program-Program SAP yang akan terimpact dengan adanya project Laminator diketahui | Done | 100% | 2024-11-15
Ana, Mela, Aryo,Rafly | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Mengetahui kondisi As-Is UX Tools | Kondisi As-Is UX Tools Diketahui | Done | 100% | 2024-11-15
W03 (18 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting selesai | Done | 100% | 2024-11-18
Mela | DISC-PP-LAM18 Maintain Resource for Laminator #2 #3 | Desain Config Resource Process dan Slitter | Config Resource Process and Slitter | Done | 25%
Mela | DISC-PP-LAM19 Maintain HR Assignment for Laminator #2 #3 | Desain Config HRMS | Config HRMS | Done | 30% | 2024-11-13
W03 (19 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting selesai | Done | 100% | 2024-11-19
Ana | DISC-PP-LAM10 Configuration Specifying Scheduling Parameters for Laminator #2 #3 | Specifying Shceduling paramater for laminator are define | Specifying Shceduling paramater for laminator are define | Done | 100% | 2024-11-19
Ana | DISC-PP-LAM11 Configuration Defining Checking Controls for Laminator #2 #3 | Checking Controls are Defined | Checking Controls are Defined | Done | 100% | 2024-11-19
Ana | DISC-PP-LAM12 Configuration Defining Confirmation Parameters for Laminator #2 #3 | Confirmation Parameters are Defined | Confirmation Parameters are Defined | Done | 100% | 2024-11-19
Ana | DISC-PP-LAM13 Configuration Defining Default Values – Task List Selection for Laminator #2 #3 | Default Values- Task List are defined | Default Values- Task List are defined | Done | 100% | 2024-11-19
Mela | DISC-PP-LAM18 Maintain Resource for Laminator #2 #3 | Desain Config Resource Process dan Slitter | Desain Config Resource Process dan Slitter | Done | 25%
W03 (20 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 25% | 2024-12-03
W03 (21 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 25% | 2024-12-03
W03 (22 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 50% | 2024-12-20
W04 (25 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 50% | 2024-12-03
W04 (26 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 50% | 2024-12-03
W04 (27 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 50% | 2024-12-03
W04 (28 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 50% | 2024-12-03
W04 (29 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 75% | 2024-12-03
W05 (02 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 75% | 2024-12-03
Ana, Mela, Aryo | DISC-NONSAP-LAM03 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Master Data PP for UX Tools | Master Data PP for UXTool telah dikirim ke UX Tools | Done | 75% | 2024-12-03
W05 (03 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Discovery cara tracebility roll customer yang telah diproduksi | Roll Customer dapat ditrace meskipun telah masuk produksi Trias | Done | 100% | 2024-12-03
Ana, Mela, Aryo | DISC-NONSAP-LAM03 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Master Data PP for UX Tools | Master Data PP for UXTool telah dikirim ke UX Tools | Done | 100% | 2024-12-03
W05 (04 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM1-20 Subcont CKI | Review New config for Laminator 2 &3 | List config laminator 2 & 3 telah direview | Done | 100% | 2024-12-04
W05 (05 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | Diskusi SWOT analysis untuk Movement type Penerimaan barang subcont | SWOT analysis terbentuk | Done | 100% | 2024-12-05
W05 (06 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-PP-LAM20 Subcont CKI | Diskusi dengan Mbak alfa dan mbak debie mengenai Bisnis Proses Subcontracted | Bisnis Proses subcontracted tergambar | Done | 50% | 2024-12-09
Ana | DISC-PP-LAM20 Subcont CKI | Discovery Bisnis Proses DL00-50 (Jual JR) | Bisnis Proses DL00-50 saat ini dapat digunakan sebagai acuan subcont | Done | 100% | 2024-12-06
W06 (09 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-PP-LAM20 Subcont CKI | Diskusi dengan Mbak alfa dan mbak debie mengenai Bisnis Proses Subcontracted | Bisnis Proses subcontracted tergambar | Done | 100% | 2024-12-09
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | Menaikkan master data skenario testing 1-6 diserver NC | Master data untuk testing skenario 1-6 ada di server NC | Done | 50% | 2024-12-10
W06 (10 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | Menaikkan master data skenario testing 1-6 diserver NC | Master data untuk testing skenario 1-6 ada di server NC | Done | 100% | 2024-12-10
W06 (11 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | testing Skenario 2C, 4A, 4B | testing mulai Planning hingga produksi SR Selesai | Done | 100% | 2024-12-11
W06 (12 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | testing Skenario 6A, 6B | testing mulai Planning hingga produksi SR Selesai | Done | 100% | 2024-12-12
W06 (13 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | testing Skenario 1A | testing mulai Planning hingga produksi SR Selesai (Produksi JR dilakukan manual) | Done | 100% | 2024-12-13
W07 (16 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | testing Skenario 1B | testing mulai Planning hingga produksi SR Selesai (Produksi JR dilakukan manual) | Done | 100% | 2024-12-16
W07 (17 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | testing Skenario 2A | testing mulai Planning hingga produksi SR Selesai (Produksi JR dilakukan manual) | Done | 100% | 2024-12-17
W07 (18 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela,Aryo | DISC-PP-LAM20 Subcont CKI | testing Skenario 5A , 5B | testing mulai Planning hingga produksi SR Selesai (Produksi JR dilakukan manual) | Done | 100% | 2024-12-18
W07 (19 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-PP-LAM20 Subcont CKI | Scenario Testing 7C | Planning dan Eksekusi skenario 7C selesai | Done | 100% | 2024-12-19
Mela | DISC-PP-LAM20 Subcont CKI | Scenario Testing 7A | Planning dan Eksekusi skenario 7A selesai | Done | 100% | 2024-12-19
Aryo | DISC-PP-LAM20 Subcont CKI | Scenario Testing 7B | Planning dan Eksekusi skenario 7B selesai | Done | 100% | 2024-12-19
W07 (20 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela, Aryo | DISC-PP-LAM20 Subcont CKI | Scenario Testing 8A,8B | Planning dan Eksekusi skenario 8A dan 8B | Done | 100% | 2024-12-20
Mela | DISC-PP-LAM20 Subcont CKI | Inspect RM dari MM untuk produksi mixing | RM mixing produksi dan inspeksi selesai | Done | 100% | 2024-12-20
Mela | DISC-PP-LAM20 Subcont CKI | Menaikkan master data baru JRWCYI dan SRWCYI | Material Baru selesai | Done | 100% | 2024-12-20
Ana | DISC-PP-LAM20 Subcont CKI | Menaikkan master data baru JRVDCI dan SRVDCI | Material Baru selesai | Done | 100% | 2024-12-20
Ana, Mela, Aryo, Rafly | DISC-PP-LAM20 Subcont CKI | Diskusi One Button dengan tim Abap (mas budi) dan MM (mas randi) | Desain One Button telah terbentuk | Done | 50% | 2024-12-23
W08 (23 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Aryo, Mela | DISC-PP-LAM20 Subcont CKI | Scenario Testing 8A dan 8B | Planning dan Eksekusi 8A dan 8B | Done | 100% | 2024-12-21
Mela | DISC-PP-LAM20 Subcont CKI | Inspect mat O dari MM untuk produksi mixing | RM mixing produksi dan inspeksi selesai | Done | 100% | 2024-12-21
Mela | DISC-PP-LAM20 Subcont CKI | Inspect RM dari MM untuk produksi mixing | RM mixing produksi dan inspeksi selesai | Done | 100% | 2024-12-21
Ana, Mela, Aryo, Rafly | DISC-PP-LAM20 Subcont CKI | Diskusi One Button dengan tim Abap dan MM | Desain One Button telah terbentuk | Done | 100% | 2024-12-23
W08 (24 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | PPPE11 Production Process of Jumbo Roll Laminating V2 | Blueprint Production Process Jumbo Roll Laminating | Blueprint Production Process Jumbo Roll Laminating pengecekan | Done | 10% | 2024-12-24
Ana, Mela, Aryo, Rafly | RICEFW-PP-LAMI2&3-28 One Button | Diskusi One Button dengan tim Abap dan MM | One Button design review | Done | 100% | 2024-12-24
W08 (26 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | PPPE11 Production Process of Jumbo Roll Laminating V2 | Blueprint Production Process Jumbo Roll Laminating | Blueprint Production Process Jumbo Roll Laminating ditambahkan perubahan | Done | 90% | 2024-12-26
Mela | PPPE12 Production Process of Slit Roll Laminating V2 | Blueprint Production Process Slit Roll | Blueprint Production Process Jumbo Roll Slit Roll ditambahkan perubahan | Done | 90% | 2024-12-26
Aryo | Business Blueprint-General Setting (Updated for LMN WR) | Blueprint General Setting | Blueprint General Setting ditambahkan perubahan | Done | 100% | 2024-12-26
Ana | PPPB01-Pengembangan Produk Baru (Updated for LAMI) | Blueprint Pengembngan Produk Baru | Blueprint Pengembngan Produk Baru ditambahkan perubahan | Done | 100% | 2024-12-26
Aryo | PPPE17 Production Process of Mixing (Updated for LMN WR) | Blueprint General Setting dan Mixing | Blueprint General Setting dan Mixing ditambahkan perubahan | Done | 100% | 2024-12-26
Ana | 2.1 Business Blueprint Design | Blueprint Confirmation | Blueprint Confirmation progress selesai | Done | 100% | 2024-12-26
Ana, Mela, Aryo, Rafly | RICEFW-PP-LAMI2&3-28 One Button | Diskusi One Button dengan tim Abap dan MM | Diskusi One Button dengan tim Abap dan MM perubahan diketahui | Done | 100% | 2024-12-26
W08 (27 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060.docx | Melakuka discovery perubahan yang dilakukan | Melakuka discovery perubahan yang dilakukan | Done | 50% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | Ricef Already done | Ricef Already done | Done | 10% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-15 T-Code Variant ZPP026L2 | Ricef Already done | Ricef Already done | Done | 10% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-16 T-Code Variant ZPP026L3 | Ricef Already done | Ricef Already done | Done | 10% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-17 T-Code Variant ZPP041L2 | Ricef Already done | Ricef Already done | Done | 10% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-18 T-Code Variant ZPP041L3 | Ricef Already done | Ricef Already done | Done | 10% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-26 Hard Code Title Bar T-Code Variant | Ricef Already done | Ricef Already done | Done | 10% | 2024-12-30
Mela | RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060.docx | Melakuka discovery perubahan yang dilakukan | Melakuka discovery perubahan yang dilakukan | Done | 50% | 2024-12-30
Mela | RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M.docx | Melakuka discovery perubahan yang dilakukan | Melakuka discovery perubahan yang dilakukan | Done | 50% | 2024-12-30
Mela | RICEFW-PP-LAMI2&3-14 Hard Code Material Group ZPP018.docx | Melakuka discovery perubahan yang dilakukan | Melakuka discovery perubahan yang dilakukan | Done | 50% | 2024-12-30
Ana, Mela, Aryo, Rafly | DISC-PP-LAM20 Subcont CKI | Diskusi One Button dengan tim Abap dan MM | Diskusi One Button dengan tim Abap dan MM diketahui | Done | 100% | 2024-12-30
W09 (30 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | Ricef Already done | Buat Ricef penambahan di tcode zpp041 | Done | 50% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-15 T-Code Variant ZPP026L2 | Ricef Already done | Buat Ricef penambahan ditcodr zpp026L2 | Done | 100% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-16 T-Code Variant ZPP026L3 | Ricef Already done | Buat Ricef penambahan ditcodr zpp026L3 | Done | 100% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-17 T-Code Variant ZPP041L2 | Ricef Already done | Buat Ricef penambahan ditcode zpp041l2 | Done | 100% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-18 T-Code Variant ZPP041L3 | Ricef Already done | Buat Ricef penambahan ditcode zpp041l3 | Done | 100% | 2024-12-30
Ana | RICEFW-PP-LAMI2&3-26 Hard Code Title Bar T-Code Variant | Ricef Already done | Buat Ricef penambahan ditcode varian tittle bar | Done | 100% | 2024-12-30
Aryo | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Ricef Already done | Buat Ricef penambahan ditcode zpp0001 | Done | 100% | 2024-12-31
Aryo | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Ricef Already done | Buat Ricef penambahan ditcode zpp011 | Done | 100% | 2025-01-01
Aryo | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Ricef Already done | Buat Ricef penambahan ditcode ztpp011 | Done | 100% | 2025-01-02
Aryo | RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | Ricef Already done | Buat Ricef penambahan ditcode zpp019 | Done | 100% | 2025-01-03
Aryo | RICEFW-PP-LAMI2&3-11 Hard Code Order Type ZPP_BD | Ricef Already done | Buat Ricef penambahan ditcode zpp_bd | Done | 100% | 2025-01-04
Aryo | RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | Ricef Already done | Buat Ricef penambahan ditcode zpp_rc | Done | 100% | 2025-01-05
Mela | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060.docx | Ricef Already done | Buat Ricef penambahan ditcode zpp060 | Done | 90% | 2024-12-30
Mela | RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060.docx | Ricef Already done | Buat Ricef penambahan ditcode ztpp060 | Done | 90% | 2024-12-30
Mela | RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M.docx | Ricef Already done | Buat Ricef penambahan ditcode zcor6m | Done | 90% | 2024-12-30
Mela | RICEFW-PP-LAMI2&3-14 Hard Code Material Group ZPP018.docx | Ricef Already done | Buat Ricef penambahan ditcode zpp018 | Done | 90% | 2024-12-30
W09 (31 Desember 2024)
W09 (31 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | Ricef Already done | Buat Ricef penambahan ditcode zpp041 | Done | 50% | 2025-01-06
Ana | Configutation in DEV NC 130 01 Defining Order Type | New Order Type are define | Order type applied | Done | 100% | 2024-12-31
Ana | Configutation in DEV NC 130 02 Defining Number Range for Order | New Number Range for order are define | Order type applied | Done | 100% | 2024-12-31
Ana | Configutation in DEV NC 130 03 Assign Number Range to Order type | Assign Number Range to Order type | Order type applied | Done | 100% | 2024-12-31
Ana | Configutation in DEV NC 130 04 Administer selection profile for the combination | Sudah terconfig | Order type applied | Done | 100% | 2024-12-31
Mela | RICEFW-PP-LAMI2&3-19 T-Code Variant ZPP060L2.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan ditcode zpp060l2 | Done | 60% | 2025-01-03
Mela | RICEFW-PP-LAMI2&3-20 T-Code Variant ZPP060L3.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan ditcode zpp060l3 | Done | 60% | 2025-01-03
Mela | RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan ditcode zpp_rs | Done | 60% | 2025-01-03
Aryo, Ana | RICEFW-PP-LAMI2&3-28 One Button | Ricef Already done | Buat Ricef One Button | Done | 10% | 2025-01-17
W09 (02 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | RICEFW-PP-LAMI2&3-19 T-Code Variant ZPP060L2.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan di zpp060l2 | Done | 90% | 2025-01-03
Mela | RICEFW-PP-LAMI2&3-20 T-Code Variant ZPP060L3.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan di zpp060l3 | Done | 90% | 2025-01-03
Mela | RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan di zpp_rs | Done | 60% | 2025-01-03
Aryo, Ana | RICEFW-PP-LAMI2&3-28 One Button | Ricef Already done | Buat Ricef One Button | Done | 10% | 2025-01-04
W09 (03 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | Ricef Already done | Buat Ricef penambahan di zpp041 | Done | 50% | 2025-01-06
Ana | Configutation in DEV NC 130 05 Defining Order Type Dependent Parameter | New Order Type are defined | Order type applied | Done | 100% | 2025-01-03
Ana | Configutation in DEV NC 130 08 Specifying Scheduling Parameters | New Number Range for order are define | Order type applied | Done | 100% | 2025-01-03
Ana | Configutation in DEV NC 130 09 Defining Checking Controls | Assign Number Range to Order type | Order type applied | Done | 100% | 2025-01-03
Ana | Configutation in DEV NC 130 10 Defining Confirmation Parameters | Sudah terconfig | Sudah terconfig | Done | 100% | 2025-01-03
Ana | Configutation in DEV NC 130 11 Defining Default Values – Task List Selection | Sudah terconfig | Sudah terconfig | Done | 100% | 2025-01-03
Mela | RICEFW-PP-LAMI2&3-19 T-Code Variant ZPP060L2.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan dizpp060l2 | Done | 90% | 2025-01-03
Mela | RICEFW-PP-LAMI2&3-20 T-Code Variant ZPP060L3.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan dizpp060l3 | Done | 90% | 2025-01-03
Mela | RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS.docx | Melakuka discovery perubahan yang dilakukan | Buat Ricef penambahan dizpp_rs | Done | 100% | 2025-01-03
Mela | Configutation in DEV NC 130 10 Mantain Resource | Configuration NEW characteristic baru ZZPRODLINE | Config | Done | 100% | 2025-01-03
Mela | Configutation in DEV NC 130 10 Mantain Resource | Menaikkan master data di plant 1000 | Master Data Naik | Done | 60% | 2025-01-06
Aryo | Configutation in DEV NC 130 10 Mantain Resource | Menaikkan master data di plant 1000 | Master Data Naik | Done | 60% | 2025-01-06
W10 (06 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | Configutation in DEV NC 130 10 Mantain Resource | Maintain resource baru JRLAM02 | Naik Resorce Baru | Done | 100% | 2025-01-06
Aryo | Configutation in DEV NC 130 10 Mantain Resource | Maintain resource baru Mixing | Naik Resorce Baru | Done | 100% | 2025-01-06
Mela | Configutation in DEV NC 130 10 Mantain Resource | Maintain resource baru JRLAM03 | Naik Resorce Baru | Done | 100% | 2025-01-06
Mela | Configutation in DEV NC 130 10 Master Data | Menaikkan master data di plant 1000 | Master Data Naik | Done | 100% | 2025-01-06
Aryo | Configutation in DEV NC 130 10 Master Data | Menaikkan master data di plant 1000 | Master Data Naik | Done | 100% | 2025-01-06
.
W10 (07 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 12 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-10
Mela | Scenario Testing 10 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-10
W10 (09 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 12 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-10
Mela | Scenario Testing 10 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-10
Ana | 2.1 Business Blueprint Design | Business Blueprint already confirmated | Bluprint Buat | Done | 100% | 2025-01-09
W10 (10 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 12 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-10
Mela | Scenario Testing 10 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-10
Ana | 2.1 Business Blueprint Design | Diskusi hasil dari konfirmasi blueprint dengan Mas Randy dan mbak debie | Bluprint Buat | Done | 100% | 2025-01-10
W11 (13 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 12 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-13
Mela | Scenario Testing 10 | Planning SR + JR Base Film | Planning dan eksekusi | Done | 70% | 2025-01-07
Ana | Scenario Testing 11 | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-13
Ana | DISC-PP-LAM20 Subcont CKI | testing Hasil Scrap CKI | Planning dan eksekusi | Done | 100% | 2025-01-13
Aryo, Ana | RICEFW-PP-LAMI2&3-28 One Button | Ricef Already done | Buat Ricef | Done | 10% | 2025-01-13
W11 (14 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | Planning dan eksekusi | Done | 100% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Planning dan eksekusi | Done | 70% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Planning dan eksekusi | Done | 100% | 2025-01-17
W11 (15 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | Scenario Testing 13B | Testing Already Done | Produksi JR dan SR | Done | 100% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | Produksi JR dan SR | Done | 100% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | Produksi JR dan SR | Done | 100% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Produksi JR dan SR | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Produksi JR dan SR | Done | 10% | 2025-01-17
W11 (16 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Produksi JR dan SR | Done | 100% | 2025-01-14
Ana,Aryo, Mela | DISC-PP-LAM20 Subcont CKI | Testing One Button SR | Produksi JR dan SR | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | Produksi JR dan SR | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | Produksi JR dan SR | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Produksi JR dan SR | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Produksi JR dan SR | Done | 10% | 2025-01-17
W11 (17 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | Testing Already Done | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | Testing Already Done | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | Testing Already Done | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | Testing Already Done | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Testing Skenario | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Testing Skenario | Done | 10% | 2025-01-17
W11 (18 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | One Button Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W12 (20 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | One Button Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W12 (21 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Eksekusi | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Eksekusi | Done | 10% | 2025-01-17
W12 (22 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | Planning dan eksekusi | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Planning dan eksekusi | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Planning dan eksekusi | Done | 10% | 2025-01-17
W12 (23 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | Eksekusi | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Eksekusi | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Eksekusi | Done | 10% | 2025-01-17
W12 (24 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | One Button Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
Ana | 01 Defining Order type | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | 04 Defining Order Type Dependent Parameter | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | 05 Administer selection profile for the combination | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | 08 Specifying Scheduling Parameters | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | 09 Defining Checking Controls | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | 10 Defining Confirmation Parameters | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | 11 Defining Default Values – Task List Selection | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | Download and Compare Data for New Production Line | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
Ana | Download and Compare Data | Configuration already done | One Button Testing | Done | 100% | 2025-01-24
W13 (28 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Scenario Testing 13A | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Mela | Scenario Testing 13B | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 13C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Scenario Testing 11C | Testing Already Done | One Button Testing | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | One Button Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W13 30 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Label Desain | Done
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Testing | Done | 10% | 2025-01-17
W13 (31 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Testing | Done | 10% | 2025-01-17
W14 (03 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Recycle | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Testing | Done | 10% | 2025-01-17
W14 (04 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Testing | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Testing | Done | 10% | 2025-01-17
W14 (05 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Label Desain | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Testing | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan | Testing | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | Testing | Done | 10% | 2025-01-17
W14 (06 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Discovery Recycle Jual | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W14 (07 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Discovery Recycle jual diketahui | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W15 (10 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Discovery recycle jual ditambahkan | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W15 (11 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Review Desain Label | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Discovery recycle jual ditambahkan | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W15 (12 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Review Desain Label | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Discovery recycle jual ditambahkan | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W15 (13 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual | Discovery recycle jual ditambahkan | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W15 (14 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi |  | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual |  | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W16 (17 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi |  | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual |  | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W16 (18 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi |  | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual |  | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W16 (19 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi |  | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual |  | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W16 (20 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Menunggu Konfrimasi | Desain Label | Done | 70% | 2025-01-14
Mela | Label | Label Menunggu Konfrimasi |  | Done | 70% | 2025-01-14
Mela | Recycle | Discovery Recycle Jual |  | Done | 70% | 2025-01-14
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 10% | 2025-01-17
Ana,Aryo, Mela | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR | One Button Testing | Done | 10% | 2025-01-17
W16 (21 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Label | Label Customer Jual & Customer Stock | Desain Label | Done | 80% | 2025-02-24
Mela | Label | Label Menunggu Konfrimasi |  | Done | 70% | 2025-02-24
Ana | WRICEF One Button | WRICEF dan Testing One Button SR selesai | WRICEF dan Testing One Button SR selesai | Done | 50% | 2025-02-28
Rafly | WRICEF ZPP0041 | Testing Produksi JR Subcont |  | Done | 50% | 2025-02-28
mela, aryo | RICEFW-PP-LAMI2&3-28 One Button | Naikkan BOM testing 130 | Upload BOM dev 130 | Done | 90% | 2025-02-24
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 50% | 2025-02-24
W17 (24 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | RICEFW-PP-LAMI2&3-28 One Button | Testing One Button SR |  | Done | 50% | 2025-02-28
Ana | Kalkulator normal | Kalkulator normal dapat digunakan |  | Done | 50% | 2025-02-28
Mela | RICEFW-PP-LAMI2&3-30 New Design Label Jumbo Roll for Subcontracting Laminate | Ricef ditambahkan
Mela | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll For Selling Subcontracting Laminate | Ricef ditambahkan
Aryo | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Fixed label customer stock (jual) | Label Desain | Done | 70% | 2025-02-28
Aryo | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Fixed label customer stock | Label Desain | Done | 70% | 2025-02-28
Aryo, Mela,Rafly | Testing dev 130 new pordline | Testing dev 130 new prodline selesai | Testing | Done | 10% | 2025-02-25
W17 (25 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Integration Testing | Integration Testing (upload Master Data) | Integration Testing | Done | 100% | 2025-02-25
Mela | Integration Testing | Integration Testing (upload Master Data) | Integration Testing | Done | 100% | 2025-02-25
Rafly | RICEFW-PP-LAMI2&3-28 One Button | Discuss new parameter |  | Done | 100% | 2025-02-25
W17 (26 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Integration Testing | Integration Testing (Run Scenario Export) | Integration Testing | 0 | 70% | 2025-02-27
Mela | Integration Testing | Integration Testing (Run Scenario Domestic) | Integration Testing | 0 | 90% | 2025-02-26
W17 (27 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Integration Testing | Integration Testing (Run Scenario Export) | Integration Testing | 0 | 70% | 2025-02-25
Mela | Integration Testing | Integration Testing (Run Scenario Domestic) |  | 0 | 90% | 2025-02-25
W17 (27 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | Integration Testing | Integration Testing (Run Scenario Export) | Testing | Done | 100% | 2025-02-25
Mea | Integration Testing | Integration Testing (Run Scenario Domestic) | Testing | Done | 100% | 2025-02-25
Aryo | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Fixed label customer stock (jual) | Label Desain | In Progress | 70% | 2025-02-28
Aryo | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Fixed label customer stock | Label Desain | In Progress | 70% | 2025-02-28
Aryo | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | In Progress | 25% | 2025-02-28
Aryo | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | In Progress | 25% | 2025-02-28
Mela | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | In Progress | 25% | 2025-02-28
Mela | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | In Progress | 25% | 2025-02-28
Rafly, Mela, | Testing XMF_RE Recycle Execution | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | In Progress | 25% | 2025-02-28
W18 (3 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Update RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Update Content Ricef ZPP001 | In Progress | 75% | 2025-03-05
Aryo | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Update RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Update Content Ricef ZPP011 | In Progress | 75% | 2025-03-05
W18 (4 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Aryo | RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | Update RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | Update Content Ricef ZPP019 | In Progress | 75% | 2025-03-05
| RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | Update RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | Update Content Ricef ZPP_RC | In Progress | 75% | 2025-03-05
W18 (5 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Rafly | RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | Update RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | Update Content Ricef ZPP016 New Format | Done | 100% | 2025-03-05
Rafly | RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | Update RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | Update Content Ricef ZPP016CX New Format | Done | 100% | 2025-03-05
Rafly | RICEFW-PP-LAMI2&3-23 Hard Code Material Group ZPP016N | Update RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016N | Update Content Ricef ZPP016N New Format | Done | 100% | 2025-03-06
W18 (6 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Rafly | RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | Update RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | Update flow and new format | Done | 100% | 2025-03-05
Rafly | RICEFW-PP-LAMI2&3-29 Execution Jumbo Roll Laminated Subcontracted ZPP041SL | Update RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | Update flow and new format | Done | 100% | 2025-03-05
W18 (7 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Rafly | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 (UX & SAP) | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | In Progress | 75% | 2025-03-10
Rafly | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 (UX & SAP) | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | In Progress | 75% | 2025-03-10
Rafly | Testing Mixingx order UX and SAP | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | In Progress | 75% | 2025-03-10

## MM (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | 1.2.1 SAP Discovery and Evaluation | List discovery MM lengkap | List discovery MM lengkap | In Progress | 50% | 2024-11-11
W01 (08 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed | Configuration List for New Production Line Laminator #2 & #3 are Listed | Done | 100% | 2024-11-11
Randi, Yuli, Alif | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Mengetahui kondisi As-Is UX Tools | Kondisi As-Is UX Tools Diketahui | Done | 100% | 2024-11-11
W02 (11 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed | Configuration List for New Production Line Laminator #2 & #3 are Listed | Done | 100% | 2024-11-11
Randi, Yuli, Alif | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Mengetahui kondisi As-Is UX Tools | kondisi As-Is UX Tools diketahui | Done | 100% | 2024-11-11
Randi, Yuli, Alif | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Mengetahui titik UX Tools yang akan terimpact dengan adanya project Laminator | titik UX Tools yang akan terimpact dengan adanya project Laminator diketahui | Done | 100% | 2024-11-13
Yuli | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Menyiapkan data untuk demo UX Tools | Data untuk demo UX Tools siap | Done | 100% | 2024-11-13
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration testing di dev nc | Integration Testing selesai, solution discovered | Done | 100%
W02 (12 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario I Goods Receipt Material Using 101 B; 2 BATCH BF>CKI Cancel Confirmation; 4 BATCH BF=CKI | Integration Testing for Scenario I Goods Receipt Material Using 101 B; 2 BATCH BF>CKI Cancel Confirmation; 4 BATCH BF=CKI selesai | Done | 100% | 2024-11-12
W02 (13 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario J Goods Receipt Material Using 563 E w/ Confirmation SR 0; Ukuran BF=CKI | Integration Testing for Scenario J Goods Receipt Material Using 563 E w/ Confirmation SR 0; Ukuran BF=CKI selesai | Done | 100% | 2024-11-13
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario K Goods Receipt Material Using 563 E w/ Confirmation; Ukuran BF=CKI | Integration Testing for Scenario K Goods Receipt Material Using 563 E w/ Confirmation; Ukuran BF=CKI selesai | Done | 100% | 2024-11-13
W02 (14 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario L Goods Receipt Material Using 563 E w/ BF Lami Confirmation SR 0; Ukuran BF>CKI | Integration Testing for Scenario L Goods Receipt Material Using 563 E w/ BF Lami Confirmation SR 0; Ukuran BF>CKI selesai | Done | 100% | 2024-11-14
W02 (15 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting selesai | Done | 100% | 2024-11-15
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting selesai | Done | 100% | 2024-11-15
W03 (18 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting | Integration Testing for Scenario M Goods Receipt Material Using 563 E; All material CKI; Printing, BF, RM; w/o slitting selesai | Done | 100% | 2024-11-18
W03 (19 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting | Integration Testing for Scenario N Goods Receipt Material Using 563 E; All material CKI; Printing, Laminate; w/o slitting selesai | Done | 100% | 2024-11-19
W03 (20 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM05 T-Code Variant List | Listing Tcode Variant | Listing Tcode Variant selesai | Done | 100% | 2024-11-20
W03 (21 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM09 Characteristic for Batch Subcontracting | Listing Characteristic for Batch Subcont | Listing Characteristic for Batch Subcont selesai | Done | 100% | 2024-11-23
W03 (22 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM09 Characteristic for Batch Subcontracting | Listing Characteristic for Batch Subcont | Listing Characteristic for Batch Subcont selesai | Done | 100% | 2024-11-23
W04 (25 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM02 HU Requirement for Storage Location and Default Value | Listing New Sloc Subcont & HU Requirement | Listing New Sloc Subcont & HU Requirement selesai | Done | 100% | 2024-11-25
Randi, Yuli, Alif | DISC-MM-LAM03 Set Profile for Packing Station | Listing Packing Station Subcont | Listing Packing Station Subcont selesai | Done | 100% | 2024-11-25
Randi, Yuli, Alif | DISC-MM-LAM04 Maintain Table ZHU_MAPP | Listing Mapping Subcont | Listing Mapping Subcont selesai | Done | 100% | 2024-11-25
W04 (26 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont Printing CKI | Listing Master Data for Material Subcont Printing CKI selesai | Done | 25% | 2024-11-29
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont Laminated CKI | Listing Master Data for Material Subcont Laminated CKI selesai | Done | 25% | 2024-11-29
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont BOPP CKI | Listing Master Data for Material Subcont BOPP CKI selesai | Done | 25% | 2024-11-29
W04 (28 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont Printing CKI | Listing Master Data for Material Subcont Printing CKI selesai | Done | 75% | 2024-11-29
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont Laminated CKI | Listing Master Data for Material Subcont Laminated CKI selesai | Done | 75% | 2024-11-29
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont BOPP CKI | Listing Master Data for Material Subcont BOPP CKI selesai | Done | 75% | 2024-11-29
W04 (29 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont Printing CKI | Listing Master Data for Material Subcont Printing CKI selesai | Done | 100% | 2024-11-29
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont Laminated CKI | Listing Master Data for Material Subcont Laminated CKI selesai | Done | 100% | 2024-11-29
Randi, Yuli, Alif | DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | Listing Master Data for Material Subcont BOPP CKI | Listing Master Data for Material Subcont BOPP CKI selesai | Done | 100% | 2024-11-29
W06 (09 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Scenario Testing | Scenario Testing selesai | Done | 100% | 2024-12-09
W06 (10 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Scenario Testing | Scenario Testing selesai | Done | 100%
W06 (11 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Scenario Testing | Scenario Testing selesai | Done | 100%
W06 (12 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Scenario Testing | Scenario Testing selesai | Done | 100%
W06 (13 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi, Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Scenario Testing | Scenario Testing selesai | Done | 100%
W07 (16 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi | DISC-MM-LAM12 Subcont CKI | Configuration List | Configuration List selesai | Done | 100%
W07 (17 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Menaikkan Material type baru ZRMB untuk RM CKI | Menaikkan Material type baru ZRMB untuk RM CKI selesai | Done | 100% | 2024-12-17
Yuli, Randi | DISC-MM-LAM12 Subcont CKI | Menaikkan Material type baru ZSUB untuk Scenario testing 3B, 4B, 5B, 6B | Menaikkan Material type baru ZSUB untuk Scenario testing 3B, 4B, 5B, 6B selesai | Done | 100% | 2024-12-17
W07 (18 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif, Randi | DISC-MM-LAM12 Subcont CKI | Konfigurasi account category group Y untuk 101 E | Konfigurasi account category group Y untuk 101 E selesai | Done | 100% | 2024-12-19
Yuli | DISC-MM-LAM12 Subcont CKI | Menaikkan master data untuk scenario testing 7A,B,C | Menaikkan master data untuk scenario testing 7A,B,C selesai | Done | 100% | 2024-12-19
W07 (19 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli, Randi | DISC-MM-LAM12 Subcont CKI | Scenario testing 7C | Scenario testing 7C selesai | Done | 100% | 2024-12-19
Alif, Randi | DISC-MM-LAM12 Subcont CKI | Scenario testing 7A,B | Scenario testing 7A,B selesai | Done | 100% | 2024-12-19
W07 (20 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | Done | 100% | 2024-12-28
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Discovery dengan tim SAP SD dan SAP PP serta Scenario testing 8A, 8B | Discovery dengan tim SAP SD dan SAP PP serta Scenario testing 8A, 8B selesai | Done | 100% | 2024-12-20
Yuli | DISC-MM-LAM12 Subcont CKI | Menaikkan master data untuk Scenario testing 8A, 8B | Menaikkan master data untuk Scenario testing 8A, 8B selesai | Done | 100% | 2024-12-20
W08 (23 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 50% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 0% | 2024-12-28
Alif | DISC-MM-LAM12 Subcont CKI | GRN RM | GRN RM selesai | Done | 100% | 2024-12-28
Yuli | DISC-MM-LAM12 Subcont CKI | Scenario testing for SR-O 8A 8B | Scenario testing for SR-O 8A 8B selesai | Done | 100% | 2024-12-28
W08 (24 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 25% | 2024-12-31
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 10% | 2024-12-28
W08 (26 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Discovery hasil review pada special stock B terkait accounting document | Discovery hasil review pada special stock B terkait accounting document selesai | In Progress | 10% | 2024-12-30
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 25% | 2024-12-31
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 10% | 2024-12-28
W08 (27 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Mempersiapkan material untuk testing cost analysis | Mempersiapkan material untuk testing cost analysis selesai | Planned | 0% | 2024-12-27
Alif | DISC-MM-LAM12 Subcont CKI | Discovery hasil review pada special stock B terkait accounting document | Discovery hasil review pada special stock B terkait accounting document selesai | In Progress | 10% | 2024-12-30
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 25% | 2024-12-31
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 10% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | Planned | 0% | 2024-12-27
W09 (30 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Mempersiapkan material untuk testing cost analysis | Mempersiapkan material untuk testing cost analysis selesai | Done | 100% | 2024-12-27
Alif | DISC-MM-LAM12 Subcont CKI | Discovery hasil review pada special stock B terkait accounting document | Discovery hasil review pada special stock B terkait accounting document selesai | In Progress | 70% | 2024-12-30
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 30% | 2024-12-31
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 30% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 60% | 2024-12-27
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Configuration MM di server dev NC | Configuration MM di server dev NC selesai | Planned | 0% | 2025-01-02
W09 (31 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Mempersiapkan material untuk testing cost analysis | Mempersiapkan material untuk testing cost analysis selesai disiapkan | Done | 100% | 2024-12-27
Alif | DISC-MM-LAM12 Subcont CKI | Discovery hasil review pada special stock B terkait accounting document | Discovery hasil review pada special stock B terkait accounting document selesai | Done | 100% | 2024-12-30
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 30% | 2024-12-31
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 30% | 2024-12-28
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 60% | 2024-12-27
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Configuration MM di server dev NC | Configuration MM di server dev NC selesai | Done | 100% | 2025-01-02
W09 (2 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Mempersiapkan material untuk testing cost analysis | Mempersiapkan material untuk testing cost analysis selesai | Done | 100% | 2025-01-03
Alif | DISC-MM-LAM12 Subcont CKI | Discovery hasil review pada special stock B terkait accounting document | Discovery hasil review pada special stock B terkait accounting document selesai | In Progress | 70% | 2025-01-03
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 30% | 2025-01-03
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-03
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 30% | 2025-01-03
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-03
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Configuration MM di server dev NC | Configuration MM di server dev NC selesai | Done | 100% | 2025-01-03
W09 (3 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Mempersiapkan material untuk testing cost analysis | Mempersiapkan material untuk testing cost analysis selesai | Done | 100% | 2025-01-03
Alif | DISC-MM-LAM12 Subcont CKI | Discovery hasil review pada special stock B terkait accounting document | Discovery hasil review pada special stock B terkait accounting document selesai | Done | 70% | 2025-01-03
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 30% | 2025-01-03
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-03
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 30% | 2025-01-03
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-03
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Configuration MM di server dev NC | Configuration MM di server dev NC selesai | Done | 100% | 2025-01-03
W10 (6 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Discovery hasil review pada special stock B terkait accounting document | Discovery hasil review pada special stock B terkait accounting document selesai | Done | 100% | 2025-01-03
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 30% | 2025-01-10
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
W10 (7 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-10
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
W10 (8 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-10
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-10
W10 (9 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-10
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-10
Alif | DISC-MM-LAM12 Subcont CKI | Explore master data material SR cki non stock item, sebagai material sisa core | Explore master data material SR cki non stock item, sebagai material sisa core selesai | In Progress | 25% | 2025-01-10
Yuli | DISC-MM-LAM12 Subcont CKI | Testing PO return untuk PO baru untuk mengembalikan sisa core | Testing PO return untuk PO baru untuk mengembalikan sisa core selesai | In Progress | 25% | 2025-01-10
Yuli | DISC-MM-LAM12 Subcont CKI | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch selesai | In Progress | 25% | 2025-01-10
W10 (10 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-10
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 25% | 2025-01-10
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-10
Alif | DISC-MM-LAM12 Subcont CKI | Explore master data material SR cki non stock item, sebagai material sisa core | Explore master data material SR cki non stock item, sebagai material sisa core selesai | In Progress | 25% | 2025-01-10
Yuli | DISC-MM-LAM12 Subcont CKI | Testing PO return untuk PO baru untuk mengembalikan sisa core | Testing PO return untuk PO baru untuk mengembalikan sisa core selesai | In Progress | 90% | 2025-01-10
Yuli | DISC-MM-LAM12 Subcont CKI | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch selesai | In Progress | 90% | 2025-01-10
W11 (13 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-17
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | In Progress | 75% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 80% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Explore master data material SR cki non stock item, sebagai material sisa core | Explore master data material SR cki non stock item, sebagai material sisa core selesai | In Progress | 90% | 2025-01-15
Yuli | DISC-MM-LAM12 Subcont CKI | Testing PO return untuk PO baru untuk mengembalikan sisa core | Testing PO return untuk PO baru untuk mengembalikan sisa core selesai | In Progress | 90% | 2025-01-15
Yuli | DISC-MM-LAM12 Subcont CKI | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch selesai | In Progress | 90% | 2025-01-15
W11 (14 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-17
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | In Progress | 75% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | In Progress | 60% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | In Progress | 80% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Documentation WRICEF One Button | Documentation WRICEF One Button selesai | In Progress | 25% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Explore master data material SR cki non stock item, sebagai material sisa core | Explore master data material SR cki non stock item, sebagai material sisa core selesai | In Progress | 90% | 2025-01-15
Yuli | DISC-MM-LAM12 Subcont CKI | Testing PO return untuk PO baru untuk mengembalikan sisa core | Testing PO return untuk PO baru untuk mengembalikan sisa core selesai | In Progress | 90% | 2025-01-15
Yuli | DISC-MM-LAM12 Subcont CKI | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch selesai | In Progress | 90% | 2025-01-15
W11 (15 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-17
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Skenario testing | Skenario testing selesai | Done | 100% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Discovery one button dengan tim ABAP | Discovery one button dengan tim ABAP selesai | Done | 100% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Documentation of Discovery one button dengan tim ABAP | Documentation of Discovery one button dengan tim ABAP selesai | Done | 100% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Diskusi flow one button dengan tim ABAP | Diskusi flow one button dengan tim ABAP selesai | Done | 100% | 2025-01-17
Randi | DISC-MM-LAM12 Subcont CKI | Documentation WRICEF One Button | Documentation WRICEF One Button selesai | Done | 100% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Explore master data material SR cki non stock item, sebagai material sisa core | Explore master data material SR cki non stock item, sebagai material sisa core selesai | Done | 100% | 2025-01-15
Yuli | DISC-MM-LAM12 Subcont CKI | Testing PO return untuk PO baru untuk mengembalikan sisa core | Testing PO return untuk PO baru untuk mengembalikan sisa core selesai | Done | 100% | 2025-01-15
Yuli | DISC-MM-LAM12 Subcont CKI | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch selesai | In Progress | 90% | 2025-01-15
W11 (16 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Yuli | DISC-MM-LAM12 Subcont CKI | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch | Testing ZMM056 upload material w/o batch untuk penerimaan material CKI w/o batch selesai | Done | 100% | 2025-01-15
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV NC untuk Laminator 2 dan 3 | Config DEV NC untuk Laminator 2 dan 3 selesai | Done | 100% | 2025-01-16
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Update master data untuk testing skenario baru | Update master data untuk testing skenario baru selesai | Done | 100% | 2025-01-16
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Testing skenario baru | Testing skenario baru selesai | In Progress | 25% | 2025-01-16
W11 (17 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Testing skenario baru | Testing skenario baru selesai | Done | 100% | 2025-01-16
Alif | DISC-MM-LAM12 Subcont CKI | Flow enchancement ZMM056SL untuk subcont | Flow enchancement ZMM056SL untuk subcont selesai | In Progress | 25% | 2025-01-21
Alif | DISC-MM-LAM12 Subcont CKI | Flow enchancement ZIC004L untuk subcont | Flow enchancement ZIC004L untuk subcont selesai | In Progress | 25% | 2025-01-21
W12 (20 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Flow enchancement ZMM056SL untuk subcont | Flow enchancement ZMM056SL untuk subcont selesai | In Progress | 50% | 2025-01-21
Alif | DISC-MM-LAM12 Subcont CKI | Flow enchancement ZIC004L untuk subcont | Flow enchancement ZIC004L untuk subcont selesai | In Progress | 50% | 2025-01-21
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV 100 untuk Laminator 2 dan 3 | Config DEV 100 untuk Laminator 2 dan 3 selesai | Done | 100% | 2025-01-20
W12 (21 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Flow enchancement ZMM056SL untuk subcont | Flow enchancement ZMM056SL untuk subcont selesai | Done | 100% | 2025-01-21
Alif | DISC-MM-LAM12 Subcont CKI | Flow enchancement ZIC004L untuk subcont | Flow enchancement ZIC004L untuk subcont selesai | Done | 100% | 2025-01-21
W12 (22 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV NC T-Code Variant | Config DEV NC T-Code Variant selesai | In Progress | 25% | 2025-01-24
W12 (23 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV NC T-Code Variant | Config DEV NC T-Code Variant selesai | In Progress | 25% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing ZMM056SL | Testing ZMM056SL selesai | In Progress | 25% | 2025-01-28
Yuli | DISC-MM-LAM12 Subcont CKI | Designing New Label HU for LAMI#2 #3 | Designing New Label HU for LAMI#2 #3 selesai | In Progress | 50% | 2025-01-24
W12 (24 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV NC T-Code Variant | Config DEV NC T-Code Variant selesai | In Progress | 25% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing ZMM056SL | Testing ZMM056SL selesai | In Progress | 60% | 2025-01-28
Yuli | DISC-MM-LAM12 Subcont CKI | Designing New Label HU for LAMI#2 #3 | Designing New Label HU for LAMI#2 #3 selesai | Done | 100% | 2025-01-24
W12 (28 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV NC T-Code Variant | Config DEV NC T-Code Variant selesai | In Progress | 30% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing ZMM056SL | Testing ZMM056SL selesai | In Progress | 80% | 2025-01-28
W12 (30 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV NC T-Code Variant | Config DEV NC T-Code Variant selesai | In Progress | 65% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing ZMM056SL | Testing ZMM056SL selesai | Done | 100% | 2025-01-28
W12 (31 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV NC T-Code Variant | Config DEV NC T-Code Variant selesai | Done | 100% | 2025-01-24
W13 (03 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Config DEV 100 New Prodline | Config DEV 100 New Prodline selesai | Done | 100% | 2025-01-24
Yuli | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-07
W13 (04 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Compare dan menaikkan DEV 130 New Prodline | Compare dan menaikkan DEV 130 New Prodline selesai | Done | 100% | 2025-01-24
Yuli | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-07
W13 (05 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Membuat template master data 130 | Membuat template master data 130 selesai | In Progress | 25% | 2025-01-24
Yuli | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-07
W13 (06 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | In Progress | 88% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Membuat template master data 130 | Membuat template master data 130 selesai | In Progress | 50% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing ZIC004SL | Testing ZIC004SL selesai | In Progress | 50% | 2025-01-28
Yuli | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-07
W13 (07 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Yuli | DISC-MM-LAM12 Subcont CKI | Update business blueprint | Update business blueprint selesai | Done | 100% | 2025-02-07
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Membuat template master data 130 | Membuat template master data 130 selesai | Done | 100% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing ZIC004SL | Testing ZIC004SL selesai | Done | 100% | 2025-01-28
Yuli | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-07
W14 (10 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | DISC-MM-LAM12 Subcont CKI | Menaikkan Master data 130 | Menaikkan Master data 130 selesai | In Progress | 25% | 2025-01-24
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Testing Skenario 9 dan 10 V2 di NC | Testing Skenario 9 dan 10 V2 di NC selesai | In Progress | 25% | 2025-01-28
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-07
Yuli | DISC-MM-LAM12 Subcont CKI | Pembuatan WRICEF untuk label HU | Pembuatan WRICEF untuk label HU selesai | In Progress | 75% | 2025-02-21
W14 (11 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | DISC-MM-LAM12 Subcont CKI | Menaikkan Master data 130 | Menaikkan Master data 130 selesai | In Progress | 50% | 2025-01-24
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Testing Skenario 9 dan 10 V2 di NC | Testing Skenario 9 dan 10 V2 di NC selesai | In Progress | 50% | 2025-01-28
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-21
Yuli | DISC-MM-LAM12 Subcont CKI | Pembuatan WRICEF untuk label HU | Pembuatan WRICEF untuk label HU selesai | In Progress | 75% | 2025-02-21
W14 (12 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | DISC-MM-LAM12 Subcont CKI | Menaikkan Master data 130 | Menaikkan Master data 130 selesai | Done | 100% | 2025-01-24
Alif, Yuli | DISC-MM-LAM12 Subcont CKI | Testing Skenario 9 dan 10 V2 di NC | Testing Skenario 9 dan 10 V2 di NC selesai | In Progress | 60% | 2025-01-28
Yuli | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-07
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-21
Yuli | DISC-MM-LAM12 Subcont CKI | Pembuatan WRICEF untuk label HU | Pembuatan WRICEF untuk label HU selesai | In Progress | 75% | 2025-02-21
W14 (13 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif | DISC-MM-LAM12 Subcont CKI | Membuat WRICEF ZIC04SL dan ZMM056SL | Membuat WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 20% | 2025-01-28
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-21
Yuli | DISC-MM-LAM12 Subcont CKI | Pembuatan WRICEF untuk label HU | Pembuatan WRICEF untuk label HU selesai | In Progress | 75% | 2025-02-21
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Testing NC Scenario 9 & 10 | Testing NC Scenario 9 & 10 selesai | In Progress | 80% | 2025-02-14
W14 (14 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | DISC-MM-LAM12 Subcont CKI | Membuat WRICEF ZIC04SL dan ZMM056SL | Membuat WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-01-24
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU | Update perubahan pada design label HU selesai | In Progress | 75% | 2025-02-21
Yuli | DISC-MM-LAM12 Subcont CKI | Pembuatan WRICEF untuk label HU | Pembuatan WRICEF untuk label HU selesai | Done | 100% | 2025-02-14
Yuli, Alif | DISC-MM-LAM12 Subcont CKI | Testing NC Scenario 9 & 10 | Testing NC Scenario 9 & 10 selesai | Done | 100% | 2025-02-14
W15 (17 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | DISC-MM-LAM12 Subcont CKI | Membuat WRICEF ZIC04SL dan ZMM056SL | Membuat WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing UXTOLL DEV | Testing UXTOLL DEV selesai | Done | 20% | 2025-01-28
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU jual dan customer | Update perubahan pada design label HU jual dan customer selesai | In Progress | 75% | 2025-02-21
W15 (18 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | DISC-MM-LAM12 Subcont CKI | Membuat WRICEF ZIC04SL dan ZMM056SL | Membuat WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing UXTOLL DEV | Testing UXTOLL DEV selesai | Done | 25% | 2025-01-28
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU jual dan customer | Update perubahan pada design label HU jual dan customer selesai | In Progress | 75% | 2025-02-21
W15 (19 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | DISC-MM-LAM12 Subcont CKI | Update otorisasi design | Update otorisasi design selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | DISC-MM-LAM12 Subcont CKI | Membuat WRICEF ZIC04SL dan ZMM056SL | Membuat WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-01-24
Alif | DISC-MM-LAM12 Subcont CKI | Testing UXTOLL DEV | Testing UXTOLL DEV selesai | Done | 40% | 2025-01-28
Yuli, Fany | DISC-MM-LAM12 Subcont CKI | Update perubahan pada design label HU jual dan customer | Update perubahan pada design label HU jual dan customer selesai | In Progress | 75% | 2025-02-21
W15 (20 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-01-24
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-01-28
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-02-21
Alif | Update tambah No. PO Customer ZIC004SL | No. PO Customer bisa masuk ke batch GRN | No. PO Customer bisa masuk ke batch GRN selesai | In Progress | 20% | 2025-02-25
W15 (21 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-01-17
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-01-24
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-01-28
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-02-21
Alif | Update tambah No. PO Customer ZIC004SL | No. PO Customer bisa masuk ke batch GRN | No. PO Customer bisa masuk ke batch GRN selesai | In Progress | 30% | 2025-02-25
W16 (24 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-02-28
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-02-28
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-02-28
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-02-28
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 50% | 2025-02-28
Alif | Update tambah No. PO Customer ZIC004SL | No. PO Customer bisa masuk ke batch GRN | No. PO Customer bisa masuk ke batch GRN selesai | In Progress | 60% | 2025-02-25
Alif, Yuli | Testing dev 130 new prodline | Testing dev 130 new prodline selesai | Testing dev 130 new prodline selesai selesai | Done | 10% | 2025-02-25
W16 (25 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-02-28
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-02-28
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-02-28
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-02-28
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 50% | 2025-02-28
Alif | Update tambah No. PO Customer ZIC004SL | No. PO Customer bisa masuk ke batch GRN | No. PO Customer bisa masuk ke batch GRN selesai | Done | 60% | 2025-02-25
Alif, Yuli | Testing dev 130 new prodline | Testing dev 130 new prodline selesai | Testing dev 130 new prodline selesai selesai | Done | 25% | 2025-02-25
W16 (26 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-02-28
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-02-28
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-02-28
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-02-28
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 50% | 2025-02-28
Alif | Update tambah No. PO Customer ZIC004SL | No. PO Customer bisa masuk ke batch GRN | No. PO Customer bisa masuk ke batch GRN selesai | Done | 60% | 2025-02-25
Alif, Yuli | Testing dev 130 new prodline | Testing dev 130 new prodline selesai | Testing dev 130 new prodline selesai selesai | Done | 50% | 2025-02-25
W16 (27 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-02-28
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-02-28
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-02-28
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-02-28
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 50% | 2025-02-28
Alif | Update tambah No. PO Customer ZIC004SL | No. PO Customer bisa masuk ke batch GRN | No. PO Customer bisa masuk ke batch GRN selesai | Done | 60% | 2025-02-25
Alif, Yuli | Testing dev 130 new prodline | Testing dev 130 new prodline selesai | Testing dev 130 new prodline selesai selesai | Done | 70% | 2025-02-25
W16 (28 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-02-28
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-02-28
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-02-28
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-02-28
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 75% | 2025-02-28
Alif | Update tambah No. PO Customer ZIC004SL | No. PO Customer bisa masuk ke batch GRN | No. PO Customer bisa masuk ke batch GRN selesai | Done | 100% | 2025-02-25
Alif, Yuli | Testing dev 130 new prodline | Testing dev 130 new prodline selesai | Testing dev 130 new prodline selesai selesai | Done | 100% | 2025-02-25
Alif, Yuli | Config T-code Variant DEV AIX 130 | Config T-Code Variant Selesai | T-code Variant MM dev 130 | Done | 10% | 2025-03-04
W17 (3 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-03-11
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-03-10
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-03-10
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-03-07
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 75% | 2025-03-07
Alif, Yuli | Config T-code Variant DEV AIX 130 | Config T-Code Variant Selesai | T-code Variant MM dev 130 | Done | 10% | 2025-03-10
W17 (4 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-03-11
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-03-10
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-03-10
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-03-07
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 75% | 2025-03-07
Alif, Yuli | Config T-code Variant DEV AIX 130 | Config T-Code Variant Selesai | T-code Variant MM dev 130 | Done | 10% | 2025-03-10
W17 (5 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-03-11
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-03-10
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-03-10
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-03-07
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 75% | 2025-03-07
Alif, Yuli | Config T-code Variant DEV AIX 130 | Config T-Code Variant Selesai | T-code Variant MM dev 130 | Done | 10% | 2025-03-10
W17 (6 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-03-11
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-03-10
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 40% | 2025-03-10
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | In Progress | 75% | 2025-03-07
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 75% | 2025-03-07
Alif, Yuli | Config T-code Variant DEV AIX 130 | Config T-Code Variant Selesai | T-code Variant MM dev 130 | Done | 10% | 2025-03-10
W17 (7 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-03-11
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-03-10
Alif | Testing UXTOOL DEV | UXTOOL DEV OK | UXTOOL DEV OK selesai | Done | 100% | 2025-03-10
Yuli, Fany | Update perubahan pada design label HU jual dan customer | Design label HU jual dan customer | Design label HU jual dan customer selesai | Done | 100% | 2025-03-07
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 80% | 2025-03-10
Alif, Yuli | Config T-code Variant DEV AIX 130 | Config T-Code Variant Selesai | T-code Variant MM dev 130 | Done | 90% | 2025-03-10
W17 (7 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Alif | Update otorisasi design | Otorisasi design update | Otorisasi design update selesai | In Progress | 25% | 2025-03-11
Alif, Yuli,Randi | Membuat WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL | WRICEF ZIC04SL dan ZMM056SL selesai | In Progress | 50% | 2025-03-10
Yuli | Membuat WRICEF New Design Label HU | WRICEF New Design Label HU | WRICEF New Design Label HU selesai | In Progress | 80% | 2025-03-10
Alif, Yuli | Config T-code Variant DEV AIX 130 | Config T-Code Variant Selesai | T-code Variant MM dev 130 | Done | 100% | 2025-03-10

## QM (hidden)
Daily Activity
W01 (11 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-QM-LAM01 Explore Inspection Type for Subcont | Menentukan Inspection type Roll Subcont |  | In Progress | 25%
Ana | DISC-QM-LAM02 Explore Task List QM for Subcont | Menentukan Task List yang digunakan saat menerima Roll Subcont |  | In Progress | 25%
W02 (12 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-QM-LAM01 Explore Inspection Type for Subcont | Menentukan Inspection type Roll Subcont |  | In Progress | 25%
Ana | DISC-QM-LAM02 Explore Task List QM for Subcont | Menentukan Task List yang digunakan saat menerima Roll Subcont |  | In Progress | 25%
W02 (13 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-QM-LAM01 Explore Inspection Type for Subcont | Menentukan Inspection type Roll Subcont |  | In Progress | 25%
Ana | DISC-QM-LAM02 Explore Task List QM for Subcont | Menentukan Task List yang digunakan saat menerima Roll Subcont |  | In Progress | 25%
W02 (14 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-QM-LAM01 Explore Inspection Type for Subcont | Menentukan Inspection type Roll Subcont |  | In Progress | 25%
Ana | DISC-QM-LAM02 Explore Task List QM for Subcont | Menentukan Task List yang digunakan saat menerima Roll Subcont |  | In Progress | 25%
W02 (15 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Mela | DISC-QM-LAM02 Explore Task List QM for Subcont | Menentukan Task List yang digunakan saat menerima Roll Subcont |  | In Progress | 25%
W02 (18 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana | DISC-QM-LAM01 Explore Inspection Type for Subcont | Menentukan Inspection type Roll Subcont |  | In Progress | 50%
Ana | DISC-QM-LAM02 Explore Task List QM for Subcont | Menentukan Task List yang digunakan saat menerima Roll Subcont |  | In Progress | 50%
W02 (19 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Ana, Mela | DISC-QM-LAM01 Explore Inspection Type for Subcont | Menentukan Inspection type Roll Subcont |  | Done | 100%
Ana | DISC-QM-LAM02 Explore Task List QM for Subcont | Menentukan Task List yang digunakan saat menerima Roll Subcont |  | Done | 100%
W17 (26 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Rafly | JR Agging | Discovery Enhance JR Agging | Discovery | In Progress | 70% | 2025-02-25
W17 (27 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Rafly | JR Agging | Explore Enhance JR Agging | Explore | In Progress | 70% | 2025-02-25
W17 (28 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Rafly | JR Agging | Testing Enhance JR Agging | Testing | In Progress | 70% | 2025-02-25
Mela | Integration Testing | Upload Inspection type and plan | Upload selesai | Done | 100% | 2025-02-25

## Sheet8 (hidden)
ACTIVITY |  | 2024
|  | NOV | DES |  |  | JAN |  | FEB
PREPARE
Project Initiation | [6 empty] | ` |  | `
Discovery and Evaluation
Business Process Map
EXPLORE |  |  |  | 10 | 12
Business Blueprint Design
Business Blueprint Confirmation & Finalization
Enhancement (RICEF) Design
Configuration Design
Authorization Requirements and Design
REALIZE
Configuration and Documentation
Enhancement (RICEFW) Development
Run Scenario Test and Integration Test
Quality Assurance Environment (QAS): Roles and Transport
Quality Assurance Environment (QAS): Data Load
Prepare End User Training and User Acceptance Test Delivery
DEPLOY
Pre Go-Live End-User Training Delivery
User Acceptance Test (UAT)
Production System Environment
Helpdesk Setup
RUN
Go Live
Post Go-Live End-User Training Delivery
Support After Go Live
Done
In Progress
Planned
Finished Milestone
Planned Milestone
EXPLORE
PREPARE
REALIZE
RUN
RUN
DEP

## Sheet4 (hidden)
ACTIVITY |  | PIC | Desember | [11 empty] | Januari
|  |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
SERVER DEV NC
SAP MM
CONFIG-MM..
CONFIG-MM..
SAP PP
CONFIG-PP..
CONFIG-PP..
SAP SD
CONFIG-PP..
CONFIG-PP..
SAP FI
CONFIG-PP..
CONFIG-PP..
SAP CO
CONFIG-PP..
CONFIG-PP..

## PM (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Alif | 1.2.1 SAP Discovery and Evaluation | List Activity WBS | Done | 100% | 2024-11-08
W01 (08 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Alif | Set Functional Location Lami 02 and 03 | Functional Location Lami 02 and 03 ready | Done | 100% | 2024-11-08
Alif | Explore Relation Field Connect to Functional Location | List Relation Field Connect to Functional Location | Done | 100% | 2024-11-08

## SD (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 25%
|  |  |  | Planned | 0%
W01 (08 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 50%
|  |  |  | Planned | 0%
W02 (11 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 75%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcon |  | In Progress | 50%
W02 (12 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 75%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W02 (13 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W02 (14 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W02 (15 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (18 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (19 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (20 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (21 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (22 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (25 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (26 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (28 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (29 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W07 (19 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 1, 2, 4, 5, 6 |  | Done | 100%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 7 A B C (cycle 2) |  | In Progress | 25%
W07 (20 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 7 A B C (cycle 2) |  | Done | 100% | 2024-12-20
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 8 A B (cycle 2) |  | In Progress | 0% | 2024-12-23
W08(23 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 8 A B (cycle 2) |  | Done | 100% | 2024-12-23
Tyas, Randi | 2.1 Business Blueprint Design | Update Business Blueprint |  | In Progress | 0% | 2024-12-24
W08(26 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | Update Business Blueprint |  | In Progress | 50%
W09(03 Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | SD Organizational Unitz |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SD General Settings |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDGI01 Reverse Goods Movement |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDCM01 Release Delivery Block karena Terms of Payments |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO11 Sales with Down Payment |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO27 Sales Order Inventory |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO01 Domestic Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO02 Domestic Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO07 Export Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO08 Export Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO13 Domestic Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO14 Domestic Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO17 Export Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO18 Export Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | Integration Testing | Create SO |  | Done | 100%
Tyas, Randi | Integration Testing | Transaksi Penjualan |  | Planned | 0%
W10(06 Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | SD Organizational Unitz |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SD General Settings |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDGI01 Reverse Goods Movement |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDCM01 Release Delivery Block karena Terms of Payments |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO11 Sales with Down Payment |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO27 Sales Order Inventory |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO01 Domestic Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO02 Domestic Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO07 Export Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO08 Export Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO13 Domestic Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO14 Domestic Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO17 Export Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO18 Export Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | Integration Testing | Create SO |  | Done | 100%
Tyas, Randi | Integration Testing | Transaksi Penjualan |  | Planned | 0%
W11(13Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait transport posting (Free To So, So To So, So To Free) for RM |  | Done | 100%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle |  | In Progress | 50%
Tyas, Randi | Integration Testing | Transaksi Penjualan for scenario 10A, 10B, 11A, 11B, 12A, 12B |  | Done | 100%
W11(14Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle |  | In Progress | 50%
Tyas, Randi | Integration Testing | Transaksi Penjualan for scenario 13A, 13B |  | In Progress | 50%
Tyas, Randi | Integration Testing | Transaksi Penjualan for scenario 10C, 11C, 12C, 13C |  | Planned | 0%
W13(31 Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle |  | Done | 100%
Tyas, Randi, Wahyu | Integration Testing | Transaksi Penjualan for scenario 13A, 13B |  | Done | 100%
Tyas, Randi, Wahyu | Integration Testing | Transaksi Penjualan for scenario 10C, 11C, 12C, 13C |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config SO Type, DO Type, Billing Type for LAM SUBCONTRACTED (DEV NC) |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config SO Type, DO Type for Recycle Disposal (DEV NC) |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config Division for OUTSOURCE LAMINATE, LAM SUBCONTRACTED, REC SUBCONTRACTED (DEV NC) |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config AAG Material for LAM SUBCONTRACTED |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Transaksi Penjualan for scenario 14A, 14B, 14C |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | In Progress | 25%
W14(03 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Transaksi Penjualan for Recycle Subcont all scenario |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | In Progress | 50%
W14(04 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | In Progress | 50%
Tyas, Randi, Wahyu | Enhancement (RICEFW) Design | WRICEF enhancement Tcode SD |  | Planned | 0%
W15(14 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | Done | 100%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 25%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 25%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 25%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | Planned | 0%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 |  | In Progress | 25%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | Planned | 0%
W16(17 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 50%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | Planned | 0%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | Planned | 0%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | Planned | 0%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | Planned | 0%
W16(18 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 50%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | In Progress | 50%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | In Progress | 25%
W16(19 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | Done | 100%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | Done | 100%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | Done | 100%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 |  | Done | 100%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | Done | 100%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | Done | 100%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont |  | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | In Progress | 25%
W16(20 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont |  | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | In Progress | 50%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Transaksi Penjualan for scenario 9 dan 10 (Step 2) |  | Done | 100%
Randi, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | In Progress | 50%
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | In Progress | 50%
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 50%
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 50%
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 25%
W16(21 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont |  | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | Done | 100%
Randi, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | Done | 100%
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | In Progress | 75%
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 75%
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 75%
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 50%
Tyas, Randi, Wahyu | Blueprint Confirmation | Business Blueprint & Business Processes are confirmed by Mr. Lai, PPIC, CKI |  | Done | 100%
Randi | Business Processes Confirmation w/ Pak Garry | Business Processes are confirmed by Pak Garry |  | Done | 100%
W17(24 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design | Review List Configuration Design SD for new SO Type, DO Type, Billing Type | Design Configuration is Reviewed | Planned | 0%
Randi | Enhancement (RICEFW) Design | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25%
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | RICEFW has been enhancement and tested | In Progress | 75%
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW has been enhancement and tested | In Progress | 75%
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW has been enhancement and tested | In Progress | 75%
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW has been enhancement and tested | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SD Organizational Unitz | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SD General Settings | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDGI01 Reverse Goods Movement | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDCM01 Release Delivery Block karena Terms of Payments | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO11 Sales with Down Payment | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO27 Sales Order Inventory | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO01 Domestic Sales Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO02 Domestic Sales Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO07 Export Sales Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO08 Export Sales Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO13 Domestic Sample Order Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO14 Domestic Sample Order Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO17 Export Sample Order Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO18 Export Sample Order Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX | Intergration Testing for New Production Line | Intergration Testing for New Production Line Done | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW is reviewed | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW is reviewed | Planned | 0%
Tyas | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW is reviewed | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | RICEFW is reviewed | Planned | 0%
Randi | Enhancement (RICEFW) Design | Review RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | RICEFW is reviewed | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | RICEFW is reviewed | Planned | 0%

## Refresh of SD (hidden)
Daily Activity
W01
W01 (07 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
CONFIGURATION
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 | Configuration is created | In Progress | 25% | 2024-11-12
W01 (08 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 | Configuration is created | In Progress | 50% | 2024-11-12
W02
W02 (11 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 | Configuration is created | In Progress | 75% | 2024-11-12
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W02 (12 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 | Configuration is created | Done | 100% | 2024-11-12
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W02 (13 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W02 (14 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W02 (15 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W03
W03 (18 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W03 (19 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W03 (20 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W03 (21 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W03 (22 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W04
W04 (25 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W04 (26 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W04 (28 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W04 (29 November 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcon in DEV NC All Scenario | Integration testing is done | In Progress | 50% | 2025-01-28
W07
W07 (19 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcont scenario 1, 2, 4, 5, 6 in DEV NC | Integration testing is done | Done | 100% | 2024-12-19
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcont scenario 7 A B C (cycle 2) in DEV NC | Integration testing is done | In Progress | 25% | 2024-12-20
W07 (20 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcont scenario 7 A B C (cycle 2) in DEV NC | Integration testing is done | Done | 100% | 2024-12-20
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcont scenario 8 A B (cycle 2) in DEV NC | Integration testing is done | In Progress | 0% | 2024-12-23
W08
W08(23 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Run Integration Testing for Subcont scenario 8 A B (cycle 2) in DEV NC | Integration testing is done | Done | 100% | 2024-12-23
Tyas, Randi | 2.1 Business Blueprint Design | Update Business Blueprint | Blueprint updated | In Progress | 0% | 2024-12-24
W08(26 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | Update Business Blueprint | Blueprint updated | In Progress | 50% | 2025-01-03
W09
W09(03 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | Update SD Organizational Unitz | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SD General Settings | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDGI01 Reverse Goods Movement | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDCM01 Release Delivery Block karena Terms of Payments | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO11 Sales with Down Payment | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO27 Sales Order Inventory | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO01 Domestic Sales Finished Goods (1st Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO02 Domestic Sales Finished Goods (2nd Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO07 Export Sales Finished Goods (1st Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO08 Export Sales Finished Goods (2nd Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO13 Domestic Sample Order Finished Goods (1st Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO14 Domestic Sample Order Finished Goods (2nd Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO17 Export Sample Order Finished Goods (1st Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | 2.1 Business Blueprint Design | Update SDSO18 Export Sample Order Finished Goods (2nd Grade) | Blueprint updated | Done | 100% | 2025-01-03
Tyas, Randi | Integration Testing | Run Integration Testing (Create SO) in DEV NC All Scenario | Integration testing is done | Done | 100% | 2025-01-06
Tyas, Randi | Integration Testing | Run Integration Testing (Transaksi Penjualan) in DEV NC All Scenario | Integration testing is done | Planned | 0% | 2025-01-28
W10
W10(06 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | SD Organizational Unitz |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SD General Settings |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDGI01 Reverse Goods Movement |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDCM01 Release Delivery Block karena Terms of Payments |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO11 Sales with Down Payment |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO27 Sales Order Inventory |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO01 Domestic Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO02 Domestic Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO07 Export Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO08 Export Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO13 Domestic Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO14 Domestic Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO17 Export Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO18 Export Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | Integration Testing | Run Integration Testing (Create SO) in DEV NC All Scenario | Integration testing is done | Done | 100% | 2025-01-06
Tyas, Randi | Integration Testing | Run Integration Testing (Transaksi Penjualan) in DEV NC All Scenario | Integration testing is done | Planned | 0% | 2025-01-28
W11
W11(13Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait transport posting (Free To So, So To So, So To Free) for RM | Discovery is done | Done | 100% | 2025-01-13
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle | Discovery is done | In Progress | 50% | 2025-01-31
Tyas, Randi | Integration Testing | Run integration testing (Transaksi Penjualan for scenario 10A, 10B, 11A, 11B, 12A, 12B) in DEV NC | Integration testing is done | Done | 100% | 2025-01-31
W11(14Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle | Discovery is done | In Progress | 50% | 2025-01-31
Tyas, Randi | Integration Testing | Run integration testing (Transaksi Penjualan for scenario 13A, 13B) in DEV NC | Integration testing is done | In Progress | 50% | 2025-01-31
Tyas, Randi | Integration Testing | Run integration testing (Transaksi Penjualan for scenario 10C, 11C, 12C, 13C) in DEV NC | Integration testing is done | Planned | 0% | 2025-01-31
W13
W13(31 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle | Discovery is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | Integration Testing | Run integration testing (Transaksi Penjualan for scenario 13A, 13B) in DEV NC | Integration testing is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | Integration Testing | Run integration testing (Transaksi Penjualan for scenario 10C, 11C, 12C, 13C) in DEV NC | Integration testing is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config SO Type, DO Type, Billing Type for LAM SUBCONTRACTED (DEV NC) | Configuration in DEV NC is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config SO Type, DO Type for Recycle Disposal (DEV NC) | Configuration in DEV NC is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config Division for OUTSOURCE LAMINATE, LAM SUBCONTRACTED, REC SUBCONTRACTED (DEV NC) | Configuration in DEV NC is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config AAG Material for LAM SUBCONTRACTED | Configuration in DEV NC is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Run integration testing (Transaksi Penjualan for scenario 14A, 14B, 14C) in DEV NC | Integration testing is done | Done | 100% | 2025-01-31
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD) in DEV NC | Discovery is done | In Progress | 25% | 2025-02-14
W14
W14(03 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Run integration testing (Transaksi Penjualan for Recycle Subcont all scenario) in DEV NC | Integration testing is done | Done | 100% | 2025-02-03
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD | Discovery is done | In Progress | 50% | 2025-02-14
W14(04 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD | Discovery is done | In Progress | 50% | 2025-02-14
Tyas, Randi, Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created WRICEF enhancement Tcode SD | RICEFW is created | Planned | 0%
W15
W15(14 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD | Discovery is done | Done | 100% | 2025-02-14
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW is created | In Progress | 25% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW is created | In Progress | 25% | 2025-02-19
Tyas | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW is created | In Progress | 25% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | RICEFW is created | In Progress | 25% | 2025-02-19
W16
W16(17 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW is created | In Progress | 50% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW is created | In Progress | 50% | 2025-02-19
Tyas | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW is created | In Progress | 50% | 2025-02-19
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Update List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | List Config is updated | Planned | 0%
W16(18 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW is created | In Progress | 50% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW is created | In Progress | 50% | 2025-02-19
Tyas | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW is created | In Progress | 50% | 2025-02-19
Malak | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | RICEFW is created | In Progress | 50% | 2025-02-19
Malak | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-06 ZOLAPSLS | RICEFW is created | In Progress | 50% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | RICEFW is created | In Progress | 50% | 2025-02-19
Malak | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT | RICEFW is created | In Progress | 50% | 2025-02-19
Randi | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | RICEFW is created | In Progress | 50% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | RICEFW is created | In Progress | 50% | 2025-02-19
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Update List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | List Config is updated | In Progress | 25%
W16(19 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW is created | Done | 100% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW is created | Done | 100% | 2025-02-19
Tyas | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW is created | Done | 100% | 2025-02-19
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | RICEFW is created | In Progress | 50% | 2025-02-19
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | RICEFW is created | In Progress | 50% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | RICEFW is created | Done | 100% | 2025-02-19
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT | RICEFW is created | In Progress | 50% | 2025-02-19
Randi | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | RICEFW is created | Done | 100% | 2025-02-19
Wahyu | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | RICEFW is created | Done | 100% | 2025-02-19
Randi | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Update List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | List Config is updated | In Progress | 25% | 2025-02-21
W16(20 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design (Phase 2) | Created RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Update List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | List Config is updated | In Progress | 50% | 2025-02-21
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Run integration testing (Transaksi Penjualan for scenario 9 dan 10 (Step 2)) in DEV NC | Integration testing is done | Done | 100% | 2025-02-21
Randi, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | Unit Testing on DEV NC is done | In Progress | 50% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 50% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 50% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 50% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 25% | 2025-03-03
W16(21 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design (Phase 2) | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design (Phase 2) | Cretaed RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Update List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | List Config is updated | Done | 100% | 2025-02-21
Randi, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | Unit Testing on DEV NC is done | Done | 100% | 2025-02-21
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 50% | 2025-03-03
Tyas, Randi, Wahyu | Blueprint Confirmation | Business Blueprint & Business Processes are confirmed by Mr. Lai, PPIC, CKI | Confirmation is done | Done | 100% | 2025-02-21
Randi | Business Processes Confirmation w/ Pak Garry | Business Processes are confirmed by Pak Garry | Confirmation is done | Done | 100% | 2025-02-21
W17
W17(24 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Review List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | Design Configuration is Reviewed | Planned | 0%
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 25% | 2025-03-03
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SD Organizational Unitz | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SD General Settings | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDGI01 Reverse Goods Movement | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDCM01 Release Delivery Block karena Terms of Payments | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO11 Sales with Down Payment | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO27 Sales Order Inventory | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO01 Domestic Sales Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO02 Domestic Sales Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO07 Export Sales Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO08 Export Sales Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO13 Domestic Sample Order Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO14 Domestic Sample Order Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO17 Export Sample Order Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO18 Export Sample Order Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line | Integration Testing on DEV 130 AIX is done | In Progress | 25% | 2025-02-28
W17(25 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Discovery Design Config for new SO Type (Fill Target Quantity in new SO Type) | Design Config is discovered | In Progress | 25% | 2025-02-26
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 50% | 2025-03-03
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line | Integration Testing on DEV 130 AIX is done | In Progress | 25% | 2025-02-28
W17(26 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Discovery Design Config for new SO Type (Fill Target Quantity in new SO Type) | Design Config is discovered | Done | 100% | 2025-02-26
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 50% | 2025-03-03
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line | Integration Testing on DEV 130 AIX is done | In Progress | 25% | 2025-02-28
W17(27 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Revise List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | List Config is revised | In Progress | 50% | 2025-02-28
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line | Integration Testing on DEV 130 AIX is done | In Progress | 25% | 2025-02-28
W17(28 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Revise List Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | List Config is revised | Done | 100% | 2025-02-28
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line | Integration Testing on DEV 130 AIX is done | Done | 100% | 2025-02-28
W18
W18(03 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Revise Details of Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | Details of Configuration Design (Phase 2) is revised | Planned | 0% | 2025-03-07
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
W18(04 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Revise Details of Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | Details of Configuration Design (Phase 2) is revised | In Progress | 25% | 2025-03-07
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
W18(05 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Revise Details of Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | Details of Configuration Design (Phase 2) is revised | In Progress | 50% | 2025-03-07
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
W18(06 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Revise Details of Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | Details of Configuration Design (Phase 2) is revised | In Progress | 75% | 2025-03-07
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line (Dom. Sales Order Scrap Film & Dom. Sales Order Recycle) | Integration Testing on DEV 130 AIX is done | In Progress | 50% | 2025-03-07
W18(07 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design (Phase 2) | Revise Details of Configuration Design (Phase 2) SD for new SO Type, DO Type, Billing Type | Details of Configuration Design (Phase 2) is revised | Done | 100% | 2025-03-07
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line (Dom. Sales Order Scrap Film & Dom. Sales Order Recycle) | Integration Testing on DEV 130 AIX is done | Done | 100% | 2025-03-07
W19
W19(10 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Randi | Enhancement (RICEFW) Design (Phase 2) | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25% | 2025-03-03
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC (Phase 2) | Unit Testing for RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Unit Testing on DEV NC is done | In Progress | 75% | 2025-03-03
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX (Phase 1) | Run Intergration Testing for New Production Line ((Domestic Sales Order 1st Grade LAMI (Slitting Coater) & Domestic Sales Order 1st Grade LAMI 3 (Make To Stock)) | Integration Testing on DEV 130 AIX is done | Done | 100% | 2025-03-10
W19(11 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)

## ABAP (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi, Dila, Ryan | Discover all tcode/program that use hard coded of order type | Get list of all tcode/program that use hard coded of order type | List hardcode is documented | In Progress | 25% | 2024-11-11
Ryan | DISC-ABAP-LAM01 Discover hard code order type in ZPP041 (Eksekusi JR) | Get list of hard coded order type in ZPP041 | List hardcode is documented | In Progress | 25% | 2024-11-15
Budi | DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Download PRO JR) | Get list of hard coded order type in ZPP002 | List hardcode is documented | In Progress | 25% | 2024-11-15
Dila | DISC-ABAP-LAM03 Discover Hard Code Order Type in ZPP001 (Eksekusi SR) | Get list of hard coded order type in ZPP001 | List hardcode is documented | In Progress | 25% | 2024-11-15
W01 (08 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi, Dila, Ryan | Discover all tcode/program that use hard coded of order type | Get list of all tcode/program that use hard coded of order type | List hardcode is documented | Done | 100% | 2024-11-11
Ryan | DISC-ABAP-LAM01 Discover hard code order type in ZPP041 (Eksekusi JR) | Get list of hard coded order type in ZPP041 | List hardcode is documented | In Progress | 25% | 2024-11-15
Budi | DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Download PRO JR) | Get list of hard coded order type in ZPP002 | List hardcode is documented | In Progress | 25% | 2024-11-15
Dila | DISC-ABAP-LAM03 Discover Hard Code Order Type in ZPP001 (Eksekusi SR) | Get list of hard coded order type in ZPP001 | List hardcode is documented | In Progress | 25% | 2024-11-15
W02 (11 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM01 Discover hard code order type in ZPP041 (Eksekusi JR) | Get list of hard coded order type in ZPP041 | List hardcode is documented | In Progress | 75% | 2024-11-15
Budi | DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Download PRO JR) | Get list of hard coded order type in ZPP002 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM03 Discover hard code order type in ZPP001 (Eksekusi SR) | Get list of hard coded order type in ZPP001 | List hardcode is documented | In Progress | 75% | 2024-11-15
W02 (12 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM01 Discover hard code order type in ZPP041 (Eksekusi JR) | Get list of hard coded order type in ZPP041 | List hardcode is documented | In Progress | 75% | 2024-11-15
Budi | DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Planning JR) | Get list of hard coded order type in ZPP002 | List hardcode is documented | In Progress | 75% | 2024-11-15
Budi | DISC-ABAP-LAM06 Discover Hard Code Order Type in ZTPP002 (Download PRO JR) | Get list of hard coded order type in ZTPP002 | List hardcode is documented | In Progress | 25% | 2024-11-15
Dila | DISC-ABAP-LAM03 Discover hard code order type in ZPP001 (Eksekusi SR) | Get list of hard coded order type in ZPP001 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM04 Discover Hard Code Order Type in ZPP011 (Report JR Harian) | Get list of hard coded order type in ZPP011 | List hardcode is documented | In Progress | 25% | 2024-11-15
Dila | DISC-ABAP-LAM08 Discover Hard Code Order Type in ZTPP011 | Get list of hard coded order type in ZTPP011 | List hardcode is documented | In Progress | 25% | 2024-11-15
W02 (13 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM01 Discover hard code order type in ZPP041 (Eksekusi JR) | Get list of hard coded order type in ZPP041 | List hardcode is documented | In Progress | 75% | 2024-11-15
Budi | DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Planning JR) | Get list of hard coded order type in ZPP002 | List hardcode is documented | In Progress | 75% | 2024-11-15
Budi | DISC-ABAP-LAM06 Discover Hard Code Order Type in ZTPP002 (Download PRO JR) | Get list of hard coded order type in ZTPP002 | List hardcode is documented | In Progress | 25% | 2024-11-15
Dila | DISC-ABAP-LAM03 Discover hard code order type in ZPP001 (Eksekusi SR) | Get list of hard coded order type in ZPP001 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM04 Discover Hard Code Order Type in ZPP011 (Report JR Harian) | Get list of hard coded order type in ZPP011 | List hardcode is documented | In Progress | 25% | 2024-11-15
Dila | DISC-ABAP-LAM08 Discover Hard Code Order Type in ZTPP011 | Get list of hard coded order type in ZTPP011 | List hardcode is documented | In Progress | 75% | 2024-11-15
W02 (14 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM01 Discover hard code order type in ZPP041 (Eksekusi JR) | Get list of hard coded order type in ZPP041 | List hardcode is documented | In Progress | 75% | 2024-11-15
Budi | DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Planning JR) | Get list of hard coded order type in ZPP002 | List hardcode is documented | In Progress | 75% | 2024-11-15
Budi | DISC-ABAP-LAM06 Discover Hard Code Order Type in ZTPP002 (Download PRO JR) | Get list of hard coded order type in ZTPP002 | List hardcode is documented | In Progress | 25% | 2024-11-15
Dila | DISC-ABAP-LAM03 Discover hard code order type in ZPP001 (Eksekusi SR) | Get list of hard coded order type in ZPP001 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM04 Discover Hard Code Order Type in ZPP011 (Report JR Harian) | Get list of hard coded order type in ZPP011 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM08 Discover Hard Code Order Type in ZTPP011 | Get list of hard coded order type in ZTPP011 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM08 Discover Hard Code Order Type in ZPP016 | Get list of hard coded order type in ZPP016 | List hardcode is documented | In Progress | 25% | 2024-11-22
W02 (15 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM01 Discover hard code order type in ZPP041 (Eksekusi JR) | Get list of hard coded order type in ZPP041 | List hardcode is documented | Done | 100% | 2024-11-15
Budi | DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Planning JR) | Get list of hard coded order type in ZPP002 | List hardcode is documented | Done | 100% | 2024-11-15
Budi | DISC-ABAP-LAM06 Discover Hard Code Order Type in ZTPP002 (Download PRO JR) | Get list of hard coded order type in ZTPP002 | List hardcode is documented | Done | 100% | 2024-11-15
Dila | DISC-ABAP-LAM03 Discover hard code order type in ZPP001 (Eksekusi SR) | Get list of hard coded order type in ZPP001 | List hardcode is documented | Done | 100% | 2024-11-15
Dila | DISC-ABAP-LAM04 Discover Hard Code Order Type in ZPP011 (Report JR Harian) | Get list of hard coded order type in ZPP011 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM08 Discover Hard Code Order Type in ZTPP011 | Get list of hard coded order type in ZTPP011 | List hardcode is documented | In Progress | 75% | 2024-11-15
Dila | DISC-ABAP-LAM08 Discover Hard Code Order Type in ZPP016 | Get list of hard coded order type in ZPP016 | List hardcode is documented | In Progress | 25% | 2024-11-22
W03 (18 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM02 Discover Hard Code Order Type in ZPP060 (Good Issue JR) | Get list of hard coded order type in ZPP060 | List hardcode is documented | In Progress | 50% | 2024-11-22
Ryan | DISC-ABAP-LAM07 Discover Hard Code Order Type in ZTPP060 (Insert GI PRO JR to SQL) | Get list of hard coded order type in ZTPP060 | List hardcode is documented | In Progress | 25% | 2024-11-22
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 25% | 2024-11-22
Budi | DISC-ABAP-LAM09 Discover Hard Code Order Type in ZCOR6M (Confirmation Mixing) | Get list of hard coded order type in ZCOR6M | List hardcode is documented | In Progress | 25% | 2024-11-22
W03 (19 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM02 Discover Hard Code Order Type in ZPP060 (Good Issue JR) | Get list of hard coded order type in ZPP060 | List hardcode is documented | Done | 100% | 2024-11-22
Ryan | DISC-ABAP-LAM07 Discover Hard Code Order Type in ZTPP060 (Insert GI PRO JR to SQL) | Get list of hard coded order type in ZTPP060 | List hardcode is documented | Done | 100% | 2024-11-22
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 25% | 2024-11-22
Budi | DISC-ABAP-LAM09 Discover Hard Code Order Type in ZCOR6M (Confirmation Mixing) | Get list of hard coded order type in ZCOR6M | List hardcode is documented | In Progress | 25% | 2024-11-22
W03 (20 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 25% | 2024-12-06
Ryan | DISC-ABAP-LAM13 Discover Hard Code Order Type ZPP_TB (Timbang) | Get list of hard coded order type in ZPP_TB | List hardcode is documented | In Progress | 0% | 2024-12-06
Budi | DISC-ABAP-LAM09 Discover Hard Code Order Type in ZCOR6M (Confirmation Mixing) | Get list of hard coded order type in ZCOR6M | List hardcode is documented | In Progress | 25% | 2024-11-22
W03 (21 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 25% | 2024-12-06
Ryan | DISC-ABAP-LAM13 Discover Hard Code Order Type ZPP_TB (Timbang) | Get list of hard coded order type in ZPP_TB | List hardcode is documented | In Progress | 0% | 2024-12-06
Budi | DISC-ABAP-LAM09 Discover Hard Code Order Type in ZCOR6M (Confirmation Mixing) | Get list of hard coded order type in ZCOR6M | List hardcode is documented | Done | 100% | 2024-11-22
W04 (28 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 25% | 2024-12-06
Ryan | DISC-ABAP-LAM13 Discover Hard Code Order Type ZPP_TB (Timbang) | Get list of hard coded order type in ZPP_TB | List hardcode is documented | In Progress | 0% | 2024-12-06
Budi | DISC-ABAP-LAM12 Discover Hard Code Order Type ZPP_RC (Closing Raw Recycle) | Get list of hard coded order type in ZPP_RC | List hardcode is documented | In Progress | 25% | 2024-11-29
Budi | DISC-ABAP-LAM19 Discover Hard Code Material Group ZPP016N | Get list of hard coded order type in ZPP016N | List hardcode is documented | In Progress | 25% | 2024-11-29
Dila | DISC-ABAP-LAM16 Discover Hard Code Material Group ZPP016 | Get list of hard coded material group in ZPP016 | List hardcode is documented | Done | 100% | 2024-11-29
W04 (29 November 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 25% | 2024-12-06
Ryan | DISC-ABAP-LAM13 Discover Hard Code Order Type ZPP_TB (Timbang) | Get list of hard coded order type in ZPP_TB | List hardcode is documented | In Progress | 75% | 2024-12-06
Budi | DISC-ABAP-LAM12 Discover Hard Code Order Type ZPP_RC (Closing Raw Recycle) | Get list of hard coded order type in ZPP_RC | List hardcode is documented | Done | 100% | 2024-11-29
Budi | DISC-ABAP-LAM19 Discover Hard Code Material Group ZPP016N | Get list of hard coded order type in ZPP016N | List hardcode is documented | Done | 100% | 2024-11-29
Dila | DISC-ABAP-LAM17 Discover Hard Code Material Group ZPP016CX | Get list of hard coded material group in ZPP016CX | List hardcode is documented | In Progress | 25% | 2024-11-29
Dila | DISC-ABAP-LAM18 Discover Hard Code Material Group ZTPP016N | Get list of hard coded material group in ZPP016N | List hardcode is documented | In Progress | 25% | 2024-11-29
W01 (4 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 25% | 2024-12-06
Ryan | DISC-ABAP-LAM13 Discover Hard Code Order Type ZPP_TB (Timbang) | Get list of hard coded order type in ZPP_TB | List hardcode is documented | Done | 100% | 2024-12-06
Dila | DISC-ABAP-LAM17 Discover Hard Code Material Group ZPP016CX | Get list of hard coded material group in ZPP016CX | List hardcode is documented | Done | 100% | 2024-11-29
Dila | DISC-ABAP-LAM18 Discover Hard Code Material Group ZTPP016N | Get list of hard coded material group in ZPP016N | List hardcode is documented | Done | 100% | 2024-11-29
Budi | DISC-ABAP-LAM20 Discover Hard Code Title Bar T-Code Variant ZPP041 | Get list of hard coded tittle bar ZPP041 | List hardcode is documented | Done | 100% | 2024-12-06
Budi | DISC-ABAP-LAM21 Discover Hard Code Sloc in ZPP019 (Process Order For Roll Stripping) | Get list of hard coded order type in ZPP019 | List hardcode is documented | In Progress | 75% | 2024-12-06
Budi | DISC-ABAP-LAM22 Discover Hard Code Sloc in ZPP005N (Report Pending Order) | Get list of hard coded sloc in ZPP005N | List hardcode is documented | In Progress | 25% | 2024-12-06
W01 (5 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | In Progress | 50% | 2024-12-06
Dila | DISC-ABAP-LAM17 Discover Hard Code Material Group ZPP016CX | Get list of hard coded material group in ZPP016CX | List hardcode is documented | Done | 100% | 2024-11-29
Dila | DISC-ABAP-LAM18 Discover Hard Code Material Group ZTPP016N | Get list of hard coded material group in ZPP016N | List hardcode is documented | Done | 100% | 2024-11-29
Budi | DISC-ABAP-LAM20 Discover Hard Code Title Bar T-Code Variant ZPP041 | Get list of hard coded tittle bar ZPP041 | List hardcode is documented | Done | 100% | 2024-12-06
Budi | DISC-ABAP-LAM21 Discover Hard Code Sloc in ZPP019 (Process Order For Roll Stripping) | Get list of hard coded order type in ZPP019 | List hardcode is documented | Done | 100% | 2024-12-06
Budi | DISC-ABAP-LAM22 Discover Hard Code Sloc in ZPP005N (Report Pending Order) | Get list of hard coded sloc in ZPP005N | List hardcode is documented | Done | 100% | 2024-12-06
Budi | DISC-ABAP-LAM23 Discover Post Good Movement for JR Execution (Special Stock) | Discover Movement for Free Stock or Special Stock in ZPP041 | Flow program is documented | In Progress | 75% | 2024-12-20
W01 (6 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan | DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | Get list of hard coded order type in ZPP_RS | List hardcode is documented | Done | 100% | 2024-12-06
W02 (13 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Budi, Dila | Create Enhancement Summary | Get list of enhancement needed | List hardcode is documented | Done | 100% | 2024-12-13
W03 (16 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi | DISC-ABAP-LAM23 Discover Post Good Movement for JR Execution (Special Stock) | Discover Movement for Free Stock or Special Stock in ZPP041 | Flow program is documented | In Progress | 75% | 2024-12-20
W03 (17 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi | DISC-ABAP-LAM23 Discover Post Good Movement for JR Execution (Special Stock) | Discover Movement for Free Stock or Special Stock in ZPP041 | Flow program is documented | In Progress | 75% | 2024-12-20
W03 (18 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi | DISC-ABAP-LAM23 Discover Post Good Movement for JR Execution (Special Stock) | Discover Movement for Free Stock or Special Stock in ZPP041 | Flow program is documented | In Progress | 75% | 2024-12-20
W03 (19 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi | DISC-ABAP-LAM23 Discover Post Good Movement for JR Execution (Special Stock) | Discover Movement for Free Stock or Special Stock in ZPP041 | Flow program is documented | In Progress | 75% | 2024-12-20
W03 (20 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Budi | DISC-ABAP-LAM23 Discover Post Good Movement for JR Execution (Special Stock) | Discover Movement for Free Stock or Special Stock in ZPP041 | Flow program is documented | Done | 100% | 2024-12-20
Dila | DISC-ABAP-LAM25 List Job for OLAP | List job yang ada di SAP untuk kebutuhan OLAP | Job list is documented | Done | 100% | 2024-12-20
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
W03 (20 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
W04 (23 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
W04 (24 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
W04 (26 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
W04 (27 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
W05 (30 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
W05 (31 Desember 2024)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
W05 (02 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 25%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
W05 (03 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 50%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
W06 (06 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 50%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
Ryan | RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-01-06
Ryan | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
W06 (07 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 50%
Ryan, Dila, Budi | Discuss flow JR to SR ( | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
Ryan | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Flow program is documented | In Progress | 25% | 2024-12-17
W06 (08 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 50%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
Ryan | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed |  | In Progress | 25% | 2024-12-17
W06 (09 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 50%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
Ryan | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Flow program is documented | In Progress | 25% | 2024-12-17
W06 (10 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | In Progress | 50%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 0% | 2024-12-28
Ryan | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed |  | In Progress | 25% | 2024-12-17
W07 (13 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila | DISC-ABAP-LAM24 Discover One Push Button JR to SR | Discover One Push Button JR to SR | Flow program is documented | Done | 100%
Ryan, Dila, Budi | Discuss flow JR to SR | Flow JR to SR documented | Flow program is documented | In Progress | 75% | 2024-12-28
Ryan | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-06
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed |  | In Progress | 25% | 2024-12-17
W07 (14 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Flow JR to SR documented | Flow program is documented | In Progress | 75% | 2024-12-28
Ryan | RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-01-06
Budi | RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-01-06
Dila | RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-01-06
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Bug program is fixed | Program is developed and tested in DEV NC | In Progress | 50% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Flow program is documented | In Progress | 25% | 2024-12-17
W07 (15 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Flow JR to SR documented | Flow program is documented | In Progress | 75% | 2024-12-28
Randi, Dila | Discuss Adjustment SR-O to SR-X for Customer Stock | Program is developed | Program is developed and tested in DEV NC | In Progress | 50%
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Bug program is fixed | Flow program is documented | In Progress | 50% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Flow program is documented | In Progress | 25% | 2024-12-17
Dila | Adjustment SR-O to SR-X for Customer Stock | Program is developed | Program is developed and tested in DEV NC | In Progress | 25% | 2024-12-17
W07 (16 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Flow JR to SR documented | Flow program is documented | In Progress | 75% | 2024-12-28
Randi, Dila | Discuss Adjustment SR-O to SR-X for Customer Stock | Program is developed | Program is developed and tested in DEV NC | In Progress | 50%
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Bug program is fixed | Program is developed in DEV NC | In Progress | 50% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Flow program is documented | In Progress | 25% | 2024-12-17
Dila | Adjustment SR-O to SR-X for Customer Stock | Program is developed | Program is developed and tested in DEV NC | In Progress | 25% | 2024-12-17
W07 (17 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Discuss Flow JR to SR | Flow JR to SR is documented | In Progress | 75% | 2024-12-28
Randi, Dila | Discuss Adjustment SR-O to SR-X for Customer Stock | Program is developed | Program is developed and tested in DEV NC | In Progress | 50%
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Bug program is fixed | Program is developed and tested in DEV NC | In Progress | 50% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Program is developed and tested in DEV NC | In Progress | 25% | 2024-12-17
Dila | Adjustment SR-O to SR-X for Customer Stock | Program is developed | Program is developed and tested in DEV NC | In Progress | 25% | 2024-12-17
W08 (23 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Discuss Flow JR to SR | Flow JR to SR is documented | Done | 100% | 2024-12-28
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Fix bug program in DEV NC | Program is fixed and tested in DEV NC | Done | 100% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Flow program is documented | Done | 100% | 2024-12-17
Budi, Ana | Discuss Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Discuss Flow JR to SR | Flow JR to SR is documented | In Progress | 75% | 2024-12-24
Budi | RICEFW-MMPP-LAMI2&3-03 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Program is developed | Program is developed and tested in DEV NC | In Progress | 25% | 2024-12-28
Budi | RICEFW-MMPP-LAMI2&3-05 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | Program is developed | Program is developed and tested in DEV NC | In Progress | 75% | 2024-12-28
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-01-28
W08 (24 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Discuss Flow JR to SR | Flow JR to SR documented | Done | 100% | 2024-12-28
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Fix bug program in DEV NC | Program is fixed and tested in DEV NC | Done | 100% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Program is developed and tested in DEV NC | Done | 100% | 2024-12-17
Budi, Ana | Discuss Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Discuss Flow JR to SR | Flow JR to SR documented | In Progress | 75% | 2024-12-24
Budi | RICEFW-MMPP-LAMI2&3-03 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2024-12-28
Budi | RICEFW-MMPP-LAMI2&3-05 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2024-12-28
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-01-28
Ryan | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013N) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-01-31
W09 (28 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Discuss Flow JR to SR | Flow JR to SR is documented | Done | 100% | 2024-12-28
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Fix bug program in DEV NC | Program is fixed and tested in DEV NC | Done | 100% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Program is developed and tested in DEV NC | Done | 100% | 2024-12-17
Budi, Ana | Discuss Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Discuss Flow JR to SR | Flow JR to SR is documented | In Progress | 75% | 2024-12-24
Budi | RICEFW-MMPP-LAMI2&3-03 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2024-12-28
Budi | RICEFW-MMPP-LAMI2&3-05 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2024-12-28
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-28
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-02-05
Ryan | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013N) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-01-31
W09 (30 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Ryan, Dila, Budi, Randi, Ana | Discuss flow JR to SR (Create PRO Ori, Combine and Mapping Sloc SR) | Discuss Flow JR to SR | Flow JR to SR is documented | Done | 100% | 2024-12-28
Budi, Dila | Fix bug program One Push Button JR to SR (Mapping Order Type by Plant) | Fix bug program in DEV NC | Program is fixed and tested in DEV NC | Done | 100% | 2024-12-17
Budi, Dila | Develop Program One Push Button JR to SR | Program One Push Button JR to SR is developed | Program is developed and tested in DEV NC | Done | 100% | 2024-12-17
Budi, Ana | Discuss Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Discuss Flow JR to SR | Flow JR to SR is documented | Done | 100% | 2024-12-24
Budi | RICEFW-MMPP-LAMI2&3-03 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2024-12-28
Budi | RICEFW-MMPP-LAMI2&3-05 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2024-12-28
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-28
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-02-05
Ryan | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013N) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-31
Budi, Ryan | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-02-05
W09 (30 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-28
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-02-05
Ryan | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-31
Budi, Ryan | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-05
Ryan | RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-05
W09 (31 Januari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-28
William, Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-05
Ryan | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-31
Budi, Ryan | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-05
Ryan | RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-05
W10 (03 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-28
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-05
Ryan | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-01-31
Budi, Ryan | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-05
Ryan | RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-05
W12 (13 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-14
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-14
Anbow | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | Program is developed |  | Done | 100% | 2025-02-14
Anbow | RICEFW-SD-LAMI2&3-06 ZOLAP_SALES_DETAIL_IT | Program is developed |  | Done | 100% | 2025-02-14
W12 (14 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
William | DISC-ABAP-LAM24 Discover Hard Code Recycle Execution ZPP_RE | Discover hardcode in ZPP_RE | Discovery result is documented | Done | 100% | 2025-02-14
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-14
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-14
W12 (17 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-17
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-17
Budi | RICEFW-MMPP-LAMI2&3-02 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL custom validation customer based on matgroup) | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-21
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-17
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-17
W12 (18 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop template design in DEV NC | Template design is developed in DEV NC | In Progress | 25% | 2025-02-20
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop template design in DEV NC | Template design is developed in DEV NC | In Progress | 25% | 2025-02-20
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-17
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-20
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-20
W12 (21 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Program is developed in DEV AIX | Program is developed and tested in DEV AIX | Done | 100% | 2025-01-28
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-27
Ryan | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | Develop program in DEV AIX | Program is developed and tested in DEV AIX | Done | 100% | 2025-01-31
Budi, Ryan | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-05
Ryan | RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | Develop program in DEV AIX | Program is developed and tested in DEV AIX | Done | 100% | 2025-02-05
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-21
Budi | RICEFW-MMPP-LAMI2&3-02 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL custom validation customer based on matgroup) | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-21
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-21
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-02-25
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Program is developed in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-17
W13 (24 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-24
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-27
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 25% | 2025-02-27
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Program is developed in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | Planned | 0% | 2025-02-28
W13 (25 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 75% | 2025-02-24
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-27
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-27
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Program is developed in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | Planned | 0% | 2025-02-28
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop program in DEV NC | Program is developed and tested in DEV NC | In Progress | 50% | 2025-02-27
W13 (26 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-24
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-27
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-02-27 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Program is developed in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-02-28
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop program in DEV NC | Program is developed and tested in DEV NC | Done | 100% | 2025-02-27
W13 (27 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-02-27 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-02-28
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
W13 (28 Februari 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-02-27 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-02-27
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-02-28
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-02-27
W14 (3 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W14 (4 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W14 (5 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W14 (6 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W14 (7 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W15 (10 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W15 (11 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W15 (12 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W15 (13 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
W15 (14 Maret 2025)
Team | Activity in WBS | Target/Activity | Deliverables | Status | Status (%) | Target (Date)
Dila | RICEFW-SDMM-LAMI2&3-01 Sales & Receiving Support Document Creation for Subcontracting Laminator (ZIC004SL) - Terdapat tambahan kolom PO Customer | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Budi | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
William | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Develop program in DEV NC | Program is developed and tested in DEV NC | On Hold | 50% | 2025-03-07 | RICEF belum selesai, belum ada kepastian untuk diteruskan atau tidak
William | RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
William | RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
Dila | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Develop program in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 75% | 2025-03-07
All ABAP | Review Enhanced Program | Review finished program/enhancement | All Programs/Enhancements are reviewed | In Progress | 25% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Develop Program and Smartform in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07
Fany | RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Develop Program and Template in DEV AIX | Program is developed and tested in DEV AIX | In Progress | 50% | 2025-03-07

## FICO (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Yuki, Munah, Haikal | 1.2.1 SAP Discovery and Evaluation | Discovery list for Project Laminator #2 #3 Completed | List konfigurasi Modul FICO lengkap | Done | 100% | 2024-11-07
W01 (08 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-CO-LAM00 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List konfigurasi Modul FICO lengkap | Done | 100% | 2024-11-08
| DISC-FI-LAM02 Master Data GL Account | Get List of GL Account for New Production Line Laminator #2 & #3 | Mempersiapkan GL Account New Line Production | In Progress | 25% | 2024-11-08
| DISC-FI-LAM03 Define Valuation Class | Get List of Valuation Class for New Production Line Laminator #2 & #3 | Mempersiapkan Valuation Class New Line Production | Done | 100% | 2024-11-08
| DISC-FI-LAM04 Automatic Materials Management Posting | Get GL Account used for Valuation Class of New Production Line Laminator #2 & #3 | Mempersiapkan GL Account di valuation class New Line Production | Done | 100% | 2024-11-08
Haikal | DISC-CO-LAM01 Cost Center | Check Cost Center pada setiap server SAP (Cost Center Group dan Hierarchy) | Memastikan Cost Center Lami telah di Assign ke CC group | Done | 100% | 2024-11-08
| DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Memastikan activity type untuk Cost Center Laminator lenngkap | Done | 100% | 2024-11-11
W01 (11 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM02 Master Data GL Account | Get List of GL Account for New Production Line Laminator #2 & #3 | Mempersiapkan GL Account New Line Production | Done | 100% | 2024-11-11
| DISC-FI-LAM05 Renevue Account Determination | Determine GL account mapping related to sales transactions for New Production Line Laminator #2 & #3 | Mempersiapkan GL Account transaksi sales untuk New Line Production lengkap | Done | 100% | 2024-11-11
| DISC-FI-LAM06 Asset Class Specify Account Determination | Get Account determination asset for New Production Line Laminator #2 & #3 | Memastikan Account Determination Asset Laminating lengkap | Done | 100% | 2024-11-11
Haikal, Yuki | DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Memastikan Activity type untuk cost center laminator tersedia | Done | 100% | 2024-11-13
| DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Memastikan Profir center Laminating tersedia di semua server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List konfigurasi new line production laminator lengkap | In Progress | 25% | 2024-11-15
W01 (12 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM07 Asset Number Ranges | Get Number range for New Production Line Laminator #2 & #3 | Memastikan Number range asset Laminator tersedia | Done | 100% | 2024-11-12
| DISC-FI-LAM08 Define Asset Class | Get asset class list for New Production Line Laminator #2 & #3 | Memastikan asset class Laminator tersedia | Done | 100% | 2024-11-12
Haikal | DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List konfigurasi new line production laminator lengkap | In Progress | 25% | 2024-11-15
W01 (13 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM09 Asset Account Assignment Acquisitions | Determine GL account related to fix asset transactions for New Production Line Laminator #2 & #3 | Memastikan mapping GL account per depreciation area Laminator 2 & 3 tersedia | Done | 100% | 2024-11-13
Munah | DISC-FI-LAM10 Assign Asset Class to Depreciation Area | Define depreciation key (Depreciation method, Depreciation are, and useful life) for New Production Line Laminator #2 & #3 | Memastikan depreciation key Laminator 2 & 3 tersedia | Done | 100% | 2024-11-13
Haikal | DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List konfigurasi new line production laminator lengkap | In Progress | 25% | 2024-11-15
W01 (14 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM11 Acct Determination For Exch.Rate Differences | Check configuration Exchange rate difference | Memastikan GL yang digunakan laminator 2 & 3 tersedia di konfigurasi account determination | Done | 100% | 2024-11-14
Munah | DISC-FI-LAM12 Assign GL to Financial Statement Version | Check mapping GL Account of the financian statement version | Memastikan GL account yang digunakan laminator termasuk ke dalam range FS statement | In Progress | 50% | 2024-11-14
Haikal | DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List konfigurasi new line production laminator lengkap | In Progress | 25% | 2024-11-15
W01 (15 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM12 Assign GL to Financial Statement Version | Check mapping GL Account of the financian statement version | Memastikan GL account yang digunakan laminator termasuk ke dalam range FS statement | Done | 100% | 2024-11-15
Haikal, Yuki | DISC-CO-LAM04 Relation between production lne code, cost center, and reporting | Discovery Relation between production line code, cost center, and reporting Laminator #2 #3 | Memastikan relasi cost center sampai reporting telah dimaintain | In Progress | 25% | 2024-11-15
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List konfigurasi new line production laminator lengkap | In Progress | 50% | 2024-11-15
W02 (18 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI | Accounting Document Testing sesuai dengan referensi di PRD | Planned | 0% | 2024-11-18
Haikal, Yuki | DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | List konfigurasi new line production laminator lengkap | In Progress | 100% | 2024-11-15
W02 (12 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Yuki,Haikal | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI Cycle 1 | Accounting Document Testing sesuai dengan referensi di PRD | In Progress | 25% | 2024-12-12
|  |  |  | Planned | 0% | 2024-12-12
W02 (13 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Yuki,Haikal | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI Cycle 1 | Accounting Document Testing sesuai dengan referensi di PRD | In Progress | 50% | 2024-12-13
|  |  |  | Planned | 0% | 2024-12-13
W02 (16 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Yuki,Haikal | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI Cycle 1 | Accounting Document Testing sesuai dengan referensi di PRD | In Progress | 50% | 2024-12-16
Munah,Yuki,Haikal | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI Cycle 2 | Accounting Document Testing sesuai dengan referensi di PRD | In Progress | 15% | 2024-12-16
W02 (17 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Yuki,Haikal | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI Cycle 1 | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100% | 2024-12-17
Munah,Yuki,Haikal | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI Cycle 2 (9 A,B,C) | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100% | 2024-12-17
W02 (18 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Haikal | DISC-FI-LAM14 Subcont CKI | Collect integration testing document subcont CKI Cycle 2 (4A) | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100% | 2024-12-18
Munah,Yuki | DISC-FI-LAM14 Subcont CKI | Menyiapkan material master data Testing (price change dan costing) | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100% | 2024-12-18
W02 (19 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Haikal | DISC-FI-LAM14 Subcont CKI | Cek & collect integration testing document subcont CKI Cycle 2 (1 A&B, 2 A&C, 4B, 5 A&B, 6 A&B) | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100% | 2024-12-20
W02 (20 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Haikal | DISC-FI-LAM14 Subcont CKI | Cek & collect integration testing document subcont CKI Cycle 2 (1 A&B, 2 A&C, 4B, 5 A&B, 6 A&B) | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100% | 2024-12-20
Yuki | DISC-FI-LAM14 Subcont CKI | Menyiapkan material master data Testing (price change dan costing) | Material untuk Testing telah termaintain cost | Done | 100% | 2024-12-20
Munah,Haikal | DISC-FI-LAM14 Subcont CKI | Cek & collect integration testing document subcont CKI Cycle 2 (7 A,B,C & 8 A,B) | Accounting Document Testing sesuai dengan referensi di PRD | In Progress | 25% | 2024-12-20
W02 (23 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Haikal | DISC-FI-LAM14 Subcont CKI | Cek & collect integration testing document subcont CKI Cycle 2 (7 A,B,C & 8 A,B) | Accounting Document Testing sesuai dengan referensi di PRD | In Progress | 75% | 2024-12-23
Munah,Haikal,Yuki | DISC-FI-LAM14 Subcont CKI | Cek Amount Testing (memastikan bahwa cost usd/kg dan idr/kg material testing telah sesuai) - Setting Cost S2/S3 -> std Cost - Setting Cost V2 -> Actual Cost | Cost material testing sesuai | Done | 100% | 2024-12-23
Munah,Haikal,Yuki | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | Planned | 0% | 2024-12-23
W02 (23 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Haikal,Yuki | DISC-FI-LAM14 Subcont CKI | Cek & collect integration testing document subcont CKI Cycle 2 (8 A,B) | Accounting Document Testing sesuai dengan referensi di PRD | In Progress | 75% | 2024-12-24
Munah,Haikal,Yuki | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | Planned | 0% | 2024-12-24
W02 (24 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah,Haikal,Yuki | DISC-FI-LAM14 Subcont CKI | Cek & collect integration testing document subcont CKI Cycle 2 (8 A,B) | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100% | 2024-12-24
Munah,Haikal,Yuki | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | Planned | 0% | 2024-12-24
W02 (26 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | In Progress | 75% | 2024-12-26
Munah | DISC-FI-LAM14 Subcont CKI | Discovery hasil review testing | Pertanyaan review testing dapat penuhi | In Progress | 50% | 2024-12-26
W02 (27 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Discovery hasil review testing | Pertanyaan review testing dapat penuhi | In Progress | 75% | 2024-12-27
Munah | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | In Progress | 75% | 2024-12-27
Munah |  | List business blueprint design FICO | List BP design modul FICO lengkap | Done | 100% | 2024-12-27
W02 (30 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Discovery hasil review testing | Pertanyaan review testing dapat penuhi | In Progress | 75%
Munah | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | In Progress | 75%
Munah | BP - FIAA01. Asset Sales and Lease Back | Mengupdate BP Asset Sales and Lease Back | BP Asset Sales and Lease Back terupdate | Done | 100%
W02 (06 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Discovery hasil review testing | Pertanyaan review testing dapat penuhi | In Progress | 75%
Munah | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | In Progress | 75%
Munah | DISC-FI-LAM14 Subcont CKI | Menyiapkan material master data Testing (price change dan costing) | Master data testing tersedia dan termaintain cost | Done | 100%
Munah | BP - FIMD04. Asset Master Data Maintenance | Mengupdate BP Asset Master Data Maintenance | BP Asset Master Data Maintenance terupdate | Done | 100%
Munah | BP - FIAA02. Asset Transfer | Mengupdate BP Asset Transfer | BP Asset Transfer terupdate | Done | 100%
Munah | BP - FIAA03. Asset Retirement | Mengupdate BP Asset Retirement | BP Asset Retirement terupdate | Done | 100%
W02 (07 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Discovery hasil review testing | Pertanyaan review testing dapat penuhi | Done | 100%
Munah | DISC-FI-LAM14 Subcont CKI | Presentasi hasil testing Cycle 2 | Hasil collect accounting document di riview oleh leader | Done | 100%
Munah |  | Konfigurasi Valuation Class di DEV NC | Konfigurasi valuation class laminating di DEV NC tersedia | Done | 100%
Munah | BP - FIAA04. Settlement AUC | Mengupdate BP Settlement AUC | BP Settlement AUC terupdate | Done | 100%
Munah | BP - FIAA05. Delta Depreciation Area for Parallel Asset Valuation | Mengupdate BP Delta Depreciation Area for Parallel Asset Valuation | BP Delta Depreciation Area for Parallel Asset Valuation terupdate | Done | 100%
W02 (08 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | BP - CO Master Data | Mengupdate BP Master Data | BP Master Data terupdate | Done | 100%
Munah | BP - COMD01-06 Master Data Maintenance | Cek BP Master Data Maintenance | Memastikan BP Master Data Maintenance sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
Munah | BP - COOM01 Plan Rate Calculation | Cek BP Plan Rate Calculation | Memastikan BP Plant Rate Calculation sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
W02 (09 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | BP - COOM02 Create Actual Distribution Cycle | Cek BP Create Actual Distribution Cycle | Memastikan BP Create Actual Distribution Cycle sesuai dengan environment pembahan laminator 2 & 3 | In Progress | 50%
Munah | BP - COOM03 Create Actual Assessment Cycle | Mengupdate BP Create Actual Assessment Cycle | BP Create Actual Assessment Cycle terupdate | Done | 100%
Munah | BP - COCL01 Period End Closing | Cek BP Period End Closing | Memastikan BP Pleriod end closing sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
W02 (10 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | BP - COOM02 Create Actual Distribution Cycle | Cek BP Create Actual Distribution Cycle | Memastikan BP Create Actual Distribution Cycle sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
Munah | BP - COPL01 Planning Profit Center | Cek BP Planning Profit Center | Memastikan BP Plan profit center sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
Munah | BP - COPC01 Standard Cost Estimate | Cek BP Standard Cost Estimate | Memastikan BP Standard cost estimate sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
W02 (13 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | BP - COPC02 Raw Rec and Recycle Price Change | Cek BP Raw Rec and Recycle Price Change | Memastikan BP Raw Rec and Recycle Price Change sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
Munah | BP - COPA01 Create Actual COPA Assessment Cycle | Cek BP Create Actual COPA Assessment Cycle | Memastikan BP Create actual COPA assessment cycle sesuai dengan environment pembahan laminator 2 & 3 | Done | 100%
Munah | DISC-FI-LAM14 Subcont CKI | Discovery DO Disposal for Recycle | Mendapatkan referensi DO Disposal di PRD | In Progress | 50%
W02 (14 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Discovery DO Disposal for Recycle | Mendapatkan referensi DO Disposal di PRD | Done | 100%
Munah | DISC-FI-LAM14 Subcont CKI | Collect Accounting Document Testing 11 A&B, 12 A&B | Accounting Document Testing sesuai dengan referensi di PRD | Done | 100%
Munah |  |  |  | Planned | 0%
W02 (04 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Closing Scenario Testing | Step closing testing selesai | Done | 100%
Munah, Fila | DISC-FI-LAM14 Subcont CKI | Create PNL dan COPA | PNL dan COPA Testing ulang selesai | Done | 100%
W02 (20 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Compare Table DEV130 | Tabel yang berubah sesuai design konfig | Done | 100%
Munah, Fila | DISC-FI-LAM14 Subcont CKI | Closing Scenario Testing (NC) | Step closing testing ulang selesai | In Progress | 10%
Munah | DISC-FI-LAM14 Subcont CKI | Collect Doc Testing untuk PPT konfirmasi Accounting | Collect Accounting Doc selesai | In Progress | 10%
W02 (21 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Testing ulang Sc 9 & 10 | Testing ulang Sc 9 & 10 selesai | Done | 100% | 2025-02-21
Munah, Fila | DISC-FI-LAM14 Subcont CKI | Closing Scenario Testing (NC) | Step closing testing ulang selesai | In Progress | 10% | 2025-02-21
Munah, Fila | DISC-FI-LAM14 Subcont CKI | Collect Doc Testing untuk PPT konfirmasi Accounting | Collect Accounting Doc selesai | In Progress | 10% | 2025-02-22
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | Planned | 0% | 2025-02-22
Munah |  | Costing Material DEV130 | Cost material terupdate sesuai PRD | Planned | 0% | 2025-02-22
Munah, Fila |  | Update PPT Konfirmasi | PPT Konfirmasi ke Accounting dan Tax selesai | Planned | 0% | 2025-02-22
W02 (24 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah | DISC-FI-LAM14 Subcont CKI | Testing ulang Sc 9 & 10 | Testing ulang Sc 9 & 10 selesai | Done | 100% | 2025-02-21
Munah, Fila | DISC-FI-LAM14 Subcont CKI | Closing Scenario Testing (NC) | Step closing testing ulang selesai | Done | 100% | 2025-02-21
Munah, Fila | DISC-FI-LAM14 Subcont CKI | Collect Doc Testing untuk PPT konfirmasi Accounting | Collect Accounting Doc selesai | In Progress | 50% | 2025-02-21
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 25% | 2025-02-24
Munah |  | Costing Material DEV130 | Cost material terupdate sesuai PRD | Done | 100% | 2025-02-21
Munah, Fila |  | Update PPT Konfirmasi | PPT Konfirmasi ke Accounting dan Tax selesai | In Progress | 75% | 2025-02-24
W02 (25 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | Collect Doc Testing untuk PPT konfirmasi Accounting | Collect Accounting Doc selesai | Done | 100% | 2025-02-21
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila |  | Update PPT Konfirmasi | PPT Konfirmasi ke Accounting dan Tax selesai | Done | 100% | 2025-02-24
Munah, Fila |  | Presentasi PPT Konfirmasi ke Accounting & Tax | Konfirmasi Bisnis proses dan pencatatan selesai | Done | 100% | 2025-02-24
W02 (26 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah |  | MoM Meeting konfirmasi PPT | MoM hasil meeting konfirmasi selesai | Done | 100% | 2025-02-26
W02 (27 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
W02 (28 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
W02 (28 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
W02 (03 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
W02 (04 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah | Integration Testing | Costing material testing kupas dan timbang | Cost material DEV 130 terupdate di bulan maret 2025 | Done | 100% | 2025-03-04
Munah | Integration Testing | Closing Activity Testing DEV 130 | Scenario Closing dapat dijalankan di server DEV 130 | Done | 100% | 2025-03-04
W02 (04 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah | Integration Testing | Costing material testing kupas dan timbang | Cost material DEV 130 terupdate di bulan maret 2025 | Done | 100% | 2025-03-04
Munah | Integration Testing | Closing Activity Testing DEV 130 | Scenario Closing dapat dijalankan di server DEV 130 | Done | 100% | 2025-03-04
W02 (05 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah | Integration Testing | Costing material testing kupas dan timbang | Cost material DEV 130 terupdate di bulan maret 2025 | Done | 100% | 2025-03-04
Munah | Integration Testing | Closing Activity Testing DEV 130 | Scenario Closing dapat dijalankan di server DEV 130 | Done | 100% | 2025-03-04
W02 (06 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah | Integration Testing | Costing material testing kupas dan timbang | Cost material DEV 130 terupdate di bulan maret 2025 | Done | 100% | 2025-03-04
Munah | Integration Testing | Closing Activity Testing DEV 130 | Scenario Closing dapat dijalankan di server DEV 130 | Done | 100% | 2025-03-04
W02 (07 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
W02 (10 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 25% | 2025-02-24
Munah | Integration Testing | Costing material testing kupas dan timbang | Cost material DEV 130 terupdate di bulan maret 2025 | Done | 100% | 2025-03-10
W02 (11 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 50% | 2025-02-24
Munah, Fila | Scenario Testing | Scenario Testing FICO DEV 130 dapat dijalankan di server DEV 130 | Scenario Testing FICO DEV 130 sesuai | In Progress | 20% | 2025-03-18
W02 (12 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 75% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 75% | 2025-02-24
Munah, Fila | Scenario Testing | Scenario Testing FICO DEV 130 dapat dijalankan di server DEV 130 | Scenario Testing FICO DEV 130 sesuai | In Progress | 20% | 2025-03-18
W02 (13 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | In Progress | 75% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | In Progress | 75% | 2025-02-24
Munah, Fila | Scenario Testing | Scenario Testing FICO DEV 130 dapat dijalankan di server DEV 130 | Scenario Testing FICO DEV 130 sesuai | In Progress | 20% | 2025-03-18
W02 (14 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | DISC-CO-LAM00 Konfigurasi CO | List konfigurasi CO sesuai terupdate | List konfigurasi CO terupdate sesuai hasil konfirmasi | Done | 100% | 2025-02-24
Munah, Fila | DISC-FI-LAM01 FI Configuration List | List konfigurasi FI sesuai terupdate | List konfigurasi FI terupdate sesuai hasil konfirmasi | Done | 100% | 2025-02-24
Munah, Fila | Scenario Testing | Scenario Testing FICO DEV 130 dapat dijalankan di server DEV 130 | Scenario Testing FICO DEV 130 sesuai | In Progress | 35% | 2025-03-18
W02 (17 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Munah, Fila | DISC-FI-LAM14 Subcont CKI | PNL dan COPA Testing Ulang | PNL dan COPA Testing ulang selesai | In Progress | 50% | 2025-02-24
Munah, Fila | Scenario Testing | Scenario Testing FICO DEV 130 dapat dijalankan di server DEV 130 | Scenario Testing FICO DEV 130 sesuai | In Progress | 35% | 2025-03-18
Munah | EUT | PPT EUT untuk Accounting | PPT untuk EUT Accounting selesai | In Progress | 50% | 2025-03-18

## OLAP & Meeting Pagi (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Complete list of Excel file and Data Source OLAP | Complete list of Excel file and Data Source OLAP | Done | 100%
|  |  |  | Done | 100%
W01 (08 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Complete list of Excel file and Data Source OLAP | Complete list of Excel file and Data Source OLAP | Done | 100%
|  |  |  | Done | 100%
W01 (11 November 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM01 Meeting Pagi - List of Table, View, and SP | Complete List of table and view Meeting Pagi | Complete List of table and view Meeting Pagi | Done | 50%
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Discovery OLAP 2024 - OLAP Excel File List and Data Source | Complete Discovery OLAP 2024 - OLAP Excel File List and Data Source | In Progress | 25%
W05 (17 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM01 Meeting Pagi - List of Table, View, and SP | Complete List of table Meeting Pagi | Complete List of table Meeting Pagi | In Progress | 75%
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Discovery OLAP 2024 - OLAP Excel File List and Data Source | Complete Discovery OLAP 2024 - OLAP Excel File List and Data Source | In Progress | 25%
W05 (18 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM01 Meeting Pagi - List of Table, View, and SP | Complete List of table Meeting Pagi | Complete List of table Meeting Pagi | Done | 100%
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Discovery OLAP 2024 - OLAP Excel File List and Data Source | Complete Discovery OLAP 2024 - OLAP Excel File List and Data Source | In Progress | 50%
W05 (19 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Discovery OLAP 2024 - OLAP Excel File List and Data Source | Complete Discovery OLAP 2024 - OLAP Excel File List and Data Source | In Progress | 50%
W05 (20 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Discovery OLAP 2024 - OLAP Excel File List and Data Source | Complete Discovery OLAP 2024 - OLAP Excel File List and Data Source | In Progress | 50%
Taufiq, Malak | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Discovery data interfacing SAP and OLAP | Complete Discovery data interfacing SAP and OLAP | In Progress | 25%
W06 (23 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Adit, Taufiq | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Complete the list of OLAP Excel File List and Data Source which will be enhanced | Complete the list of OLAP Excel File List and Data Source which will be enhanced | In Progress | 50%
Adit, Taufiq | DISC-NONSAPOLAP-LAM04 OLAP 2024 - Data Interface List | Complete the list of data interfacing SAP and OLAP which will be enhanced | Complete the list of data interfacing SAP and OLAP which will be enhanced | In Progress | 50%
W06 (24 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Adit, Taufiq | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Complete the list of OLAP Excel File List and Data Source which will be enhanced | Complete the list of OLAP Excel File List and Data Source which will be enhanced | In Progress | 50%
Adit, Taufiq | DISC-NONSAPOLAP-LAM04 OLAP 2024 - Data Interface List | Complete the list of data interfacing SAP and OLAP which will be enhanced | Complete the list of data interfacing SAP and OLAP which will be enhanced | In Progress | 75%
W08 (26 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Adit, Malak | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Complete the list of OLAP Excel File List and Data Source which will be enhanced | Complete the list of OLAP Excel File List and Data Source which will be enhanced | In Progress | 50%
Malak | DISC-NONSAPOLAP-LAM04 OLAP 2024 - Data Interface List | Review the list of data interfacing SAP and OLAP which will be enhanced | Complete Review the list of data interfacing SAP and OLAP which will be enhanced | In Progress | 75%
W08 (27 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Review the list of OLAP Excel File List and Data Source which will be enhanced | Complete Review the list of OLAP Excel File List and Data Source which will be enhanced | In Progress | 75%
Malak | DISC-NONSAPOLAP-LAM04 OLAP 2024 - Data Interface List | Review the list of data interfacing SAP and OLAP which will be enhanced | Complete Review the list of data interfacing SAP and OLAP which will be enhanced | In Progress | 75%
W09 (30 Desember 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Review the list of OLAP Excel File List and Data Source which will be enhanced | Review the list of OLAP Excel File List and Data Source which will be enhanced | In Progress | 75%
Malak | DISC-NONSAPOLAP-LAM04 OLAP 2024 - Data Interface List | Review the list of data interfacing SAP and OLAP which will be enhanced | Review the list of data interfacing SAP and OLAP which will be enhanced | In Progress | 75%
W09 (3 Januari 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | Review the list of OLAP Excel File List and Data Source which will be enhanced | Review the list of OLAP Excel File List and Data Source which will be enhanced | Done | 100%
Malak | DISC-NONSAPOLAP-LAM04 OLAP 2024 - Data Interface List | Review the list of data interfacing SAP and OLAP which will be enhanced | Review the list of data interfacing SAP and OLAP which will be enhanced | Done | 100%
W09 (14 Januari 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit, Debie, Ana | Confirm Master Data of Meeting Pagi to functional team | Completed confirmation | Completed confirmation | Done | 100%
Malak, Adit | DISC-NONSAPOLAP-LAM05 - Update Master Data Meeting Pagi | Completed update master data Meeting Pagi DEV | Completed update master data Meeting Pagi DEV | Done | 100%
Malak, Adit | DISC-NONSAPOLAP-LAM06 - Update View, and SP Meeting Pagi | Completed Update View and SP Meeting Pagi DEV | Completed Update View and SP Meeting Pagi DEV | Done | 100%
W10 (22 Januari 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit, Wahyu | Confirm Master Data of OLAP to functional team | Completed confirmation | Completed confirmation | In Progress | 50%
Malak, Adit | OLAP Excel File List and Data Source | Review the list of OLAP Excel File List and Data Source which will be enhanced | Review the list of OLAP Excel File List and Data Source which will be enhanced | In Progress | 50%
W10 (23 Januari 2024)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit, Wahyu | Confirm Master Data of OLAP to functional team | Completed confirmation | Completed confirmation | Done | 100%
Malak, Adit | OLAP Excel File List and Data Source | Review the list of OLAP Excel File List and Data Source which will be enhanced | Review the list of OLAP Excel File List and Data Source which will be enhanced | Done | 100%
W11 (30 Januari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit | WRICEF-OLAP-LAM01 | Deploy object BA999 to BA130 and BA320 | Deploy object BA999 to BA130 and BA320 | Done | 100%
W11 (3 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit | WRICEF-OLAP-LAM01 | Deploy object BI_DW to BI_DW_DEV | Deploy object BA999 to BA130 and BA320 | Done | 100%
W11 (17 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit | WRICEF-Meeting Pagi-LAM01 Insert Master Data Line | Complete Insert Master Data Line | Add new mater data | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM02 Insert Master Data LineRecycle (MeetingPagi) | Complete Insert Master Data LineRecycle (MeetingPagi) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM03 Insert Master Data SAPLine (MeetingPagi) | Complete Insert Master Data SAPLine (MeetingPagi) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM04 Insert Master Data SAPLine (BI_DW) | Complete Insert Master Data SAPLine (BI_DW) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM05 Insert Master Data GASTON | Complete Insert Master Data GASTON | Add new mater data | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM06 Insert Master Data KWHTON | Complete Insert Master Data KWHTON | Add new mater data | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM07 Insert Master Data WTRTON | Complete Insert Master Data WTRTON | Add new mater data | Done | 100%
W11 (18 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit | WRICEF-Meeting Pagi-LAM08 Alter Stored Procedure ProsesJR (MeetingPagi) | Complete update Stored Procedure ProsesJR (MeetingPagi) | Updated stored procedure | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM09 Alter Stored Procedure ProsesRecalJR (MeetingPagi) | Complete update Stored Procedure ProsesRecalJR (MeetingPagi) | Updated stored procedure | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM10 Alter Stored Procedure ProsesRecalSR1 (MeetingPagi) | Complete update Stored Procedure ProsesRecalSR1 (MeetingPagi) | Updated stored procedure | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM11 Alter Stored Procedure ProsesRecalSR2 (MeetingPagi) | Complete update Stored Procedure ProsesRecalSR2 (MeetingPagi) | Updated stored procedure | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM12 Alter Stored Procedure ProsesRecalSrc (MeetingPagi) | Complete update Stored Procedure ProsesRecalSrc (MeetingPagi) | Updated stored procedure | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM13 Alter Stored Procedure ProsesSrc (MeetingPagi) | Complete update Stored Procedure ProsesSrc (MeetingPagi) | Updated stored procedure | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM14 Alter Stored Procedure ProsesSR1st (MeetingPagi) | Complete update Stored Procedure ProsesSR1st (MeetingPagi) | Updated stored procedure | Done | 100%
Malak, Adit | WRICEF-Meeting Pagi-LAM15 Alter Stored Procedure ProsesSR2nd (MeetingPagi) | Complete update Stored Procedure ProsesSR2nd (MeetingPagi) | Updated stored procedure | Done | 100%
W12 (19 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit | WRICEF-OLAP-LAM01 Insert Master Data ZOLAP_PRODLINE (BA999) | Insert Master Data ZOLAP_PRODLINE (BA999) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-OLAP-LAM02 Insert Master Data T023 (BA999) | Insert Master Data T023 (BA999) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-OLAP-LAM03 Insert Master Data ZDIM_LINE (BA999) | Insert Master Data ZDIM_LINE (BA999) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-OLAP-LAM04 Insert Master Data T001L (BA999) | Insert Master Data T001L (BA999) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-OLAP-LAM05 Insert Master Data TVLKT (BA999) | Insert Master Data TVLKT (BA999) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-OLAP-LAM06 Insert Master Data T003O (BA999) | Insert Master Data T003O (BA999) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-OLAP-LAM07 Insert Master Data TVAK (BA999) | Insert Master Data TVAK (BA999) | Add new mater data | Done | 100%
Malak, Adit | WRICEF-OLAP-LAM08 Insert Master Data T0023T (B)I_DW | Insert Master Data T0023T (B)I_DW | Add new mater data | Done | 100%
W12 (20 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Create Cube Dev for Report OLAP Sales | Cube Dev for Report OLAP Sales has been created | Done | 100% | 2025-02-19
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Tested Cube Dev fot Report OLAP Sales | Cube Dev for Report OLAP Sales has been tested | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Create file excel OLAP2025 ST -TS | File excel OLAP2025 ST - TS | Done | 100%
W12 (21 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 CNV PROD - TS | Create File OLAP2025 CNV PROD - TS | Create File OLAP2025 CNV PROD - TS | Done | 100%
Malak | WRICEF-OLAP-LAM24 Create File OLAP2025 LAI - TS | Create File OLAP2025 LAI - TS | Create File OLAP2025 LAI - TS | Done | 100%
W12 (24 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak, Adit | DISC-NONSAPOLAP-LAM05 - Update Master Data OLAP | Completed update master data OLAP DEV | Completed update master data OLAP DEV | Done | 100%
Malak, Adit | DISC-NONSAPOLAP-LAM06 - Update View, and SP OLAP | Completed Update View and SP OLAP DEV | Completed Update View and SP OLAP DEV | Done | 100%
W12 (25 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-DBCO-LAM01 Add New Parameter-ZOLAPPRD RC MALAM | Add Parameter on Job ZOLAPPRD RC MALAM - Program ZFICO_PRCINV_VALUES - Variant BA_RC_PRD on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM02 Add New Parameter-ZOLAPPRD RC PAGI | Add Parameter on Job ZOLAPPRD RC PAGI - Program ZFICO_PRCINV_VALUES - Variant BA_RC_PRD on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM03 Add New Parameter-ZOLAPPRD RC SIANG | Add Parameter on Job ZOLAPPRD RC SIANG - Program ZFICO_PRCINV_VALUES - Variant BA_RC_PRD on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM04 Add New Parameter-ZOLAPPRD RC SORE | Add Parameter on Job ZOLAPPRD RC SORE - Program ZFICO_PRCINV_VALUES - Variant BA_RC_PRD on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM05 Add New Parameter-ZOLAPPRD ZCOMAT | Add Parameter on Job ZOLAPPRD ZCOMAT - Program ZFICO_PRCINV_VALUES - Variant BA_RC_PRD on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM06 Add New Parameter-UX_STOCK_BY_CHAR_DAILY | Add Parameter on Job UX_STOCK_BY_CHAR_DAILY - Program ZTBAP_STOCK_BY_CHAR1 - Variant BG_JOB on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM10 Add New Parameter-UX_REKAP_SLITTING_DAILY-1 | Add Parameter on Job UX_REKAP_SLITTING_DAILY-1 - Program ZTPPR_SLITTING_REKAP_PC_V2 - Variant BG_JOB_DAILY-1 on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM11 Add New Parameter-UX_INSP_LOT_LAMSCRIM_DAILY | Add Parameter on Job UX_INSP_LOT_LAMSCRIM_DAILY - Program ZTQM_INSP_LOT - Variant BG_JOB_LS on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM12 Add New Parameter-UX_INSP_LOT_LAMSCRIM_DAILY-1 | Add Parameter on Job UX_INSP_LOT_LAMSCRIM_DAILY-1 - Program ZTQM_INSP_LOT - Variant BG_JOB_LS-1 on Server DEV | Add new parameter | In Progress | 75%
W12 (26 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-OLAP-LAM09 Enhancement SAP Program-ZOLAPSLS | Testing Enhancement SAP Program ZOLAP_SALES_DETAIL | Enhancement SAP Program ZOLAP_SALES_DETAIL has been tested | In Progress | 50%
Malak | WRICEF-OLAP-LAM10 Enhancement SAP Program-ZOLAP_SALES_DETAIL | Testing Enhancement SAP Program ZOLAPSLS | Enhancement SAP Program ZOLAPSLS has been tested | In Progress | 50%
Malak | WRICEF-OLAP-LAM11 Enhancement SAP Program-ZOLAP_SALES_DETAIL_IT | Testing Enhancement SAP Program ZOLAP_SALES_DETAIL_IT | Enhancement SAP Program ZOLAPSLS has been tested | In Progress | 50%
W12 (27 Februari 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-DBCO-LAM13 Add New Parameter-UX_STOCK_REC_DAILY | Add Parameter on Job UX_STOCK_REC_DAILY - Program ZTMMR_STOCK_RM - Variant BG_JOB_REC on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM16 Add New Parameter-REKAP_SLITTING_HARIAN | Add Parameter on Job REKAP_SLITTING_HARIAN - Program ZPPR_SLITTING_REKAP_DAILY - Variant OLAPSELECTION on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM17 Add New Parameter-ZPP011 & ZPP016 06:00 | Add Parameter on Job ZPP011 & ZPP016 06:00 - Program ZPPR_SLITTING_REKAP_DAILY - Variant OLAPSELECTION on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM18 Add New Parameter-ZPP011 & ZPP016 14:30 | Add Parameter on Job ZPP011 & ZPP016 14:30 - Program ZPPR_SLITTING_REKAP_DAILY - Variant OLAPSELECTION on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM19 Add New Parameter-ZPP011 & ZPP016 22:30 | Add Parameter on Job ZPP011 & ZPP016 22:30 - Program ZPPR_SLITTING_REKAP_DAILY - Variant OLAPSELECTION on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM20 Add New Parameter-ZPP011 & ZPP016 NOW | Add Parameter on Job ZPP011 & ZPP016 NOW - Program ZPPR_SLITTING_REKAP_DAILY - Variant OLAPSELECTION on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM21 Add New Parameter-MP SR-SCRAP | Add Parameter on Job MP SR-SCRAP - Program ZPPR_SLITTING_REKAP_PC_CX - Variant OLAPSELECTION on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM22 Add New Parameter-MP SLIT ROLL | Add Parameter on Job MP SLIT ROLL - Program ZPPR_SLITTING_REKAP_PC_V2 - Variant OLAPSELECTION on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM24 Add New Parameter-R MP SLIT_ROLL_TODAY | Add Parameter on Job R MP SLIT_ROLL_TODAY - Program ZPPR_SLITTING_REKAP_PC_V2 - Variant OLAPSELECTION1 on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM29 Add New Parameter-ZOLAPPRD RC MALAM | Add Parameter on Job ZOLAPPRD RC MALAM - Program ZMMR_MTR_STOCK - Variant STOCK RC on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM30 Add New Parameter-ZOLAPPRD RC PAGI | Add Parameter on Job ZOLAPPRD RC PAGI - Program ZMMR_MTR_STOCK - Variant STOCK RC on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM31 Add New Parameter-ZOLAPPRD RC SIANG | Add Parameter on Job ZOLAPPRD RC SIANG - Program ZMMR_MTR_STOCK - Variant STOCK RC on Server DEV | Add new parameter | In Progress | 75%
Malak | WRICEF-DBCO-LAM32 Add New Parameter-ZOLAPPRD RC SORE | Add Parameter on Job ZOLAPPRD RC SORE - Program ZMMR_MTR_STOCK - Variant STOCK RC on Server DEV | Add new parameter | In Progress | 75%
W13 (5 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data ZPP011 for Testing on Report | Data ZPP011 for Report OLAP Sales has been downloaded | In Progress | 75%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data ZPP016 for Testing on Report | Data ZPP016 for Report OLAP Sales has been downloaded | In Progress | 75%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data ZOLAPPG for Testing on Report | Data ZOLAPPG for Report OLAP Sales has been downloaded | In Progress | 75%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Make Cube OLAP_MassBalance_2025_TS_DEV on Localhost for Testing Report | Cube Dev for Report OLAP Sales has been created | In Progress | 75%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Make Cube OLAP_OLAP_RCY_2025_TS_DEV on Localhost for Testing Report | Cube Dev for Report OLAP Sales has been created | In Progress | 75%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Make Cube OLAP_SALES_2025_TS_TS_DEV on Localhost for Testing Report | Cube Dev for Report OLAP Sales has been created | In Progress | 75%
W13 (7 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data BKPF, BSEG for Testing on Report | Data BKPF , BSEG for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MARA for Testing on Report | Data MARA for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLIT for Testing on Report | Data MLIT for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLHD for Testing on Report | Data MLHD for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLPP for Testing on Report | Data MLPP for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLCR for Testing on Report | Data MLCR for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKBE for Testing on Report | Data EKBE for Report OLAP Sales has been downloaded | In Progress
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKKO for Testing on Report | Data EKKO for Report OLAP Sales has been downloaded | In Progress
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKPO for Testing on Report | Data EKPO for Report OLAP Sales has been downloaded | In Progress
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKET for Testing on Report | Data EKET for Report OLAP Sales has been downloaded | In Progress
W14 (10 Maret 2025)
Team | Activity in WBS | Target | Deliverable | Status | Status (%) | Target (Date)
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data BKPF, BSEG for Testing on Report | Data BKPF , BSEG for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MARA for Testing on Report | Data MARA for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLIT for Testing on Report | Data MLIT for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLHD for Testing on Report | Data MLHD for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLPP for Testing on Report | Data MLPP for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLCR for Testing on Report | Data MLCR for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKBE for Testing on Report | Data EKBE for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKKO for Testing on Report | Data EKKO for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKPO for Testing on Report | Data EKPO for Report OLAP Sales has been downloaded | Done | 100%
Malak | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EKET for Testing on Report | Data EKET for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MSEG_2 for Testing on Report | Data MSEG_2 for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MAKT for Testing on Report | Data MAKT for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data EBAN for Testing on Report | Data EBAN for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data KONV for Testing on Report | Data KONV for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data MLCD for Testing on Report | Data MLCD for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data CKMLHD for Testing on Report | Data CKMLHD for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data CKMLCR for Testing on Report | Data CKMLCR for Report OLAP Sales has been downloaded | Done | 100%
Adit | WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | Download Data CKMLPP for Testing on Report | Data CKMLPP for Report OLAP Sales has been downloaded | Done | 100%

## UXTOOL (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Understand with end to end process of UX Tool Application | Understand with end to end process of UX Tool Application | Understand with end to end process of UX Tool Application Complete | In Progress | 0% | 2024-11-13
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | Planned | 0%
W01 (08 November 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Understand with end to end process of UX Tool Application | Understand with end to end process of UX Tool Application | Understand with end to end process of UX Tool Application Complete | In Progress | 0% | 2024-11-13
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | Planned | 0%
W01 (11 November 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Understand with end to end process of UX Tool Application | Understand with end to end process of UX Tool Application | Understand with end to end process of UX Tool Application Complete | In Progress | 50% | 2024-11-13
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | Planned | 0%
W01 (12 November 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL | Explore list change for UXTOOL | Explore list change for UXTOOL Complete | In Progress | 50% | 2024-11-13
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | Planned | 0%
W01 (12 November 2024)
Team | Activity in WBS | Target | Deliverables |  | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL Complete | In Progress | 50% | 2024-11-18
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | Planned | 0%
W05 (13 November 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL Complete | In Progress | 50% | 2024-11-18
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | Planned | 0%
W05 (13 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | In Progress | 50%
W05 (16 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM13 UXTOOL Discussion with SAP functional to validate data for new Line Lamintor | Complete validate data | Complete validate data | validate data Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Lamintor | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | Planned | 0%
W05 (17 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM13 UXTOOL Discussion with SAP functional to validate data for new Line Lamintor | Complete validate data | Complete validate data | validate data Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Lamintor | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | Planned | 0%
W05 (18 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM13 UXTOOL Discussion with SAP functional to validate data for new Line Lamintor | Complete validate data | Complete validate data | validate data Complete | Planned | 0%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Lamintor | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | Planned | 0%
W05 (19 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL & check list master data UX tool | Explore list change for UXTOOL Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM11 UXTOOL Review & Discovery impact of new Laminator | Complete list of Discovery Project Laminator #2 and #3 | Complete list of Discovery Project Laminator #2 and #3 | list of Discovery Project Laminator #2 and #3 Complete | Done | 100% | 2024-12-17
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM13 UXTOOL Discussion with SAP functional to validate data for new Line Laminator | Complete validate data | Complete validate data | validate data Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | In Progress | 50%
W05 (20 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM13 UXTOOL Discussion with SAP functional to validate data for new Line Laminator | Complete validate data | Complete validate data | validate data Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | In Progress | 50%
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W06 (23 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM12 UXTOOL Define change list & configuration UXTOOL for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | Complete changelist & UXTOOL configuration for new Line Laminator | changelist & UXTOOL configuration for new Line Laminator Complete | Done | 100%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM13 UXTOOL Discussion with SAP functional to validate data for new Line Laminator | Complete validate data | Complete validate data | validate data Complete | Done | 100%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | In Progress | 50%
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W06 (27 Desember 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM15 UXTOOL Validation and Mitigation of UXTool Data for New Laminator Line | Complete Validate and Mitigation of UXTool Data for New Laminator Line | Complete Validate and Mitigation of UXTool Data for New Laminator Line | Validate and Mitigation of UXTool Data for New Laminator Line Complete | In Progress | 50%
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W06 (5 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | In Progress | 50%
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM15 UXTOOL Validation and Mitigation of UXTool Data for New Laminator Line | Complete Validate and Mitigation of UXTool Data for New Laminator Line | Complete Validate and Mitigation of UXTool Data for New Laminator Line | Validate and Mitigation of UXTool Data for New Laminator Line Complete | Done | 50%
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W06 (6 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | In Progress | 50%
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W07 (13 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development |  | In Progress | 50%
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W07 (14 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete Update data in UXTOOL Development | Complete Update data in UXTOOL Development | Update data in UXTOOL Development Complete | In Progress | 50%
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W08 (23 Januari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator Complete | In Progress | 50% | 2025-01-28
Nafianta, Rasyid, Krisna | Checking Master Data base on Blueprint Confirmastion | Complete Checking Master Data base on Blueprint Confirmastion | Complete Checking Master Data base on Blueprint Confirmastion | Checking Master Data base on Blueprint Confirmastion Complete | In Progress | 50% | 2025-01-28
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W08 (28 Januari 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Nafianta, Rasyid, Krisna | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | Complete DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator | DISC-NONSAP-LAM14 UXTOOL Update data in UXTOOL Development for new Line Laminator Complete | Done | 100% | 2025-01-28
Nafianta, Rasyid, Krisna | Checking Master Data base on Blueprint Confirmastion | Complete Checking Master Data base on Blueprint Confirmastion | Complete Checking Master Data base on Blueprint Confirmastion | Checking Master Data base on Blueprint Confirmastion Complete | Done | 100% | 2025-01-28
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Ana, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W08 (30 Januari 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Krisna, Rafly, Mela, Aryo, Alif | Testing UXTOOL Server DEV new Line Laminator | Complete Testing in UXTOOL Development | Complete Testing in UXTOOL Development |  | Planned | 0% | 2025-02-25
Krisna | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode | Complete WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode |  | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data | Complete WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data |  | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 | Complete WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 |  | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM08 Master Data Role Define | Complete WRICEF-UXTOOL-LAM08 Master Data Role Define |  | WRICEF-UXTOOL-LAM08 Master Data Role Define Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM09 Master Data Role Users | Complete WRICEF-UXTOOL-LAM09 Master Data Role Users |  | WRICEF-UXTOOL-LAM09 Master Data Role Users Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD | Complete WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD |  | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME | Complete WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME |  | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 | Complete WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 |  | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR | Complete WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR |  | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC | Complete WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC |  | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR | Complete WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR |  | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE | Complete WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE |  | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM17 Master Data SYS_023 | Complete WRICEF-UXTOOL-LAM17 Master Data SYS_023 |  | WRICEF-UXTOOL-LAM17 Master Data SYS_023 Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME | Complete WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME |  | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM19 Master Data SYS_001L | Complete WRICEF-UXTOOL-LAM19 Master Data SYS_001L |  | WRICEF-UXTOOL-LAM19 Master Data SYS_001L Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM20 Master Data SYS_003O | Complete WRICEF-UXTOOL-LAM20 Master Data SYS_003O |  | WRICEF-UXTOOL-LAM20 Master Data SYS_003O Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR | Complete WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR |  | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE | Complete WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE |  | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU | Complete WRICEF-UXTOOL-LAM23 Master Data SYS_CORU |  | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM24 Master Data PackingStation | Complete WRICEF-UXTOOL-LAM24 Master Data PackingStation |  | WRICEF-UXTOOL-LAM24 Master Data PackingStation Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR | Complete WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR |  | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM26 Master Data RESOURCE | Complete WRICEF-UXTOOL-LAM26 Master Data RESOURCE |  | WRICEF-UXTOOL-LAM26 Master Data RESOURCE Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM27 Master Data HR0001 | Complete WRICEF-UXTOOL-LAM27 Master Data HR0001 |  | WRICEF-UXTOOL-LAM27 Master Data HR0001 Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM28 Master Data HR1001 | Complete WRICEF-UXTOOL-LAM28 Master Data HR1001 |  | WRICEF-UXTOOL-LAM28 Master Data HR1001 Complete | Planned | 0% | 2025-02-05
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Rafly, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W08 (3 Februari 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Krisna, Rafly, Mela, Aryo, Alif | Testing UXTOOL Server DEV new Line Laminator | Complete Testing in UXTOOL Development | Complete Testing in UXTOOL Development |  | In Progress | 25% | 2025-02-25
Krisna | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode | Complete WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode |  | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data | Complete WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data |  | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 | Complete WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 |  | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM08 Master Data Role Define | Complete WRICEF-UXTOOL-LAM08 Master Data Role Define |  | WRICEF-UXTOOL-LAM08 Master Data Role Define Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM09 Master Data Role Users | Complete WRICEF-UXTOOL-LAM09 Master Data Role Users |  | WRICEF-UXTOOL-LAM09 Master Data Role Users Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD | Complete WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD |  | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME | Complete WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME |  | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 | Complete WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 |  | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR | Complete WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR |  | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC | Complete WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC |  | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR | Complete WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR |  | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE | Complete WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE |  | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM17 Master Data SYS_023 | Complete WRICEF-UXTOOL-LAM17 Master Data SYS_023 |  | WRICEF-UXTOOL-LAM17 Master Data SYS_023 Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME | Complete WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME |  | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM19 Master Data SYS_001L | Complete WRICEF-UXTOOL-LAM19 Master Data SYS_001L |  | WRICEF-UXTOOL-LAM19 Master Data SYS_001L Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM20 Master Data SYS_003O | Complete WRICEF-UXTOOL-LAM20 Master Data SYS_003O |  | WRICEF-UXTOOL-LAM20 Master Data SYS_003O Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR | Complete WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR |  | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE | Complete WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE |  | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU | Complete WRICEF-UXTOOL-LAM23 Master Data SYS_CORU |  | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM24 Master Data PackingStation | Complete WRICEF-UXTOOL-LAM24 Master Data PackingStation |  | WRICEF-UXTOOL-LAM24 Master Data PackingStation Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR | Complete WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR |  | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM26 Master Data RESOURCE | Complete WRICEF-UXTOOL-LAM26 Master Data RESOURCE |  | WRICEF-UXTOOL-LAM26 Master Data RESOURCE Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM27 Master Data HR0001 | Complete WRICEF-UXTOOL-LAM27 Master Data HR0001 |  | WRICEF-UXTOOL-LAM27 Master Data HR0001 Complete | Planned | 0% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM28 Master Data HR1001 | Complete WRICEF-UXTOOL-LAM28 Master Data HR1001 |  | WRICEF-UXTOOL-LAM28 Master Data HR1001 Complete | Planned | 0% | 2025-02-05
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Rafly, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W08 (4 Februari 2024)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Krisna, Rafly, Mela, Aryo, Alif | Testing UXTOOL Server DEV new Line Laminator | Complete Testing in UXTOOL Development | Complete Testing in UXTOOL Development |  | In Progress | 50% | 2025-02-25
Krisna | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode | Complete WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode |  | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data | Complete WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data |  | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 | Complete WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 |  | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM08 Master Data Role Define | Complete WRICEF-UXTOOL-LAM08 Master Data Role Define |  | WRICEF-UXTOOL-LAM08 Master Data Role Define Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM09 Master Data Role Users | Complete WRICEF-UXTOOL-LAM09 Master Data Role Users |  | WRICEF-UXTOOL-LAM09 Master Data Role Users Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD | Complete WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD |  | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME | Complete WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME |  | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 | Complete WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 |  | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR | Complete WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR |  | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC | Complete WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC |  | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR | Complete WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR |  | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE | Complete WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE |  | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM17 Master Data SYS_023 | Complete WRICEF-UXTOOL-LAM17 Master Data SYS_023 |  | WRICEF-UXTOOL-LAM17 Master Data SYS_023 Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME | Complete WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME |  | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM19 Master Data SYS_001L | Complete WRICEF-UXTOOL-LAM19 Master Data SYS_001L |  | WRICEF-UXTOOL-LAM19 Master Data SYS_001L Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM20 Master Data SYS_003O | Complete WRICEF-UXTOOL-LAM20 Master Data SYS_003O |  | WRICEF-UXTOOL-LAM20 Master Data SYS_003O Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR | Complete WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR |  | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE | Complete WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE |  | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU | Complete WRICEF-UXTOOL-LAM23 Master Data SYS_CORU |  | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM24 Master Data PackingStation | Complete WRICEF-UXTOOL-LAM24 Master Data PackingStation |  | WRICEF-UXTOOL-LAM24 Master Data PackingStation Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR | Complete WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR |  | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM26 Master Data RESOURCE | Complete WRICEF-UXTOOL-LAM26 Master Data RESOURCE |  | WRICEF-UXTOOL-LAM26 Master Data RESOURCE Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM27 Master Data HR0001 | Complete WRICEF-UXTOOL-LAM27 Master Data HR0001 |  | WRICEF-UXTOOL-LAM27 Master Data HR0001 Complete | In Progress | 50% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM28 Master Data HR1001 | Complete WRICEF-UXTOOL-LAM28 Master Data HR1001 |  | WRICEF-UXTOOL-LAM28 Master Data HR1001 Complete | In Progress | 50% | 2025-02-05
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
Rafly, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | In Progress | 50% | 2025-02-20
W08 (20 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Krisna, Rafly, Mela, Aryo, Alif | Testing UXTOOL Server DEV new Line Laminator | Complete Testing in UXTOOL Development | Complete Testing in UXTOOL Development | Testing in UXTOOL Development Complete | In Progress | 50% | 2025-02-25
Krisna | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode | Complete WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode |  | WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data | Complete WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data |  | WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation | Complete WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation |  | WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 | Complete WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 |  | WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM08 Master Data Role Define | Complete WRICEF-UXTOOL-LAM08 Master Data Role Define |  | WRICEF-UXTOOL-LAM08 Master Data Role Define Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM09 Master Data Role Users | Complete WRICEF-UXTOOL-LAM09 Master Data Role Users |  | WRICEF-UXTOOL-LAM09 Master Data Role Users Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD | Complete WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD |  | WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME | Complete WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME |  | WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 | Complete WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 |  | WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR | Complete WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR |  | WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC | Complete WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC |  | WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR | Complete WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR |  | WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE | Complete WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE |  | WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM17 Master Data SYS_023 | Complete WRICEF-UXTOOL-LAM17 Master Data SYS_023 |  | WRICEF-UXTOOL-LAM17 Master Data SYS_023 Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME | Complete WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME |  | WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM19 Master Data SYS_001L | Complete WRICEF-UXTOOL-LAM19 Master Data SYS_001L |  | WRICEF-UXTOOL-LAM19 Master Data SYS_001L Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM20 Master Data SYS_003O | Complete WRICEF-UXTOOL-LAM20 Master Data SYS_003O |  | WRICEF-UXTOOL-LAM20 Master Data SYS_003O Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR | Complete WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR |  | WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE | Complete WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE |  | WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU | Complete WRICEF-UXTOOL-LAM23 Master Data SYS_CORU |  | WRICEF-UXTOOL-LAM23 Master Data SYS_CORU Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM24 Master Data PackingStation | Complete WRICEF-UXTOOL-LAM24 Master Data PackingStation |  | WRICEF-UXTOOL-LAM24 Master Data PackingStation Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR | Complete WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR |  | WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM26 Master Data RESOURCE | Complete WRICEF-UXTOOL-LAM26 Master Data RESOURCE |  | WRICEF-UXTOOL-LAM26 Master Data RESOURCE Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM27 Master Data HR0001 | Complete WRICEF-UXTOOL-LAM27 Master Data HR0001 |  | WRICEF-UXTOOL-LAM27 Master Data HR0001 Complete | Done | 100% | 2025-02-05
Krisna | WRICEF-UXTOOL-LAM28 Master Data HR1001 | Complete WRICEF-UXTOOL-LAM28 Master Data HR1001 |  | WRICEF-UXTOOL-LAM28 Master Data HR1001 Complete | Done | 100% | 2025-02-05
Debie, Alif, Yuli | Konfirmasi Master Data UXTOOL yang diprovide MM | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | Done | 100% | 2025-02-20
Rafly, Mela, Aryo | Konfirmasi Master Data UXTOOL yang diprovide PP | Complete Confirmation data | Complete Confirmation data | Confirmation Data Complete | Done | 100% | 2025-02-20
W08 (21 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverebles | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL |  | Complete Review Mater Data UXTOOL | Planned | 0% | 2025-02-24
Krisna, Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) |  | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) |  | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) |  | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) |  | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) |  | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) |  | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) |  | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) |  | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) |  | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) |  | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) |  | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) |  | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) |  | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) |  | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) |  | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) |  | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) |  | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) |  | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) |  | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) |  | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) |  | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) |  | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) |  | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) |  | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) |  | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 |  | ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 |  | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 |  | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 |  | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 |  | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 |  | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-02-28
Krisna, Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution |  | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-02-28
W08 (24 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL |  | Complete Review Mater Data UXTOOL | In Progress | 50% | 2025-03-05
Krisna, Rasyid, Nafi | Update Master Data ZUX_HOME | Complete Update Master Data ZUX_HOME |  | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) |  | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) |  | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) |  | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) |  | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) |  | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) |  | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) |  | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) |  | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) |  | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) |  | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) |  | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) |  | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) |  | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) |  | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) |  | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) |  | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) |  | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) |  | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) |  | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) |  | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) |  | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) |  | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) |  | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) |  | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) |  | ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 |  | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 |  | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 |  | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 |  | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 |  | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 |  | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution |  |  | Planned | 0% | 2025-03-05
W08 (25 Februari 20245
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL |  | Complete Review Mater Data UXTOOL | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) |  | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) |  | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) |  | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) |  | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) |  | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) |  | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | In Progress | 50% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) |  | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) |  | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) |  | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) |  | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) |  | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) |  | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) |  | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) |  | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) |  | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) |  | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) |  | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) |  | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) |  | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) |  | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) |  | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) |  | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) |  | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) |  | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) |  | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 |  | ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 |  | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 |  | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 |  | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 |  | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 |  | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-05
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution |  | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-05
W08 (26 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Reviewed Mater Data UXTOOL | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
2025-03-10
2025-03-10
W08 (27 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Reviewed Mater Data UXTOOL | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
W08 (28 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Reviewed Mater Data UXTOOL | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP041L2 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
2025-03-10
2025-03-10
W09 (03 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Reviewed Mater Data UXTOOL | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF01 COR1M Create PRO Mixing | Complete Testing MF01 COR1M Create PRO Mixing |  | Testing MF01 COR1M Create PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF02 COR2M Change PRO Mixing | Complete Testing MF02 COR2M Change PRO Mixing |  | Testing MF02 COR2M Change PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF06 COR6M Confirmation of Mixing | Complete Testing MF06 COR6M Confirmation of Mixing |  | Testing MF06 COR6M Confirmation of Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
W09 (04 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Reviewed Mater Data UXTOOL | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF01 COR1M Create PRO Mixing | Complete Testing MF01 COR1M Create PRO Mixing |  | Testing MF01 COR1M Create PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF02 COR2M Change PRO Mixing | Complete Testing MF02 COR2M Change PRO Mixing |  | Testing MF02 COR2M Change PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF06 COR6M Confirmation of Mixing | Complete Testing MF06 COR6M Confirmation of Mixing |  | Testing MF06 COR6M Confirmation of Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
Krisna, Nafi | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | In Progress | 50% | 2025-03-09
W09 (06 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Krisna, Rasyid, Nafi | Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Complete Review Mater Data UXTOOL | Reviewed Mater Data UXTOOL | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF01 COR1M Create PRO Mixing | Complete Testing MF01 COR1M Create PRO Mixing |  | Testing MF01 COR1M Create PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF02 COR2M Change PRO Mixing | Complete Testing MF02 COR2M Change PRO Mixing |  | Testing MF02 COR2M Change PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF06 COR6M Confirmation of Mixing | Complete Testing MF06 COR6M Confirmation of Mixing |  | Testing MF06 COR6M Confirmation of Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
Krisna, Nafi | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | In Progress | 50% | 2025-03-09
W09 (07 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF01 COR1M Create PRO Mixing | Complete Testing MF01 COR1M Create PRO Mixing |  | Testing MF01 COR1M Create PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF02 COR2M Change PRO Mixing | Complete Testing MF02 COR2M Change PRO Mixing |  | Testing MF02 COR2M Change PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF06 COR6M Confirmation of Mixing | Complete Testing MF06 COR6M Confirmation of Mixing |  | Testing MF06 COR6M Confirmation of Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
Krisna, Nafi | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | In Progress | 50% | 2025-03-09
W10 (12 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Rafly, Mela, Aryo, Alif | Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | Complete Testing X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) | X3ST116 Transfer Posting STS 313 R.Rec->Gdg (1155->1815) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | Complete Testing X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) | X3ST219 Transfer Posting STS 313 Rec -> Gdg (1161->1061) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | Complete Testing X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) | X3ST366 Transfer Posting STS 313 R.Rec -> R.Rec (1152->1155) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | Complete Testing X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) | X5ST121 Transfer Posting STS 315 Terima R.Rec/Rec (1155) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | Complete Testing XST814 Transfer Posting STS Stand->JR NA (L100->1L01) | XST814 Transfer Posting STS Stand->JR NA (L100->1L01) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | Complete Testing XST815 Transfer Posting STS Stand->JR NA (M100->1L02) | XST815 Transfer Posting STS Stand->JR NA (M100->1L02) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | Complete Testing XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) | XHRS109 Create Reservation Res HU Gdg->ReslitFG (1813->1307) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | Complete Testing XMRS042 Create Reservation Res RM->Feed (1815->1061) | XMRS042 Create Reservation Res RM->Feed (1815->1061) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | Complete Testing XMRS142 Create Reservation Res Feed->RM (1061->1815) | XMRS142 Create Reservation Res Feed->RM (1061->1815) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | Complete Testing XGI070 Goods Issue GI to Cleaning (LAM Line#2) | XGI070 Goods Issue GI to Cleaning (LAM Line#2) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | Complete Testing XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) | XGI071 Goods Issue Rev GI to Cleaning (LAM Line#2) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI072 Goods Issue GI to Cleaning (LAM Line#3) | XGI072 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | Complete Testing XGI073 Goods Issue GI to Cleaning (LAM Line#3) | XGI073 Goods Issue GI to Cleaning (LAM Line#3) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | Complete Testing XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) | XMRI246 Create Reservation Reserv Packing Mat (LAM-WR) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | Complete Testing XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) | XMRI247 Create Reservation Reserv Rev Packing Mat (LAM-WR) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | Complete Testing XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) | XMRI248 Create Reservation Reserv S/P (LAM Feeding WR) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | Complete Testing XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) | XMRI249 Create Reservation Reserv Rev S/P (LAM Feeding KR) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | Complete Testing XMRI250 Create Reservation Reserv S/P (LAM General WR) | XMRI250 Create Reservation Reserv S/P (LAM General WR) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | Complete Testing XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) | XMRI251 Create Reservation Reserv Rev S/P (LAM General KR) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | Complete Testing XMRI252 Create Reservation Reserv S/P (LAM Line#2) | XMRI252 Create Reservation Reserv S/P (LAM Line#2) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | Complete Testing XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) | XMRI253 Create Reservation Reserv Rev S/P (LAM Line#2) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | Complete Testing XMRI254 Create Reservation Reserv S/P (LAM Line#3) | XMRI254 Create Reservation Reserv S/P (LAM Line#3) Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | Complete Testing XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) | XMRI255 Create Reservation Reserv Rev S/P (LAM Line#3) Testing Complete | Done | 100% | 2025-03-10
Alif | Testing XST816 Transfer Posting STS U. Input LAM->FI LAM (1062->1L51) | Complete Testing XST816 Transfer Posting STS U. Input LAM->FI LAM (1062->1L51) |  | XST816 Transfer Posting STS U. Input LAM->FI LAM (1062->1L51) Complete | In Progress | 50% | 2025-03-10
Alif | Testing XHRS110 Transfer Posting Res HU Gdg->Input LAM-HU (1813->1063) | Complete Testing XHRS110 Transfer Posting Res HU Gdg->Input LAM-HU (1813->1063) |  | XHRS110 Transfer Posting Res HU Gdg->Input LAM-HU (1813->1063) Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF01 COR1M Create PRO Mixing | Complete Testing MF01 COR1M Create PRO Mixing |  | Testing MF01 COR1M Create PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF02 COR2M Change PRO Mixing | Complete Testing MF02 COR2M Change PRO Mixing |  | Testing MF02 COR2M Change PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF06 COR6M Confirmation of Mixing | Complete Testing MF06 COR6M Confirmation of Mixing |  | Testing MF06 COR6M Confirmation of Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP041L3 Cancel & Re-execution of Jumbo Roll Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | Complete Testing ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 | ZPP026L2 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 2 Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | Complete Testing ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 | ZPP026L3 Execution & Change Winder of Jumbo Roll Execution & Change Winder of Jumbo Roll Laminator 3 Testing Complete | Done | 100% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
Krisna, Nafi | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | In Progress | 50% | 2025-03-09
W10 (13 Maret 2025)
Team | Activity in WBS | Target | Deliverables | Deliverable | Status | Status (%) | Target (Date)
Rafly, Mela, Aryo, Alif | Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | Complete Testing X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) | X4ST116 Transfer Posting STS 314 R.Rec->Gdg (1815->1155) Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | Complete Testing X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) | X4ST219 Transfer Posting STS 314 Rec -> Gdg (1061->1161) Testing Complete | In Progress | 50% | 2025-03-10
Alif | Testing XST816 Transfer Posting STS U. Input LAM->FI LAM (1062->1L51) | Complete Testing XST816 Transfer Posting STS U. Input LAM->FI LAM (1062->1L51) |  | XST816 Transfer Posting STS U. Input LAM->FI LAM (1062->1L51) Complete | In Progress | 50% | 2025-03-10
Alif | Testing XHRS110 Transfer Posting Res HU Gdg->Input LAM-HU (1813->1063) | Complete Testing XHRS110 Transfer Posting Res HU Gdg->Input LAM-HU (1813->1063) |  | XHRS110 Transfer Posting Res HU Gdg->Input LAM-HU (1813->1063) Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF01 COR1M Create PRO Mixing | Complete Testing MF01 COR1M Create PRO Mixing |  | Testing MF01 COR1M Create PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF02 COR2M Change PRO Mixing | Complete Testing MF02 COR2M Change PRO Mixing |  | Testing MF02 COR2M Change PRO Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing MF06 COR6M Confirmation of Mixing | Complete Testing MF06 COR6M Confirmation of Mixing |  | Testing MF06 COR6M Confirmation of Mixing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | Complete Testing ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 | ZPP060L2 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 2 Testing Complete | In Progress | 50% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | Complete Testing ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 | ZPP060L3 Change Goods Issue Cancel & Re-execution of Jumbo Roll Laminator 3 Testing Complete | Planned | 0% | 2025-03-10
Rafly, Mela, Aryo, Alif | Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | Complete Testing XMF_RE Recycle Execution | XMF_RE Recycle Execution Testing Complete | Planned | 0% | 2025-03-10
Krisna, Nafi | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | XLABELJR - ZLABELJR Print Label JR Subcont | In Progress | 50% | 2025-03-09

## CO (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Yuki, Munah, Haikal | 1.2.1 SAP Discovery and Evaluation | List discovery Project Laminator #2 #3 lengkap | Done | 100% | 2024-11-07
W01 (08 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal | DISC-CO-LAM01 Cost Center | Check Cost Center pada setiap server SAP (Cost Center Group dan Hierarchy) | Done | 100% | 2024-11-08
| DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Done | 100% | 2024-11-11
W02 (11 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Done | 100% | 2024-11-13
| DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (12 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Done | 100% | 2024-11-13
| DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (13 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (14 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (15 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM04 Relation between production lne code, cost center, and reporting | Discovery Relation between production line code, cost center, and reporting Laminator #2 #3 | In Progress | 25% | 2024-11-15
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | In Progress | 25% | 2024-11-15

## Review Program (hidden)
Modul | Program | PIC | Review Status | Remaks
PP | RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | Ana, Ryan |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | Mela, Ryan |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | Aryo, Dila |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | Aryo, Dila |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | Rafly, Budi
| RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | Rafly, Budi |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060 | Mela, Ryan |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M | Mela, Budi |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | Aryo , Budi |  | Revisi Ricef
| RICEFW-PP-LAMI2&3-11 Hard Code Order Type ZPP_BD | Aryo, Dila
| RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | Aryo, Budi |  | Revisi Ricef, tanpa hardcode
| RICEFW-PP-LAMI2&3-13 Hard Code Order Type ZPP_TB | Rafly, Ryan
| RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | Rafly, Dila
| RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | Rafly, Dila
| RICEFW-PP-LAMI2&3-23 Hard Code Material Group ZTPP016N | Rafly, Dila
| RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS | Mela, Ryan
| RICEFW-PP-LAMI2&3-27 Hard Code Material Group ZPP016N | Rafly, Budi
| RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | Rafli, Budi
| RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | Aryo, Fani
| RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | Mela, Fani
| RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | Aryo, Fani
| RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | Ana, William
MM | RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | Alif, Dila
| RICEFW-MM-LAMI2&3-01 Mass Process PR PO CUstomer Stock (ZIC004SL) | Alif, Dila
| RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | Yuli, Fany
MM-PP | RICEFW-MMPP-LAMI2&3-01 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | Rafli, Budi
| RICEFW-MMPP-LAMI2&3-02 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | Ana, Budi
| RICEFW-MMPP-LAMI2&3-03 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | Ana, Budi
| RICEFW-MMPP-LAMI2&3-04 Planning Jumbo Roll For Subcontracting Laminatre (ZPP002) | Rafli, Budi
SD-MM | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | Randi, Ryan | Cancelled
SD-MM-PP | RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | Alif, Ryan
| RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | Wahyu, Budi
| RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | Randi, William
SD | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | Wahyu, Budi
| RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | Wahyu, Dila
| RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | Tyas, Ryan
| RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | Malak, Anbow
| RICEFW-SD-LAMI2&3-06 ZOLAPSLS | Malak, William
| RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | Wahyu, Fany
| RICEFW-SD-LAMI2&3-08 ZOLAP_SALES_DETAIL_IT | Malak, Anbow

## Meeting Pagi (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
|  |  | Done | 0%
|  |  | Done | 0%
W01 (08 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAP-LAM02 Meeting Pagi - Table List | Complate List of table Meeting Pagi | In Progress | 0%
Taufiq, Malak, Adit | DISC-NONSAP-LAM03 Meeting Pagi - SP and View List | Complate List of SP and View Meeting Pagi | In Progress | 0%

## WEEKLY (hidden)
Last Week Target
W11 (20 Des - 24 Des 2021)
Team | Target | Status
Functional |  | DONE
Functional |  | DONE
This Week Target
W12 (27 Des - 31 Des 2021)
Team | Target | Status
Functional |  | IN PROGRESS

## DISCOVERY (hidden)
Week# | Module | Discovery & Evaluation | PIC | Status (%) | Status (GCG) | Date | Status | Cancel Reason | Priority
W06 | Material Management |  |  | 0%
| Material Management |  |  | 0%
| Sales and Distribution |  |  | 0%
| Controlling |  |  | 0%
| Finance |  |  | 0%
| Quality Management |  |  | 0%
| Production and Planning |  |  | 0%

## WBS ALL (1) (hidden)
| W01 | PIC | JANUARY '21 | [27 empty] | FEBRUARY '21 | [27 empty] | MARCH '21 | [30 empty] | APRIL '21 | [32 empty] | NOV '24 | [27 empty] | DES '24 | [34 empty] | JAN '24 | [25 empty] | FEB'25 | [27 empty] | MAR'25
|  |  | W01 | [6 empty] | W02 | [6 empty] | W03 | [6 empty] | W04 | [6 empty] | W05 | [6 empty] | W06 | [6 empty] | W07 | [6 empty] | W08 | [6 empty] | W09 | [6 empty] | W10 | [6 empty] | W11 | [6 empty] | W12 | [6 empty] | W13 | [6 empty] | W14 | [6 empty] | W15 | [6 empty] | W16 | [6 empty] | W17 | [7 empty] | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6 | [6 empty] | W7 | [6 empty] | W8 | [6 empty] | W9 | [6 empty] | W10 | [6 empty] | W11 | [6 empty] | W12 | [6 empty] | W13 | [6 empty] | W14 | [6 empty] | W15 | [6 empty] | W16 | [6 empty] | W17 | [6 empty] | W18 | [6 empty] | W19 | [6 empty] | W20 | [6 empty] | W21 | [6 empty] | W22 | [6 empty] | W23 | [6 empty] | W23 | [6 empty] | W23 | [6 empty] | W23
|  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
PREPARE | 100%
1.1 Project Initiation | 100%
1.2 Discovery and Evaluation | 100%
1.2.1 SAP Discovery and Evaluation | 100%
Material Management | 100%
DISC-MM-LAM01 Configuration List | 100% | Randi
DISC-MM-LAM02 Maintain Storage Location | 100% | Randi
DISC-MM-LAM02 HU Requirement for Storage Location and Default Value | 100% | Randi
DISC-MM-LAM03 Set Profile for Packing Station | 100% | Randi
DISC-MM-LAM04 Maintain Table ZHU_MAPP | 100% | Randi
DISC-MM-LAM05 T-Code Variant List | 100% | Alif, Yuli
DISC-MM-LAM06 Material Group for Material Subcontracting | 100% | Alif, Yuli
DISC-MM-LAM07 Master Data & Characteristic for Material Subcontracting | 100% | Randi, Alif, Yuli
DISC-MM-LAM08 Goods Receipt Non Valuated Material for Subcontracting | 100% | Alif, Yuli
DISC-MM-LAM10 Define Movement Type | 100% | Alif, Yuli
DISC-MM-LAM12 Subcont CKI | 100% | Alif, Yuli
Sales and Distribution | 100%
DISC-SD-LAM01 Configuration List | 100%
DISC-SD-LAM02 Creating Division | 100%
DISC-SD-LAM03 Assigning Division to Sales Organization | 100%
DISC-SD-LAM04 Setting up Sales Area | 100%
DISC-SD-LAM05 Defining Common Divisions | 100%
DISC-SD-LAM06 Assigning Sales Office to Sales Area | 100%
DISC-SD-LAM07 SIS Header Configuration | 100%
DISC-SD-LAM08 SIS Item Configuration | 100%
DISC-SD-LAM09 Defining Pricing Procedure Determination | 100%
DISC-SD-LAM10 Materials: Account Assignment Group | 100%
DISC-SD-LAM11 Divisions by Sales Org - Assigning Order Type | 100%
DISC-SD-LAM12 Assigning Sales Area to Credit Control Area | 100%
DISC-SD-LAM13 Materials : Product Hierarchy | 100%
DISC-SD-LAM14 Material Group 1 | 100%
DISC-SD-LAM15 Material Group 2 | 100%
DISC-SD-LAM16 Material Group 3 | 100%
DISC-SD-LAM17 Subcont CKI | 100%
Finance and Controlling | 100%
DISC-CO-LAM00 Konfigurasi CO | 100% | YUKI & HAIKAL
DISC-CO-LAM01 Cost Center | 100% | YUKI & HAIKAL
DISC-CO-LAM02 Cost Element | 100% | YUKI & HAIKAL
DISC-CO-LAM03 Activity Type | 100% | YUKI & HAIKAL
DISC-CO-LAM04 Profit Center | 100% | YUKI & HAIKAL
DISC-CO-LAM05 Relation between production line code, cost center, and reporting | 100% | YUKI
DISC-CO-LAM06 Splitting Structure | 100% | YUKI & HAIKAL
DISC-CO-LAM07 Result Analysis Keys | 100% | YUKI & HAIKAL
DISC-CO-LAM08 Variance Keys | 100% | YUKI & HAIKAL
DISC-CO-LAM09 Settlement Profile | 100% | YUKI & HAIKAL
DISC-CO-LAM10 Allocation Structure | 100% | YUKI & HAIKAL
DISC-CO-LAM11 Source Structure | 100% | YUKI & HAIKAL
DISC-CO-LAM12 PA Transfer Structure | 100% | YUKI & HAIKAL
DISC-CO-LAM13 Material Ledger | 100% | YUKI & HAIKAL
DISC-CO-LAM14 Profitability Analysis - Characteristics | 100% | YUKI & HAIKAL
DISC-CO-LAM15 Profitability Analysis – Value Fields | 100% | YUKI & HAIKAL
DISC-CO-LAM16 Profitability Analysis – Costing Key | 100% | YUKI & HAIKAL
DISC-CO-LAM17 Actual Assesment Cycle | 100% | YUKI & HAIKAL
DISC-CO-LAM18 Distribution Cycle | 100% | YUKI & HAIKAL
DISC-CO-LAM19 Cost Splitting | 100% | YUKI & HAIKAL
DISC-CO-LAM20 Price Calculation | 100% | YUKI & HAIKAL
DISC-CO-LAM21 Actual COPA Assesment Cycle | 100% | YUKI & HAIKAL
DISC-CO-LAM22 Allocate Packing Costs to COGS | 100% | YUKI & HAIKAL
DISC-CO-LAM23 Allocate PCA Temp | 100% | YUKI & HAIKAL
DISC-FI-LAM01 FI Configuration List | 100% | Munah
DISC-FI-LAM02 Master Data GL Account | 100% | Munah
DISC-FI-LAM03 Define Valuation Class | 100% | Munah
DISC-FI-LAM04 Automatic Materials Management Posting | 100% | Munah
DISC-FI-LAM05 Renevue Account Determination | 100% | Munah
DISC-FI-LAM06 Asset Class Specify Account Determination | 100% | Munah
DISC-FI-LAM07 Asset Number Ranges | 100% | Munah
DISC-FI-LAM08 Define Asset Class | 100% | Munah
DISC-FI-LAM09 Asset Account Assignment Acquisitions | 100% | Munah
DISC-FI-LAM10 Assign Asset Class to Depreciation Area | 100% | Munah
DISC-FI-LAM11 Acct Determination For Exch.Rate Differences | 100% | Munah
DISC-FI-LAM12 Assign GL to Financial Statement Version | 100% | Munah
DISC-FI-LAM13 Report Painter : Change Report | 100% | Munah
DISC-FI-LAM14 Subcont CKI | 100% | Munah,Fila,Yuki,Haikal
Quality Management | 100%
DISC-QM-LAM01 Explore Inspection Type for Subcont | 100% | Ana,Mela
DISC-QM-LAM02 Explore Task List QM for Subcont | 100% | Ana,Mela
Plan Maintenance | 100%
DISC-QM-LAM01 Functional Location | 100%
DISC-QM-LAM02 Explore Relation Field Connect to Functional Location | 100%
Production Planning | 100%
DISC-PP-LAM01 Configuration List | 100% | Ana
DISC-PP-LAM02 Enhancement List | 100% | Ana
DISC-PP-LAM03 T-Code Variant List | 100% | Mela
DISC-PP-LAM04 Defining Order Type for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM05 Defining Number Range for Order for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM06 Defining Order Type Dependent Parameter for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM07 Administer selection profile for the combination for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM08 Determining Capacity Planner for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM09 Configuration Creating Class for Laminator #2 #3 | 100% | Mela
DISC-PP-LAM10 Configuration Specifying Scheduling Parameters for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM11 Configuration Defining Checking Controls for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM12 Configuration Defining Confirmation Parameters for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM13 Configuration Defining Default Values – Task List Selection for Laminator #2 #3 | 100% | Ana
DISC-PP-LAM14 Configuration Defining Characteristic for Laminator #2 #3 | 100% | Mela
DISC-PP-LAM15 Maintain Table ZTMAP for Laminator #2 #3 | 100% | Mela
DISC-PP-LAM18 Maintain Resource for Laminator #2 #3 | 100% | Mela
DISC-PP-LAM19 Maintain HR Assignment for Laminator #2 #3 | 100% | Mela
DISC-PP-LAM20 Subcont CKI | 100% | Ana
ABAP | 100%
DISC-ABAP-LAM01 Discover Hard Code Order Type in ZPP041 (Eksekusi JR) | 100% | Ryan
DISC-ABAP-LAM02 Discover Hard Code Order Type in ZPP060 (Good Issue JR) | 100% | Ryan
DISC-ABAP-LAM03 Discover Hard Code Order Type in ZPP001 (Eksekusi SR) | 100% | Dila
DISC-ABAP-LAM04 Discover Hard Code Order Type in ZPP011 (Report JR Harian) | 100% | Dila
DISC-ABAP-LAM05 Discover Hard Code Order Type in ZPP002 (Planning JR) | 100% | Budi
DISC-ABAP-LAM06 Discover Hard Code Order Type in ZTPP002 (Download PRO JR) | 100% | Budi
DISC-ABAP-LAM07 Discover Hard Code Order Type in ZTPP060 (Insert GI PRO JR to SQL) | 100% | Ryan
DISC-ABAP-LAM08 Discover Hard Code Order Type in ZTPP011 | 100% | Dila
DISC-ABAP-LAM09 Discover Hard Code Order Type in ZCOR6M (Confirmation Mixing) | 100% | Budi
DISC-ABAP-LAM10 Discover Hard Code Order Type ZPP_RS (Timbang Scrap) | 100% | Ryan
DISC-ABAP-LAM11 Discover Hard Code Order Type ZPP_BD (Balancing) | 100% | Dila
DISC-ABAP-LAM12 Discover Hard Code Order Type ZPP_RC (Closing Raw Recycle) | 100% | Budi
DISC-ABAP-LAM13 Discover Hard Code Order Type ZPP_TB (Timbang) | 100% | Ryan
DISC-ABAP-LAM14 Discover Hard Code Order Type ZLABELJR | 100% | Ryan
DISC-ABAP-LAM15 Discover Hard Code Material Group ZPP018 (Adjustment Material Purc) | 100% | Ryan
DISC-ABAP-LAM16 Discover Hard Code Material Group ZPP016 | 100% | Dila
DISC-ABAP-LAM17 Discover Hard Code Material Group ZPP016CX | 100% | Dila
DISC-ABAP-LAM18 Discover Hard Code Material Group ZTPP016N | 100% | Dila
DISC-ABAP-LAM19 Discover Hard Code Material Group ZPP016N | 100% | Budi
DISC-ABAP-LAM20 Discover Hard Code Title Bar T-Code Variant ZPP041 | 100% | Budi
DISC-ABAP-LAM21 Discover Hard Code Sloc in ZPP019 (Process Order For Roll Stripping) | 100% | Budi
DISC-ABAP-LAM22 Discover Hard Code Sloc in ZPP005N (Report Pending Order) | 100% | Budi
DISC-ABAP-LAM23 Discover Post Good Movement for JR Execution (Special Stock) | 100% | Budi
DISC-ABAP-LAM24 Discover Hard Code Recycle Execution ZPP_RE | 100% | William
DISC-ABAP-LAM25 Discover One Push Button JR to SR | 100% | Ryan, Dila
1.2.2 NON SAP Discovery and Evaluation | 100%
Non SAP | 100%
DISC-NONSAP-LAM01 UXTOOL Refresh Knowledge as is Application | 100% | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26
DISC-NONSAP-LAM02 UXTOOL Review & Discovery impact of new Laminator | 100% | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26
DISC-NONSAP-LAM15 UXTOOL Validation and Mitigation of UXTool Data for New Laminator Line | 100% | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26
DISC-NONSAP-LAM03 UXTOOL Define change list & configuration UXTOOL for new Line Lamintor | 100% | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26
Non SAP OLAP & Meeting Pagi | 100% | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26; W4 28 to W4 29
DISC-NONSAPOLAP-LAM01 Meeting Pagi - List of Table, View, and SP | 100% | Malak, Adit | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26; W4 28 to W4 29
DISC-NONSAPOLAP-LAM02 Meeting Pagi - Frontend | 100% | Malak, Adit | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26; W4 28 to W4 29
DISC-NONSAPOLAP-LAM03 OLAP 2024 - OLAP Excel File List and Data Source | 100% | Malak, Adit | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26; W4 28 to W4 29
DISC-NONSAPOLAP-LAM04 OLAP 2024 - Data Interface List | 100% | Malak, Adit | bar: W1 7 to W1 8; W2 11 to W2 15; W3 18 to W3 22; W4 25 to W4 26; W4 28 to W4 29
1.3 Business Process Map | 100%
EXPLORE | 67.74%
2.1 Business Blueprint Design | 100% | bar: W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
2.2.1 Material Management | 100% | bar: W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-MD02-Raw Material | 100% | Alif | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-MD03 SFG | 100% | Alif | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-MD04 FG | 100% | Alif | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-GI01 Goods Issue to Cost Center v01 | 100% | Yuli | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 26; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-GI02 Mengembalikan Barang (GI to Cost Center) | 100% | Yuli | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-PK01 Packing v0.1 | 100% | Yuli | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-PK02 Repack v01 | 100% | Yuli | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 26; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-ST01 Trf Sloc to Sloc (Non HU) | 100% | Randi | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-ST02 Trf Sloc to Sloc (With HU) | 100% | Randi | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
MM-BP-ST05 Trf to Gudang FG | 100% | Randi | bar: W11 16 to W11 17; W7 16 to W7 20; W8 23 to W8 27; W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 14
2.2.2 Sales and Distribution | 100% | bar: W11 16 to W11 17; W9 30 to W9 3
SD Organizational Unitz | 100% | Tyas | bar: W11 16 to W11 17; W9 30 to W9 3
SD General Settings | 100% | Tyas | bar: W11 16 to W11 17; W9 30 to W9 3
SDGI01 Reverse Goods Movement | 100% | Tyas | bar: W11 16 to W11 17; W9 30 to W9 3
SDCM01 Release Delivery Block karena Terms of Payments | 100% | Tyas | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO11 Sales with Down Payment | 100% | Tyas | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO27 Sales Order Inventory | 100% | Tyas | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO01 Domestic Sales Finished Goods (1st Grade) | 100% | Tyas | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO02 Domestic Sales Finished Goods (2nd Grade) | 100% | Wahyu | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO07 Export Sales Finished Goods (1st Grade) | 100% | Wahyu | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO08 Export Sales Finished Goods (2nd Grade) | 100% | Wahyu | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO13 Domestic Sample Order Finished Goods (1st Grade) | 100% | Wahyu | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO14 Domestic Sample Order Finished Goods (2nd Grade) | 100% | Wahyu | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO17 Export Sample Order Finished Goods (1st Grade) | 100% | Wahyu | bar: W11 16 to W11 17; W9 30 to W9 3
SDSO18 Export Sample Order Finished Goods (2nd Grade) | 100% | Wahyu | bar: W11 16 to W11 17; W9 30 to W9 3
2.2.3 Quality Management | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.4 Finance and Controlling | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FI General Seeting | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FIMD01. GL Account Master Data Maintenance | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FIMD04. Asset Master Data Maintenance | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FIAA01. Asset Sales and Lease Back | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FIAA02. Asset Transfer | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FIAA03. Asset Retirement | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FIAA04. Settlement AUC | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - FIAA05. Delta Depreciation Area for Parallel Asset Valuation | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COGS01 General Settings | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - CO Master Data | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COMD01-06 Master Data Maintenance | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COOM01 Plan Rate Calculation | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COOM02 Create Actual Distribution Cycle | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COOM03 Create Actual Assessment Cycle | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COCL01 Period End Closing | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COPL01 Planning Profit Center | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COPC01 Standard Cost Estimate | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COPC02 Raw Rec and Recycle Price Change | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP - COPA01 Create Actual COPA Assessment Cycle | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.5 Plan Maintenance | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.6 Production Planning | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
Business Blueprint-General Setting (Updated for LMN WR) | 100% | Aryo | bar: W11 16 to W11 17; W6 9 to W6 13; W9 30 to W9 3
PPPB01-Pengembangan Produk Baru (Updated for LAMI) | 100% | Ana | bar: W11 16 to W11 17; W6 9 to W6 13; W9 30 to W9 3
PPPE11 Production Process of Jumbo Roll Laminating V2 | 100% | Mela | bar: W11 16 to W11 17; W6 9 to W6 13; W9 30 to W9 3
PPPE12 Production Process of Slit Roll Laminating V2 | 100% | Mela | bar: W11 16 to W11 17; W6 9 to W6 13; W9 30 to W9 3
PPPE17 Production Process of Mixing (Updated for LMN WR) | 100% | Aryo | bar: W11 16 to W11 17; W6 9 to W6 13; W9 30 to W9 3
2.2 Business Blueprint Confirmation & Finalization | 42.86% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.1 End to End Business Process | 100% | bar: W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.2 Material Management | 0% | bar: W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.3 Sales and Distribution | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.4 Quality Management | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.5 Finance and Controlling | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.6 Plan Maintenance | 100% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
2.2.7 Production Planning | 0% | bar: W11 16 to W11 17; W5 2 to W5 6; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
BP-… | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
2.3 Enhancement (RICEFW) Design | 60.36% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
2.3.1 SAP | 44.65% | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1 Production Planning | 57.9% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 27; W9 30 to W9 3
RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | 75% | Rafly | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | 0% | Rafly | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060 | 0% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-08 Hard Code Order Type ZTPP011 | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M | 0% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-11 Hard Code Order Type ZPP_BD | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-13 Hard Code Order Type ZPP_TB | 0% | Rafly | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-15 T-Code Variant ZPP026L2 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-16 T-Code Variant ZPP026L3 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-17 T-Code Variant ZPP041L2 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-18 T-Code Variant ZPP041L3 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-19 T-Code Variant ZPP060L2 | 0% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-20 T-Code Variant ZPP060L3 | 0% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | 100% | Rafly | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | 0% | Rafly | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-23 Hard Code Material Group ZTPP016N | 0% | Rafly | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS | 0% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-26 Hard Code Title Bar T-Code Variant | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-27 Hard Code Material Group ZPP016N | 100% | Rafly | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | 70% | Rafli | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | 75% | Aryo, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | 0% | Mela, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | 75% | Aryo, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | 0% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-34 Kalkulator Normal | 0% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2 Material Management | 76.67% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | 80% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20; W12 20 to W12 24
RICEFW-MM-LAMI2&3-02 Mass Process PR PO CUstomer Stock (ZIC004SL) | 80% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20; W12 20 to W12 24
RICEFW-MM-LAMI2&3-03 New Design Label HU for Subcontracting Laminate | 70% | Yuli, Fani | bar: W6 9 to W6 13; W7 16 to W7 20; W12 20 to W12 24
2.3.1.3 Material Management-Production Planning | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-03 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | 25% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-04 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 25% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-05 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 25% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.4 Sales & Distribution-Material Management | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMM-LAMI2&3-01 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013N) | 25% | Randi, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.5 Sales & Distribution-Material Management-Production Planning | 33.33% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP05N) | 25% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | 50% | Wahyu, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | 25% | Randi | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.6 Sales & Distribution | 50% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | 50% | Wahyu | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | 50% | Wahyu | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | 50% | Tyas | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | 50% | Malak | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-06 ZOLAPSLS | 50% | Malak | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | 50% | Wahyu | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT | 50% | Malak | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.7 Quality Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-QM-LAMI2&3-01 Validating 24-Hour Aging of Laminate Subcont CKI (ZQA32) | 0% | Rafli | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.2 NON SAP | 76.07% | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1 NON SAP | 76.07% | bar: W6 9 to W6 13; W7 16 to W7 20
Non SAP Meeting Pagi & OLAP | 79.69% | bar: W6 9 to W6 13; W7 16 to W7 20
Meeting Pagi | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Insert New Data | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM01 Insert Master Data Line | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM02 Insert Master Data LineRecycle (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM03 Insert Master Data SAPLine (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM04 Insert Master Data SAPLine (BI_DW) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM05 Insert Master Data GASTON | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM06 Insert Master Data KWHTON | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM07 Insert Master Data WTRTON | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Enhancement Stored Procedure | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM08 Alter Stored Procedure ProsesJR (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM09 Alter Stored Procedure ProsesRecalJR (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM010 Alter Stored Procedure ProsesRecalSR1 (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM011 Alter Stored Procedure ProsesRecalSR2 (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM12 Alter Stored Procedure ProsesRecalSrc (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM13 Alter Stored Procedure ProsesSrc (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM14 Alter Stored Procedure ProsesSR1st (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-Meeting Pagi-LAM15 Alter Stored Procedure ProsesSR2nd (MeetingPagi) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Data Interfacing - BAPI WS | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Add New Parameter | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-BAPI WS-LAM01 Add New Parameter-Download_AUFK-Add Order Type | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Data Interfacing - DBCO | 59.38% | bar: W6 9 to W6 13; W7 16 to W7 20
Add New Parameter | 59.38% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM01 Add New Parameter-ZOLAPPRD RC MALAM | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM02 Add New Parameter-ZOLAPPRD RC PAGI | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM03 Add New Parameter-ZOLAPPRD RC SIANG | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM04 Add New Parameter-ZOLAPPRD RC SORE | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM05 Add New Parameter-ZOLAPPRD ZCOMAT | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM06 Add New Parameter-UX_STOCK_BY_CHAR_DAILY | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM07 Add New Parameter-UX_PRO_TECO_SHIFT_2 | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM08 Add New Parameter-UX_PRO_TECO_SHIFT_3 | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM09 Add New Parameter-UX_PRO_TECO_SHIFT_1 | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM10 Add New Parameter-UX_REKAP_SLITTING_DAILY-1 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM11 Add New Parameter-UX_INSP_LOT_LAMSCRIM_DAILY | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM12 Add New Parameter-UX_INSP_LOT_LAMSCRIM_DAILY-1 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM13 Add New Parameter-UX_STOCK_REC_DAILY | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM14 Add New Parameter-MR ZPP009A DAILY | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM15 Add New Parameter-MR ZPP009A MONTHLY | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM16 Add New Parameter-REKAP_SLITTING_HARIAN | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM17 Add New Parameter-ZPP011 & ZPP016 06:00 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM18 Add New Parameter-ZPP011 & ZPP016 14:30 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM19 Add New Parameter-ZPP011 & ZPP016 22:30 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM20 Add New Parameter-ZPP011 & ZPP016 NOW | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM21 Add New Parameter-MP SR-SCRAP | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM22 Add New Parameter-MP SLIT ROLL | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM23 Add New Parameter-ZPPR_DL_JR_TODAY_ZPP011 | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM24 Add New Parameter-R MP SLIT_ROLL_TODAY | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM25 Add New Parameter-ZPP011 & ZPP016 06:00 | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM26 Add New Parameter-ZPP011 & ZPP016 14:30 | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM27 Add New Parameter-ZPP011 & ZPP016 22:30 | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM28 Add New Parameter-ZPP011 & ZPP016 NOW | 25% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM29 Add New Parameter-ZOLAPPRD RC MALAM | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM30 Add New Parameter-ZOLAPPRD RC PAGI | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM31 Add New Parameter-ZOLAPPRD RC SIANG | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-DBCO-LAM32 Add New Parameter-ZOLAPPRD RC SORE | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
OLAP Excel File | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Insert New Data | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM01 Insert Master Data ZOLAP_PRODLINE (BA999) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM02 Insert Master Data T023 (BA999) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM03 Insert Master Data ZDIM_LINE (BA999) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM04 Insert Master Data T001L (BA999) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM05 Insert Master Data TVLKT (BA999) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM06 Insert Master Data T003O (BA999) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM07 Insert Master Data TVAK (BA999) | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM08 Insert Master Data T0023T (B)I_DW | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Enhancement SAP Program | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM09 Enhancement SAP Program-ZOLAPSLS | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM10 Enhancement SAP Program-ZOLAP_SALES_DETAIL | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM11 Enhancement SAP Program-ZOLAP_SALES_DETAIL_IT | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Enhancement View | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM12 Alter SP [BA999].[dbo].[v_OLAP_JR_DEFECT_CNV_2025] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM13 Alter SP [BA999].[dbo].[v_OLAP_JR_PROPERTIES_CNV_2025] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM14 Alter SP [BA999].[dbo].[v_OLAPRefresh_RMConsumptionPerLine_w/Val_TS_CNV] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM15 Alter SP [BA999].[dbo].[v_OLAPRefresh_Consumption_PerJR_wo/Val_TS] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM16 Alter SP [BA999].[dbo].[v_OLAPRefresh_OutputJRCONV_w/Val_TS] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM17 Alter SP [BA999].[dbo].[v_OLAPRefresh_JRStockConv_TS] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM18 Alter SP [BA999].[dbo].[v_OLAPRefresh_OutputSR2025_CONV_TS] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM19 Alter SP [BA999].[dbo].[v_OLAPRefresh_SRStockRwRsCONV_TS] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM20 Alter SP [BA999].[dbo].[v_OLAPRefresh_JRStockConv_TS_w/o_T] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-OLAP-LAM21 Alter SP [BA999].[dbo].[v_OLAPRefresh_SRStockRwRsCONV_TS_w/o_T] | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
UXTOOL | 69.44% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM08 Master Data Role Define | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM09 Master Data Role Users | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM17 Master Data SYS_023 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM19 Master Data SYS_001L | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM20 Master Data SYS_003O | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM23 Master Data SYS_CORU | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM24 Master Data PackingStation | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM26 Master Data RESOURCE | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM27 Master Data HR0001 | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM28 Master Data HR1001 | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
2.4 Configuration Design | 95.83% | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.2 SAP | 95.83% | bar: W6 9 to W6 13; W7 16 to W7 20
Material Management | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Finance | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Controlling | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
Plan Maintenance | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
Production Planning | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
01 Defining Order type | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30 to W9 31
02 Defining Number Range for Order | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30 to W9 31
03 Assign number range to Order | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30 to W9 31
04 Defining Order Type Dependent Parameter | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30 to W9 31
05 Administer selection profile for the combination | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
08 Specifying Scheduling Parameters | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
09 Defining Checking Controls | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
10 Defining Confirmation Parameters | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
11 Defining Default Values – Task List Selection | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
12 Defining New Production Line | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
13 Creating Characteristic | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
14 Assign Characteritic to Class | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
Maintain Table ZTMAP_SLOC_JR_GR | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
Maintain Table ZTMAP_SLOCFILM | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
Maintain Table ZTMAP_SLOCRR | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3
Maintain Resource Process | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3; W10 6
Maintain Resource Mixing | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3; W10 6
Maintain HR Assignment in Resource Process | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3; W10 6
Maintain HR Assignment in Resource Mixing | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W9 31 to W9 3; W10 6
Sales and Distribution | 100% | bar: W6 9 to W6 13; W7 16 to W7 20
2.5 Authorization Requirements and Design | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
2.5.2 SAP | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Material Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
MM- … | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Sales and Distribution | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
SD-… | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Finance and Controlling | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
CO-.. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
FI-… | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Quality Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
QM-… | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Plan Maintenance | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
PM-… | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
PP-… | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
2.5.2 NON SAP Authorization Requirements and Design | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Non SAP | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
NONSAP-UXTOOL.. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
NONSAP-Meeting Pagi.. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
Insert New Data | bar: W6 9 to W6 13; W7 16 to W7 20
NONSAP-OLAP.. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
REALIZE | 21.02%
3.1 Configuration and Documentation | 40.42% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.1.1 DEV 100 | 75% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Material Management | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 20
Configuration for New Production Line | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 20
Download and Compare Data | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 20
Configuration for Business Process Laminate Subcont | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Sales and Distribution | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configuration for Business Process Laminate Subcont | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Finance and Accounting | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configuration for Business Process Laminate Subcont | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configuration for New Production Line | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Production Planning | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
01 Defining Order type | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
04 Defining Order Type Dependent Parameter | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
05 Administer selection profile for the combination | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
08 Specifying Scheduling Parameters | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
09 Defining Checking Controls | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
10 Defining Confirmation Parameters | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
11 Defining Default Values – Task List Selection | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
Download and Compare Data for New Production Line | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
Download and Compare Data | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
3.1.2 DEV 130 | 70% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Material Management | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configuration for New Production Line | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 20
Download and Compare Data | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 20
Configuration for Business Process Laminate Subcont | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Sales and Distribution | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Finance and Accounting | 50% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configuration for Business Process Laminate Subcont | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configuration for New Production Line | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Plan Maintenance | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Production Planning | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
01 Defining Order type | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
02 Defining Number Range for Order | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
03 Assign number range to Order | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
04 Defining Order Type Dependent Parameter | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
05 Administer selection profile for the combination | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
08 Specifying Scheduling Parameters | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
09 Defining Checking Controls | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
10 Defining Confirmation Parameters | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
11 Defining Default Values – Task List Selection | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
12 Defining New Production Line | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
13 Creating Characteristic | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
14 Assign Characteritic to Class | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Maintain Table ZTMAP_SLOC_JR_GR | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Maintain Table ZTMAP_SLOCFILM | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Maintain Table ZTMAP_SLOCRR | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Maintain Resource Process | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Maintain Resource Mixing | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Maintain HR Assignment in Resource Process | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Maintain HR Assignment in Resource Mixing | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data for New Production Line | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27; W12 24
Configuration for Business Process Laminate Subcont | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 100% | Aryo | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.1.3 QA 320 | 16.67% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configuration | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Sales and Distribution | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Quality Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Finance and Accounting | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | 50% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Plan Maintenance | 100% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Configured | 34.59% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Download and Compare Data | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.2 Enhancement (RICEFW) Development | 69.19% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
2.3.1 SAP | 73.98% | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1 DEV NC | 78.31% | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1.1 Production Planning | 96.55% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | 100% | Ana, Ryan | W17 1: Ryan
RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | 100% | Mela, Ryan | W17 1: Ryan
RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | 100% | Aryo, Dila | W17 1: Dila
RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | 100% | Aryo, Dila | W17 1: Dila
RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | 100% | Rafly, Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | 100% | Rafly, Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060 | 100% | Mela, Ryan | W17 1: Ryan
RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M | 100% | Mela, Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | 100% | Aryo , Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-11 Hard Code Order Type ZPP_BD | 100% | Aryo, Dila | W17 1: Dila
RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | 100% | Aryo, Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-13 Hard Code Order Type ZPP_TB | 100% | Rafly, Ryan | W17 1: Ryan
RICEFW-PP-LAMI2&3-15 T-Code Variant ZPP026L2 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-16 T-Code Variant ZPP026L3 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-17 T-Code Variant ZPP041L2 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-18 T-Code Variant ZPP041L3 | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-19 T-Code Variant ZPP060L2 | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-20 T-Code Variant ZPP060L3 | 100% | Mela | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | 100% | Rafly, Dila | W17 1: Dila
RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | 100% | Rafly, Dila | W17 1: Dila
RICEFW-PP-LAMI2&3-23 Hard Code Material Group ZTPP016N | 100% | Rafly, Dila | W17 1: Dila
RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS | 100% | Mela, Ryan | W17 1: Ryan
RICEFW-PP-LAMI2&3-26 Hard Code Title Bar T-Code Variant | 100% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20; W9 30
RICEFW-PP-LAMI2&3-27 Hard Code Material Group ZPP016N | 100% | Rafly, Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-28 One Button | 100% | Ana, Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | 75% | Rafli, Budi | W17 1: Budi
RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | 75% | Aryo, Fani | W17 1: Fani
RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | 75% | Mela, Fani | W17 1: Fani
RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | 75% | Mela, Fani | W17 1: Fani
RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | 75% | Ana, William | W17 1: William
2.3.1.1.2 Material Management | 91.67% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | 100% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process PR PO CUstomer Stock (ZIC004SL) | 100% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | 75% | Yuli, Fany | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1.3 Material Management-Production Planning | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-01 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | 75% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-02 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 75% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-03 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 75% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-04 Planning Jumbo Roll For Subcontracting Laminatre (ZPP002) | 75% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1.4 Sales & Distribution-Material Management | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | 75% | Randi, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1.5 Sales & Distribution-Material Management-Production Planning | 66.67% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | 75% | Alif, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | 75% | Wahyu, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | 50% | Randi, William | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.1.6 Sales & Distribution | 65% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | 100% | Wahyu, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | 75% | Wahyu, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | 75% | Tyas, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | 0% | Malak, Anbow | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-06 ZOLAPSLS | 75% | Malak, William | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | 0% | Wahyu, Fany | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.7 Quality Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-QM-LAMI2&3-01 Validating 24-Hour Aging of Laminate Subcont CKI (ZQA32) | 0% | William | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2 DEV AIX | 69.64% | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2.1 Production Planning | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | 75% | Ana, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20; W8 27; W9 30 to W9 3
RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | 75% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | 75% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | 75% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | 75% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | 75% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060 | 75% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M | 75% | Mela, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | 75% | Aryo , Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-11 Hard Code Order Type ZPP_BD | 75% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | 75% | Aryo, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-13 Hard Code Order Type ZPP_TB | 75% | Rafly, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | 75% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | 75% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-23 Hard Code Material Group ZTPP016N | 75% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS | 75% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-27 Hard Code Material Group ZPP016N | 75% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | 75% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | 75% | Aryo, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | 75% | Mela, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | 75% | Aryo, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | 75% | Ana, William | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-34 Kalkulator Normal | 25% | Ana | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2.2 Material Management | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | 75% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process PR PO CUstomer Stock (ZIC004SL) | 75% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | 75% | Yuli, Fany | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2.3 Material Management-Production Planning | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-01 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | 75% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-02 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 75% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-03 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 75% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-04 Planning Jumbo Roll For Subcontracting Laminatre (ZPP002) | 75% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2.4 Sales & Distribution-Material Management | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | 75% | Randi, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2.5 Sales & Distribution-Material Management-Production Planning | 75% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | 75% | Alif, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | 75% | Wahyu, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | 0% | Randi, William | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.2.6 Sales & Distribution | 42.86% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | 50% | Wahyu, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | 75% | Wahyu, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | 75% | Tyas, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | 25% | Malak, Anbow | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-06 ZOLAPSLS | 75% | Malak, William | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | 0% | Wahyu, Fany | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-08 ZOLAP_SALES_DETAIL_IT | 0% | Malak, Anbow | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.1.7 Quality Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-QM-LAMI2&3-01 Validating 24-Hour Aging of Laminate Subcont CKI (ZQA32) | 0% | Rafli | bar: W6 9 to W6 13; W7 16 to W7 20
2.3.2 NON SAP | 64.39% | bar: W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-01 SP_ValueHelp Add Hardcode | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-02 SP_MIX01_01_03_OPT_GNRL Add New SFG Master Data | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-03 SP_JR041A_02_03_OPT_SISAPANJANG Add New Hardcode Matgroup for Validation | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-04 SP_JR041A_02_03_OPT_VALIDASISLOC Add New JR, SR Hardcode Matgroup for Validation | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAMI2&3-05 SP_JR041A_02_03_OPT_VALIDASILENGTH Add New JR, SR Hardcode Matgroup for Validation | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM07 Master Data SYS_USR02 | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM08 Master Data Role Define | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM09 Master Data Role Users | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM10 Master Data SYS_TRCD | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM11 Master Data ZUX_SHOME | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM12 Master Data SYS_ROLE_1251 | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM13 Master Data XTMAP_SLOC_JR_GR | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM14 Master Data XTMAP_SLOCREC | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM15 Master Data XTMAP_SLOCRR | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM16 Master Data XTMAP_RECYCLE | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM17 Master Data SYS_023 | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM18 Master Data SYS_TRCD_TIME | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM19 Master Data SYS_001L | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM20 Master Data SYS_003O | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM21 Master Data MAP_LABELJR | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM22 Master Data MTL_ORDTYPE | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM23 Master Data SYS_CORU | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM24 Master Data PackingStation | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM25 Master Data RESOURCEJR | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM26 Master Data RESOURCE | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20
WRICEF-UXTOOL-LAM27 Master Data HR0001 | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-UXTOOL-LAM28 Master Data HR1001 | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Non SAP Meeting Pagi & OLAP | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Meeting Pagi | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Insert New Data | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM01 Insert Master Data Line | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM02 Insert Master Data LineRecycle (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM03 Insert Master Data SAPLine (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM04 Insert Master Data SAPLine (BI_DW) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM05 Insert Master Data GASTON | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM06 Insert Master Data KWHTON | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM07 Insert Master Data WTRTON | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Enhancement Stored Procedure | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM08 Alter Stored Procedure ProsesJR (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM09 Alter Stored Procedure ProsesRecalJR (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM10 Alter Stored Procedure ProsesRecalSR1 (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM11 Alter Stored Procedure ProsesRecalSR2 (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM12 Alter Stored Procedure ProsesRecalSrc (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM13 Alter Stored Procedure ProsesSrc (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM14 Alter Stored Procedure ProsesSR1st (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-Meeting Pagi-LAM15 Alter Stored Procedure ProsesSR2nd (MeetingPagi) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Data Interfacing - BAPI WS | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Add New Parameter | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-BAPI WS-LAM01 Add New Parameter-Download_AUFK-Add Order Type | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Data Interfacing - DBCO | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Add New Parameter | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM01 Add New Parameter-ZOLAPPRD RC MALAM | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM02 Add New Parameter-ZOLAPPRD RC PAGI | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM03 Add New Parameter-ZOLAPPRD RC SIANG | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM04 Add New Parameter-ZOLAPPRD RC SORE | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM05 Add New Parameter-ZOLAPPRD ZCOMAT | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM06 Add New Parameter-UX_STOCK_BY_CHAR_DAILY | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM07 Add New Parameter-UX_PRO_TECO_SHIFT_2 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM08 Add New Parameter-UX_PRO_TECO_SHIFT_3 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM09 Add New Parameter-UX_PRO_TECO_SHIFT_1 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM10 Add New Parameter-UX_REKAP_SLITTING_DAILY-1 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM11 Add New Parameter-UX_INSP_LOT_LAMSCRIM_DAILY | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM12 Add New Parameter-UX_INSP_LOT_LAMSCRIM_DAILY-1 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM13 Add New Parameter-UX_STOCK_REC_DAILY | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM14 Add New Parameter-MR ZPP009A DAILY | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM15 Add New Parameter-MR ZPP009A MONTHLY | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM16 Add New Parameter-REKAP_SLITTING_HARIAN | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM17 Add New Parameter-ZPP011 & ZPP016 06:00 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM18 Add New Parameter-ZPP011 & ZPP016 14:30 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM19 Add New Parameter-ZPP011 & ZPP016 22:30 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM20 Add New Parameter-ZPP011 & ZPP016 NOW | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM21 Add New Parameter-MP SR-SCRAP | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM22 Add New Parameter-MP SLIT ROLL | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM23 Add New Parameter-ZPPR_DL_JR_TODAY_ZPP011 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM24 Add New Parameter-R MP SLIT_ROLL_TODAY | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM25 Add New Parameter-ZPP011 & ZPP016 06:00 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM26 Add New Parameter-ZPP011 & ZPP016 14:30 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM27 Add New Parameter-ZPP011 & ZPP016 22:30 | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM28 Add New Parameter-ZPP011 & ZPP016 NOW | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM29 Add New Parameter-ZOLAPPRD RC MALAM | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM30 Add New Parameter-ZOLAPPRD RC PAGI | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM31 Add New Parameter-ZOLAPPRD RC SIANG | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-DBCO-LAM32 Add New Parameter-ZOLAPPRD RC SORE | 50% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
OLAP Excel File | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Insert New Data | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM01 Insert Master Data ZOLAP_PRODLINE (BA999) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM02 Insert Master Data T023 (BA999) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM03 Insert Master Data ZDIM_LINE (BA999) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM04 Insert Master Data T001L (BA999) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM05 Insert Master Data TVLKT (BA999) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM06 Insert Master Data T003O (BA999) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM07 Insert Master Data TVAK (BA999) | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM08 Insert Master Data T0023T (B)I_DW | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Enhancement SAP Program | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM09 Enhancement SAP Program-ZOLAPSLS | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM10 Enhancement SAP Program-ZOLAP_SALES_DETAIL | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM11 Enhancement SAP Program-ZOLAP_SALES_DETAIL_IT | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Enhancement Stored Procedure | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM12 Alter SP [BA999].[dbo].[v_OLAP_JR_DEFECT_CNV_2025] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM13 Alter SP [BA999].[dbo].[v_OLAP_JR_PROPERTIES_CNV_2025] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM14 Alter SP [BA999].[dbo].[v_OLAPRefresh_RMConsumptionPerLine_w/Val_TS_CNV] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM15 Alter SP [BA999].[dbo].[v_OLAPRefresh_Consumption_PerJR_wo/Val_TS] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM16 Alter SP [BA999].[dbo].[v_OLAPRefresh_OutputJRCONV_w/Val_TS] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM17 Alter SP [BA999].[dbo].[v_OLAPRefresh_JRStockConv_TS] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM18 Alter SP [BA999].[dbo].[v_OLAPRefresh_OutputSR2025_CONV_TS] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM19 Alter SP [BA999].[dbo].[v_OLAPRefresh_SRStockRwRsCONV_TS] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM20 Alter SP [BA999].[dbo].[v_OLAPRefresh_JRStockConv_TS_w/o_T] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM21 Alter SP [BA999].[dbo].[v_OLAPRefresh_SRStockRwRsCONV_TS_w/o_T] | 75% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Create File Refresh | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM22 Create File OLAP2025 ST - TS | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM22 Create File OLAP2025 CNV PROD - TS | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
WRICEF-OLAP-LAM24 Create File OLAP2025 LAI - TS | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.3 Run Scenario Test and Integration Test | 16.5% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.3.1 Scenario Testing SAP | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
DEV AIX | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.3.1.1 Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | 0% | Ana, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20; W8 27; W9 30 to W9 3
RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | 0% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | 0% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | 0% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | 0% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | 0% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060 | 0% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M | 0% | Mela, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | 0% | Aryo , Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-11 Hard Code Order Type ZPP_BD | 0% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | 0% | Aryo, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-13 Hard Code Order Type ZPP_TB | 0% | Rafly, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | 0% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | 0% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-23 Hard Code Material Group ZTPP016N | 0% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS | 0% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-27 Hard Code Material Group ZPP016N | 0% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-28 One Button | 0% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | 0% | Rafli, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | 0% | Aryo, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | 0% | Mela, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | 0% | Rafli, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.2 Material Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | 0% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process PR PO CUstomer Stock (ZIC004SL) | 0% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | 0% | Yuli, Fany | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.3 Material Management-Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-01 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | 0% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-02 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 0% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-03 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 0% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-04 Planning Jumbo Roll For Subcontracting Laminatre (ZPP002) | 0% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.4 Sales & Distribution-Material Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | 0% | Randi, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.5 Sales & Distribution-Material Management-Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | 0% | Alif, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | 0% | Wahyu, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | 0% | Randi | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.6 Sales & Distribution | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | 0% | Wahyu | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-02 ZSD100 Conversion Upload Sales Order | 0% | Tyas | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | 0% | Wahyu | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | 0% | Tyas | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | 0% | Malak | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-06 ZOLAPSLS | 0% | Malak | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.7 Quality Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-QM-LAMI2&3-01 Validating 24-Hour Aging of Laminate Subcont CKI (ZQA32) Validating 24-Hour Aging of Laminate Subcont CKI (ZQA32) | 0% | Rafli | bar: W6 9 to W6 13; W7 16 to W7 20
QA 320 | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.3.1.1 Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-01 Hard Code Order Type ZPP041 | 0% | Ana, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20; W8 27; W9 30 to W9 3
RICEFW-PP-LAMI2&3-02 Hard Code Order Type ZPP060 | 0% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-03 Hard Code Order Type ZPP001 | 0% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-04 Hard Code Order Type ZPP011 | 0% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-05 Hard Code Order Type ZPP002 | 0% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-06 Hard Code Order Type ZTPP002 | 0% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-07 Hard Code Order Type ZTPP060 | 0% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-09 Hard Code Order Type ZCOR6M | 0% | Mela, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-10 Hard Code Order Type ZPP019 | 0% | Aryo , Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-11 Hard Code Order Type ZPP_BD | 0% | Aryo, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-12 Hard Code Order Type ZPP_RC | 0% | Aryo, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-13 Hard Code Order Type ZPP_TB | 0% | Rafly, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-21 Hard Code Material Group ZPP016 | 0% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-22 Hard Code Material Group ZPP016CX | 0% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-23 Hard Code Material Group ZTPP016N | 0% | Rafly, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-24 Hard Code Order Type ZPP_RS | 0% | Mela, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-27 Hard Code Material Group ZPP016N | 0% | Rafly, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-28 One Button | 0% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-29 Planning Jumbo Roll for Subcontracting Laminate | 0% | Rafli, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-30 New Design Label Sliit Roll Customer Stock for Subcontracting Laminate | 0% | Aryo, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-31 New Design Label Jumbo Roll for Subcontracting Laminate | 0% | Mela, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-32 New Design Label Slitt Roll for Subcontracting Laminate | 0% | Rafli, Fani | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-PP-LAMI2&3-33 Hard Code Recycle Execution ZPP_RE | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.2 Material Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process for Receiving Customer Stock (ZMM056SL) | 0% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-01 Mass Process PR PO CUstomer Stock (ZIC004SL) | 0% | Alif, Dila | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MM-LAMI2&3-02 New Design Label HU for Subcontracting Laminate | 0% | Yuli, Fany | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.3 Material Management-Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-01 Jumbo Roll Execution Subcontracting Laminate (ZPP041SL) | 0% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-02 Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 0% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-03 Cancellation Adjustment Jumbo Roll to Slitt Roll for Laminate (ZPP001SL) | 0% | Ana, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-MMPP-LAMI2&3-04 Planning Jumbo Roll For Subcontracting Laminatre (ZPP002) | 0% | Rafli, Budi | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.4 Sales & Distribution-Material Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | 0% | Randi, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.5 Sales & Distribution-Material Management-Production Planning | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-01 Report Pending Order Enhancement for Subcontracting Laminate (ZPP005N) | 0% | Alif, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | 0% | Wahyu, Ryan | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | 0% | Randi | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.6 Sales & Distribution | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | 0% | Wahyu | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-02 ZSD100 Conversion Upload Sales Order | 0% | Tyas | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | 0% | Wahyu | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | 0% | Tyas | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL | 0% | Malak | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-SD-LAMI2&3-06 ZOLAPSLS | 0% | Malak | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.1.7 Quality Management | 0% | bar: W6 9 to W6 13; W7 16 to W7 20
RICEFW-QM-LAMI2&3-01 Validating 24-Hour Aging of Laminate Subcont CKI (ZQA32) Validating 24-Hour Aging of Laminate Subcont CKI (ZQA32) | 0% | Rafli | bar: W6 9 to W6 13; W7 16 to W7 20
3.3.2 Integration Testing SAP | 49.5% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
DEV AIX | 99% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
QA 320 | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
3.3.3 Scenario Testing NON SAP | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UX TOOL | 0% | bar: W11 16 to W11 17; W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UT-UXTOOL- .. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UT-UXTOOL- .. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
OLAP | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UT-OLAP- .. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UT-OLAP- .. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
Meeting Pagi | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UT-Meeting Pagi- .. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UT-Meeting Pagi- .. | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
IT Inventory | 0% | bar: W6 9 to W6 13; W7 16 to W7 20; W8 23 to W8 27
UT-IT INV- .. | 0%
UT-IT INV- .. | 0%
3.4 Quality Assurance Environment (QAS): Roles and Transport | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.4.1 SAP Configuration and Development (RICEFW) Objects | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Material Management | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Sales and Distribution | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Quality Management | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Finance and Accounting | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Plan Maintenance | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Production Planning | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.4.2 SAP Set up Role Assignment / Authorizations in QAS | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Material Management | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Sales and Distribution | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Quality Management | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Finance and Accounting | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Plan Maintenance | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Production Planning | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.4.3 NON SAP | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.5 Quality Assurance Environment (QAS): Data Load | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.5.1 SAP Master Data | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Material Management | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Sales and Distribution | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Quality Management | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Finance and Accounting | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Plan Maintenance | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
Production Planning | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.5.2 Non SAP | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
UX TOOL.. | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.6 Prepare End User Training and User Acceptance Test Delivery | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.6.1 Prepare dokumen EUT | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
3.6.2 Prepare dokumen UAT | 0% | bar: W7 16 to W7 20; W8 23 to W8 27
DEPLOY | 0%
4.1 Pre Go-Live End-User Training Delivery | 0% | bar: W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 17
4.2 User Acceptance Test (UAT) | 0% | bar: W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 17
4.3 Production System Environment | 0% | bar: W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 17
4.4 Helpdesk Setup | 0% | bar: W9 30 to W9 3; W10 6 to W10 10; W11 13 to W11 17
GO LIVE AND SUPPORT | 0% | bar: W12 20 to W12 24; W13 27 to W13 31; W14 3 to W14 7
Go Live | 0% | bar: W12 20 to W12 24; W13 27 to W13 31; W14 3 to W14 7
Post Go-Live End-User Training Delivery | 0% | bar: W07 16; W12 20 to W12 24; W13 27 to W13 31; W14 3 to W14 7
Support After Go Live | 0% | bar: W07 16; W12 20 to W12 24; W13 27 to W13 31; W14 3 to W14 7
37.75%
*WBS ini bisa berubah sewaktu waktu menyesuaikan dengan Situasi, Kondisi atau untuk kebutuhan memperbaiki management project.
LEGEND
Planned Milestone
Planned
In Progress
Finish
Solutions are discovered and evaluated
Project Charter, Project Management Plan, Project Organization, and WBS is Defined
0 of 0 Enhancement (RICEFW) Design is completed and documented
0 of 0 Business Blueprint Design is approved
Configuration is completed and documented
Business Process Map is Completed
Configuration Design is completed and documented
0 of 0 Business Blueprint Design is documented
Authorization Design is completed and documented
Configuration is Finished and Documented
Enhancement is Finished and Documented
Testing is Executed and OK
All Configuration and Enhancment are Validated
Data load successfully validated
EUT and UAT are Prepared
EUT are Well Executed
UAT are Well Executed
Production System Environment are Ready and Documented
Helpdesk setup are Ready and Documented
Go Live

## Copy of Milestones General (Tea (hidden)
ACTIVITY |  | 2024
|  | NOV | DES |  |  | JAN |  | FEB
PREPARE
Project Initiation | [6 empty] | ` |  | `
Discovery and Evaluation
Business Process Map
EXPLORE |  |  |  | 10 | 12
Business Blueprint Design
Business Blueprint Confirmation & Finalization
Enhancement (RICEF) Design
Configuration Design
Authorization Requirements and Design
REALIZE
Configuration and Documentation
Enhancement (RICEFW) Development
Run Scenario Test and Integration Test
Quality Assurance Environment (QAS): Roles and Transport
Quality Assurance Environment (QAS): Data Load
Prepare End User Training and User Acceptance Test Delivery
DEPLOY
Pre Go-Live End-User Training Delivery
User Acceptance Test (UAT)
Production System Environment
Helpdesk Setup
RUN
Go Live
Post Go-Live End-User Training Delivery
Support After Go Live
Done
In Progress
Planned
Finished Milestone
Planned Milestone
EXPLORE
PREPARE
REALIZE
RUN
RUN
DEP

## Sheet4 (1) (hidden)
ACTIVITY |  | PIC | Desember | [11 empty] | Januari
|  |  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
SERVER DEV NC
SAP MM
CONFIG-MM..
CONFIG-MM..
SAP PP
CONFIG-PP..
CONFIG-PP..
SAP SD
CONFIG-PP..
CONFIG-PP..
SAP FI
CONFIG-PP..
CONFIG-PP..
SAP CO
CONFIG-PP..
CONFIG-PP..

## SD (1) (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 25%
|  |  |  | Planned | 0%
W01 (08 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 50%
|  |  |  | Planned | 0%
W02 (11 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 75%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcon |  | In Progress | 50%
W02 (12 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM01 Configuration List | Configuration List for New Production Line Laminator #2 & #3 are Listed |  | In Progress | 75%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W02 (13 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W02 (14 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W02 (15 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (18 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (19 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (20 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (21 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W03 (22 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (25 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (26 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (28 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W04 (29 November 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont |  | In Progress | 50%
W07 (19 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 1, 2, 4, 5, 6 |  | Done | 100%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 7 A B C (cycle 2) |  | In Progress | 25%
W07 (20 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 7 A B C (cycle 2) |  | Done | 100% | 2024-12-20
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 8 A B (cycle 2) |  | In Progress | 0% | 2024-12-23
W08(23 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Integration Testing for Subcont scenario 8 A B (cycle 2) |  | Done | 100% | 2024-12-23
Tyas, Randi | 2.1 Business Blueprint Design | Update Business Blueprint |  | In Progress | 0% | 2024-12-24
W08(26 Desember 2024)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | Update Business Blueprint |  | In Progress | 50%
W09(03 Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | SD Organizational Unitz |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SD General Settings |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDGI01 Reverse Goods Movement |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDCM01 Release Delivery Block karena Terms of Payments |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO11 Sales with Down Payment |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO27 Sales Order Inventory |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO01 Domestic Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO02 Domestic Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO07 Export Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO08 Export Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO13 Domestic Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO14 Domestic Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO17 Export Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO18 Export Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | Integration Testing | Create SO |  | Done | 100%
Tyas, Randi | Integration Testing | Transaksi Penjualan |  | Planned | 0%
W10(06 Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | 2.1 Business Blueprint Design | SD Organizational Unitz |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SD General Settings |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDGI01 Reverse Goods Movement |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDCM01 Release Delivery Block karena Terms of Payments |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO11 Sales with Down Payment |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO27 Sales Order Inventory |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO01 Domestic Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO02 Domestic Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO07 Export Sales Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO08 Export Sales Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO13 Domestic Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO14 Domestic Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO17 Export Sample Order Finished Goods (1st Grade) |  | Done | 100%
Tyas, Randi | 2.1 Business Blueprint Design | SDSO18 Export Sample Order Finished Goods (2nd Grade) |  | Done | 100%
Tyas, Randi | Integration Testing | Create SO |  | Done | 100%
Tyas, Randi | Integration Testing | Transaksi Penjualan |  | Planned | 0%
W11(13Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait transport posting (Free To So, So To So, So To Free) for RM |  | Done | 100%
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle |  | In Progress | 50%
Tyas, Randi | Integration Testing | Transaksi Penjualan for scenario 10A, 10B, 11A, 11B, 12A, 12B |  | Done | 100%
W11(14Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle |  | In Progress | 50%
Tyas, Randi | Integration Testing | Transaksi Penjualan for scenario 13A, 13B |  | In Progress | 50%
Tyas, Randi | Integration Testing | Transaksi Penjualan for scenario 10C, 11C, 12C, 13C |  | Planned | 0%
W13(31 Januari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait DO Disposal for recycle |  | Done | 100%
Tyas, Randi, Wahyu | Integration Testing | Transaksi Penjualan for scenario 13A, 13B |  | Done | 100%
Tyas, Randi, Wahyu | Integration Testing | Transaksi Penjualan for scenario 10C, 11C, 12C, 13C |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config SO Type, DO Type, Billing Type for LAM SUBCONTRACTED (DEV NC) |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config SO Type, DO Type for Recycle Disposal (DEV NC) |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config Division for OUTSOURCE LAMINATE, LAM SUBCONTRACTED, REC SUBCONTRACTED (DEV NC) |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Config AAG Material for LAM SUBCONTRACTED |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Transaksi Penjualan for scenario 14A, 14B, 14C |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | In Progress | 25%
W14(03 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Transaksi Penjualan for Recycle Subcont all scenario |  | Done | 100%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | In Progress | 50%
W14(04 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | In Progress | 50%
Tyas, Randi, Wahyu | Enhancement (RICEFW) Design | WRICEF enhancement Tcode SD |  | Planned | 0%
W15(14 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Discovery terkait Tcode SD |  | Done | 100%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 25%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 25%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 25%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | Planned | 0%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 |  | In Progress | 25%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | Planned | 0%
W16(17 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 50%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | Planned | 0%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | Planned | 0%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | Planned | 0%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | Planned | 0%
W16(18 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 50%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | In Progress | 50%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | In Progress | 25%
W16(19 Februari 2025)
Team | Activity in WBS | Target |  | Status | Status (%) | Target (Date)
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | Done | 100%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | Done | 100%
Tyas | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | Done | 100%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 |  | Done | 100%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | Done | 100%
Wahyu | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | Done | 100%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont |  | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | In Progress | 25%
W16(20 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont |  | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | In Progress | 50%
Tyas, Randi, Wahyu | DISC-SD-LAM17 Subcont CKI | Transaksi Penjualan for scenario 9 dan 10 (Step 2) |  | Done | 100%
Randi, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | In Progress | 50%
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | In Progress | 50%
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 50%
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 50%
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 25%
W16(21 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-05 ZOLAP_SALES_DETAIL |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-06 ZOLAPSLS |  | In Progress | 50%
Malak | Enhancement (RICEFW) Design | RICEFW-SD-LAMI2&3-08 ZOLAP SALES DETAIL IT |  | In Progress | 50%
Randi | Enhancement (RICEFW) Design | RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont |  | In Progress | 25%
Tyas, Randi, Wahyu | Configuration Design | List Configuration Design SD for new SO Type, DO Type, Billing Type |  | Done | 100%
Randi, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) |  | Done | 100%
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) |  | In Progress | 75%
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor |  | In Progress | 75%
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO |  | In Progress | 75%
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC | RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item |  | In Progress | 50%
Tyas, Randi, Wahyu | Blueprint Confirmation | Business Blueprint & Business Processes are confirmed by Mr. Lai, PPIC, CKI |  | Done | 100%
Randi | Business Processes Confirmation w/ Pak Garry | Business Processes are confirmed by Pak Garry |  | Done | 100%
W17(24 Februari 2025)
Team | Activity in WBS | Target | Deliverables | Status | Status (%) | Target (Date)
Tyas, Randi, Wahyu | Configuration Design | Review List Configuration Design SD for new SO Type, DO Type, Billing Type | Design Configuration is Reviewed | Planned | 0%
Randi | Enhancement (RICEFW) Design | Create RICEFW-SDMMPP-LAMI2&3-03 Report Jual Recycle Subcont | RICEFW is created | In Progress | 25%
Wahyu, Ryan | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | RICEFW has been enhancement and tested | In Progress | 75%
Wahyu, Budi | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW has been enhancement and tested | In Progress | 75%
Wahyu, Fadila | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW has been enhancement and tested | In Progress | 75%
Tyas, Ryan | Enhancement (RICEFW) Development DEV NC | Testing RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW has been enhancement and tested | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SD Organizational Unitz | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SD General Settings | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDGI01 Reverse Goods Movement | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDCM01 Release Delivery Block karena Terms of Payments | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO11 Sales with Down Payment | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO27 Sales Order Inventory | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO01 Domestic Sales Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO02 Domestic Sales Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO07 Export Sales Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO08 Export Sales Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO13 Domestic Sample Order Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO14 Domestic Sample Order Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO17 Export Sample Order Finished Goods (1st Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | 2.1 Business Blueprint Design | Revise SDSO18 Export Sample Order Finished Goods (2nd Grade) | Blueprint is Revised | In Progress | 50%
Tyas, Randi, Wahyu | Intergration Testing New Production Line DEV 130 AIX | Intergration Testing for New Production Line | Intergration Testing for New Production Line Done | In Progress | 50%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-01 ZSD024 Delivery Order Monitor | RICEFW is reviewed | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-03 ZSD113 Upload create SO | RICEFW is reviewed | Planned | 0%
Tyas | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-04 ZSD115 Upload Add SO Item | RICEFW is reviewed | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SD-LAMI2&3-07 Enhancement Report Data Billing ZSD507 | RICEFW is reviewed | Planned | 0%
Randi | Enhancement (RICEFW) Design | Review RICEFW-SDMM-LAMI2&3-02 Enhancement for Outbound Delivery Order Creation for Subcont Laminator (ZSD013SL) | RICEFW is reviewed | Planned | 0%
Wahyu | Enhancement (RICEFW) Design | Review RICEFW-SDMMPP-LAMI2&3-02 Report Stock Overview with Characteristic Enhancement for Subcontractor (ZBMBC) | RICEFW is reviewed | Planned | 0%

## CO (1) (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Yuki, Munah, Haikal | 1.2.1 SAP Discovery and Evaluation | List discovery Project Laminator #2 #3 lengkap | Done | 100% | 2024-11-07
W01 (08 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal | DISC-CO-LAM01 Cost Center | Check Cost Center pada setiap server SAP (Cost Center Group dan Hierarchy) | Done | 100% | 2024-11-08
| DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Done | 100% | 2024-11-11
W02 (11 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Done | 100% | 2024-11-13
| DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (12 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM02 Activity Type | Check Actitivty Type untuk mapping ke Cost Center | Done | 100% | 2024-11-13
| DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (13 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (14 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM03 Profit Center | Check Profit Center pada setiap server SAP | Done | 100% | 2024-11-14
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | Done | 100% | 2024-11-15
W02 (15 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Haikal, Yuki | DISC-CO-LAM04 Relation between production lne code, cost center, and reporting | Discovery Relation between production line code, cost center, and reporting Laminator #2 #3 | In Progress | 25% | 2024-11-15
| DISC-CO-LAM04 Konfigurasi CO | Configuration List for New Production Line Laminator #2 & #3 are Discovered | In Progress | 25% | 2024-11-15

## Meeting Pagi (1) (hidden)
Daily Activity
W01 (07 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
|  |  | Done | 0%
|  |  | Done | 0%
W01 (08 November 2024)
Team | Activity in WBS | Target | Status | Status (%) | Target (Date)
Taufiq, Malak, Adit | DISC-NONSAP-LAM02 Meeting Pagi - Table List | Complate List of table Meeting Pagi | In Progress | 0%
Taufiq, Malak, Adit | DISC-NONSAP-LAM03 Meeting Pagi - SP and View List | Complate List of SP and View Meeting Pagi | In Progress | 0%

## WEEKLY (1) (hidden)
Last Week Target
W11 (20 Des - 24 Des 2021)
Team | Target | Status
Functional |  | DONE
Functional |  | DONE
This Week Target
W12 (27 Des - 31 Des 2021)
Team | Target | Status
Functional |  | IN PROGRESS

## DISCOVERY (1) (hidden)
Week# | Module | Discovery & Evaluation | PIC | Status (%) | Status (GCG) | Date | Status | Cancel Reason | Priority
W06 | Material Management |  |  | 0%
| Material Management |  |  | 0%
| Sales and Distribution |  |  | 0%
| Controlling |  |  | 0%
| Finance |  |  | 0%
| Quality Management |  |  | 0%
| Production and Planning |  |  | 0%